## Slide 1
Project Management Concepts

## Slide 2: Chapter Concepts
Definition of a project and its attributes
Key constraints within which a project must be managed
Life cycle of a project
Definition of project management
Elements of the project management process
Identification and engagement of stakeholders
Implications of global project management
Project Management Institute
Benefits of project management

## Slide 3: Learning Outcomes
Define what a project is
List and discuss the attributes of a project
Explain what is meant by project objective
Define what is meant by project deliverable
Provide examples of projects
Discuss project constraints
Describe the phases of the project life cycle
Define and apply Project Management
Discuss the steps of the planning process
Identify the three elements of the executing process
Create a stakeholder register
Discuss stakeholder engagement
Discuss some implications of global project management
Discuss the Project Management Institute
List benefits of project management techniques

## Slide 4: Project Integration Management
Project Management Knowledge Areas from PMBOK® Guide

## Slide 5: Project Attributes
Clear objective
Series of interdependent activities
Various resources
Specific time frame
Unique, one-time endeavour
Sponsor or customer
Degree of uncertainty

## Slide 6: Balancing Project Constraints

## Slide 7: Project Manager Actions
Prevent, anticipate, overcome
Have good planning and communication
Be responsible

## Slide 8: The Project Life Cycle

## Slide 9: Initiating phase
First phase
Identify need, problem, or opportunity
Determine if select project
Develop project charter
  Rationale
  Project objective
  Expected benefits
  General requirements and conditions
Decide if RFP needed

## Slide 10: Planning phase
Second phase
Show how project scope will be achieved
Plan the work and work the plan
Develop baseline plan
  What needs to be done – scope, deliverable
  How it will get done – activities, sequence
  Who will do it – resources, responsibilities
  How long it will take – durations, schedule
  How much it will cost – budget
  What the risks are
Have actual resources plan the work

## Slide 11: Performing phase
Third phase
Achieve project objectives
  Project manager leads
  Project team completes the project
Increase pace as more resources are added
Monitor and control progress
Take corrective action as needed
Manage and control changes with sponsor approval
Achieve customer satisfaction with acceptance of deliverable

## Slide 12: Closing phase
Final phase
Collect and make final payments
Recognise and evaluate staff
Conduct post project evaluation
Document lessons learned
Archive project documents
Record lessons learned

## Slide 13: Project Planning Process
Establish project objective
Define scope
Create WBS
Assign responsibility
Define specific activities
Sequence activities
Estimate activity resources
Estimate activity durations
Develop project schedule
Estimate activity costs
Determine budget

## Slide 14: Create WBS and assign responsibility

## Slide 15: Sequence activities

## Slide 16: Develop the project schedule

## Slide 17: Determine budget

## Slide 18: Execute the project plan
Perform the work
Monitor and control progress
Control changes

## Slide 19: Stakeholder Engagement
Who are stakeholders?
Customer/sponsor
Project team including subcontractors and suppliers
organisations or groups
  Supportive or adversarial
  Want to be kept informed because of potential impact
What to create
Stakeholder register
  Created as identify stakeholders
  Include
    Key contact information
    Role or specific topics of interest
    Expectations
    Any known issues
    Areas of potential influence
Issue log

## Slide 20: Global Project Management
Globalisation
Adds a dimension of complexity
Changes project dynamics
Requires awareness of factors
  Cultural differences
  Currency
  Codes and regulations
  Business organisation
  Political relations
  Workforce availability
Helpful competencies
Foreign language skills
Knowledge of
  Cultures
  Geography
  World history and contemporary events
  International economics
Awareness of
  Customs and etiquette
  Geopolitical environment
Technology adoption and translation software

## Slide 21: Project Management Associations
Project Management Institute
Worldwide non-profit association of practitioners
  ~500 000 members in nearly 200 countries
  ~270 chapters in >80 countries
>30 online communities for collaboration
PMBOK® Guide
PMI Code of Ethics and Professional Conduct
Certifications
www.pmi.org
Global associations
Links available at www.cengagebrain.com

## Slide 22: Critical Success Factors
Planning and communication are critical to successful project management. They prevent problems from occurring or minimise their impact on the achievement of the project objective when they do occur.
Taking the time to develop a well thought-out plan before the start of the project is critical to the successful achievement of any project.
A project must have a clear objective of what is to be achieved and defined in terms of end product or deliverable, schedule, and budget; and is agreed upon by the customer.
Involve the sponsor or customer as a partner in the successful outcome of the project through active participation during the project.
Achieving customer satisfaction requires ongoing communication with the customer to keep the customer informed and to determine whether expectations have changed.
The key to effective project control is measuring actual progress and comparing it to planned progress on a timely and regular basis and taking any needed corrective action immediately.
After the conclusion of a project, the project performance should be evaluated to learn what could be improved if a similar project were to be undertaken in the future. Feedback should be obtained from the sponsor or customer and the project team.
Learning and understanding the culture and customs of other project participants will demonstrate respect, help build trust, and aid in developing an effective project team; and it is critical for successful global project management.

## Slide 23: Summary
A project is an endeavour to achieve a specific objective through a unique set of interrelated activities and the effective utilisation of resources.
The successful achievement of the project objective could be constrained by many factors, including scope, quality, schedule, budget, resources, risks, customer satisfaction, and stakeholder support.
The project life cycle has four phases: initiating, planning, performing, and closing the project.
Project management is planning, organising, coordinating, leading, and controlling resources to achieve the project objective. The project management process involves two major functions: first establishing a plan and then executing that plan to achieve the project objective.
Globalisation changes the dynamics of a project and adds a layer of complexity that can adversely affect the project outcome if the project participants are not aware of what they can encounter regarding cultural differences and multinational economic transactions.
The Project Management Institute is a premier worldwide non-profit association for practitioners in the project management profession.
The ultimate benefit of implementing project management techniques is having a satisfied customer – whether you are the customer of your own project or a business (contractor) being paid by a customer to perform a project.