## Slide 1
Defining Scope, Quality, Responsibility and Activity Sequence

## Slide 2: Chapter Concepts
Clearly defining the project objective
Preparing a project scope document
Understanding the importance of planning for quality
Creating a work breakdown structure
Assigning responsibility for work items
Defining specific activities
Creating a network diagram
Utilising a project management methodology called the systems development life cycle for information systems development projects

## Slide 3: Learning Outcomes
Establish a clear project objective
Prepare a project scope document
Discuss the importance and elements of a project quality plan
Develop a work breakdown structure
Prepare a responsibility assignment matrix
Describe how to define specific activities
Create a network diagram

## Slide 4: Project Integration Management Project Scope Management Project Quality Management Project Time Management
Project Management Knowledge Areas from PMBOK® Guide

## Slide 5: Establish Project Objective
Planning process is based on the project objective
  Establishes what is to be achieved
  Often stated in the project charter or RFP
  Is the tangible end product
Project objective includes
  Expected benefits
  Primary project end product or deliverable
  Date required to be completed
  Budget
Changes agreed upon by customer and contractor

## Slide 6: Define Project Scope
Project scope
Defines what needs to be done
Includes
  Items contained in project charter, RFP, proposal
  More detail
Establishes common understanding of scope with stakeholders
Project scope document
Usually contains
  Customer requirements
  Statement of Work
  Deliverables
  Acceptance criteria
  Work Breakdown Structure
Establishes baseline
Change control system to avoid scope creep

## Slide 7: Plan for Quality
Complete work according to specifications and standards
Plan for assuring quality as project progresses
Include
  References for specifications and standards
  Written procedures for quality tools and techniques
Key aspects
  Monitor as the project progresses
  Do work right the first time rather than rework

## Slide 8: Create Work Breakdown Structure
Deliverable-oriented hierarchical decomposition
Organise project work and deliverables
Create logical groupings
Subdivide into more manageable components
  Deliverable is output of work package
  Resource requirements and durations can be assigned
  Accountability can be assigned
  Project manager can monitor and control
Graphic chart or indentured list

## Slide 9: WBS with breakdown to different levels

## Slide 10: WBS with breakdown to different levels

## Slide 11: WBS with breakdown to different levels

## Slide 12: WBS
Graphic Chart
Indentured List

## Slide 13: Assign Responsibility
Responsibility assignment matrix
  Designate responsible individuals
    P = Primary responsibility
    S = Support responsibility
  Associates responsibility
    For each work item
    For each individual
Only one primary per work item

## Slide 14: Define Activities
Responsible resources define activities
  Breakdown work packages to work items
  Level needed to perform deliverable
  May not be able to define all
Comprehensive activity list
  Not always require expenditure of effort
  Could be wait time

## Slide 15: Sequence Activities
Network diagram
  Defines the sequence of activities and relationships
  Tool for arranging order
Common techniques
  PERT
  CPM
  PDM

## Slide 16: Network principles
Activities
  Represented by a box
  Consume time
  Described by verb
Relationships
  Linked in serial sequence
  Complete concurrently

## Slide 17: Loops
Illogical relationship among activities
Perpetually repeats itself
Not acceptable

## Slide 18: Laddering
Ladder activities
Allow for shortest possible time for completion
Best use of the three workers and experts
Set of repeating activities
Serial sequence
  One work
  Two wait
Can be performed at same time
Would need triple resources

## Slide 19: Create network diagram
Tips and techniques
Logical sequence of activities
Show dependent relationships
Elaborate as project progresses
Use subnetworks for similar activity sequences and relationships
Development of diagram
Questions to answer
  Finish before next start?
  Done concurrently?
  Cannot be started next?
Guidelines for detail level
  Define each work package
  Draw summary level network then add detail
  Detail to responsibility or deliverable change
  Duration less than project progress review

## Slide 20: Planning for Information Systems Development
Definition
Computer-based system
  Accepts data as input
  Processes the data
  Produces useful information
Examples
  Computerised order entry
  E-commerce
  Automatic teller machines
  Billing, payroll, and inventory
Process
Plan, execute, and control
Systems development life cycle
  Problem definition
  System analysis
  System design
  System development
  System testing
  System implementation

## Slide 21: An IS example: Internet applications development for Ukudala Office Designs
Ukudala Office Designs
Large number of sales representatives
Sell office furniture to major companies
State assignments in four regions
Management monitor state and regional sales
Build web-based IS system to track prices, inventory, and competition
Project
Project manager identified
WBS follows SDLC
Responsibility assignment matrix completed
List of tasks compiled and predecessors identified
Network diagram created

## Slide 22: IS example: WBS follows SDLC

## Slide 23: IS example: responsibility assignment matrix

## Slide 24: IS example: task list and predecessors

## Slide 25: IS example: network diagram

## Slide 26: Project Management Information Systems
Wide variety of systems available
Plan and control projects in interactive mode
Plan and test different options
Create reports, diagrams, and charts
Interface with other software applications
Appendix A has additional information

## Slide 27: Critical Success Factors
Plan the work and then work the plan. It is important to develop a plan before starting to perform the project. Taking the time to develop a well-thought-out plan is critical to the successful achievement of any project.
Participation builds commitment. By participating in the planning of the work, individuals will become committed to achieving it according to the plan.
The project must have a clear objective of what is to be achieved. The objective should be defined in terms of end product or deliverable, schedule, and budget, and it must be agreed upon by the customer and the project team that will perform the project.
The project scope document is valuable for establishing a common understanding and agreement among project stakeholders regarding the scope of the project.
Having a quality plan at the outset of the project is extremely beneficial because it will help prevent incurring additional costs and schedule extensions due to rework caused by work and deliverables that fail to meet quality requirements and customer expectations.
The key to quality control is to monitor the quality of the work early and regularly throughout the performance of the project, rather than waiting until all the work is completed before checking or inspecting for quality.
The network diagram is also is a communication tool for the project team because it shows who is responsible for each activity and how each person’s work fits into the overall project.

## Slide 28: Summary
The planning process is based on the project objective, which establishes what is to be achieved.
The project scope defines what needs to be done.
The project scope document usually contains the customer requirements, statement of work, deliverables, acceptance criteria, and a work breakdown structure.
The quality plan must include or reference the specifications, industry or government standards, and codes that must be used and met during the performance of the project work.
The work breakdown structure establishes the framework for how the work will get done to produce the project deliverables.
A responsibility assignment matrix defines who will be responsible for the work.
Activities define more specifically how the work will get done.
A network diagram defines the sequence of how and when the activities will be performed.
Project planning is a critical activity in developing an information system (IS).
A project management planning tool or methodology, called the systems development life cycle (SDLC), is often used to help plan, execute, and control IS development projects.
Numerous project management information systems are available to help project managers plan, track, and control projects in a completely interactive way.