Network Exercises

| Question 1 |  |  |
| --- | --- | --- |
|  | Activity; Duration (days); Predecessor(s). A; 2; -. B; 2; A. C; 4; A. D; 1; B. E; 3; C,D. F; 2; C,D. G; 4; E. H; 5; F,G. |  |
| 1.1 | Draw an Activity-on-Node Network Diagram for the following table | [6] |
| 1.2 | Determine duration of the project (in days). As well as the Critical Path (You can write your response on the same diagram as for question 1.1). | [6] |
| 1.3 | Determine slacks for any two non-critical activities. | [4] |
| 1.4 | Explain the significance of the critical path to a manager scheduling project activities. | [4] |
| Question 2 |  |  |
|  | Given the following table, with all durations in days. |  |
| 2.1 | Draw an Activity on Node network corresponding to the table above. | [6] |
| 2.2 | Calculate the Expected Durations, and the Finish Time for the project. | [12] |
| 2.3 | Draw up an “activity-on-arrow” diagram for the table below Activity; Predecessor. A; -. B; -. C; A. D; B, G. E; C, D. F; D. G; A. H; E. | [12] |