## Contents
GCP ERP Migration: Supporting Workbook
Karoo Retail Group (Pty) Ltd (fictitious client) ¦ Supports the SPMP for PFD473S Assessment T3 ¦ Prepared by Thabiso Matsaba (220296006) ¦ 09 October 2026
Sheet | Contents | SPMP reference | Self-check
Business Case | Weighted option scoring, run-cost comparison, 5-year NPV, IRR, payback, BCR, ROI | Section 2 (Tables 9-12) | n/a
WBS | Level-3 WBS dictionary: 95 work packages with owner, effort and dates; phase totals | Section 4 (Table 15), 5.2 | OK
Gantt | 26-week Gantt chart with critical path and milestones (conditional formatting) | Section 5.3, Appendix A.1 | n/a
PERT | Three-point estimates, critical path, go-live probability, float analysis | Section 5.4, Appendix A.2-A.3 (Tables 49-50) | OK
Resources | Staffing, hours, allocation, rates and labour cost | Section 5.5 (Table 18), 13.2, Appendix E | OK
Budget | Non-labour estimate, budget summary and reserves, phase allocation | Section 6 (Tables 19-21) | OK
Cash Flow | Monthly cash flow projection, contingency, cumulative baseline and chart | Appendix B (Table 51, Figure 5) | OK
Risk Register | 17 risks scored P x I with rating, response, owner and EMV | Section 11, Appendix C (Table 52) | OK
RACI | Responsibility assignment for 20 activities across 9 roles | Appendix D (Table 53) | OK
EVM | Earned value worked example with CPI, SPI, EAC, VAC, TCPI | Sections 6.5, 14.1-14.2 | n/a
All self-checks |  |  | OK
Legend
Blue text | Input value (estimate or assumption); change it and dependent cells update
Black text | Formula
Green text | Formula that links to another sheet
Yellow fill | Key assumption (rates, hurdle rate, approved baseline figures)
OK / CHECK | Self-check against the figures stated in the SPMP
All amounts in South African Rand (ZAR), excluding VAT at 15%. Figures are planning estimates for a fictitious client.

## Business Case
GCP ERP Migration: Options Scoring and Financial Appraisal
Supports SPMP Section 2.2 (Table 9) and 2.3 (Tables 10 to 12). R million unless stated.
Criterion | Weight | A: Do nothing | B: On-prem refresh | C: GCP replatform (selected) | D: Replace with SaaS ERP
Strategic alignment | 25% | 1 | 2 | 5 | 5
Financial return | 25% | 1 | 2 | 4 | 3
Risk (5 = low) | 15% | 1 | 3 | 3 | 2
Feasibility in 6 months | 15% | 5 | 4 | 4 | 1
Compliance and security | 10% | 1 | 3 | 4 | 4
Scalability and agility | 10% | 1 | 2 | 5 | 5
Weighted score (out of 5) | 100% | 1.6 | 2.55 | 4.2 | 3.35
Selected option (highest score) |  | C: GCP replatform (selected)
Annual run-cost line (R) | Current on-prem | Post-migration GCP
Hardware maintenance and depreciation | 1600000 | 0
Data centre, power, backup power | 1200000 | 0
Infrastructure staff (allocated) / MSP managed services | 1500000 | 700000
Software licences / cloud licences | 1400000 | 600000
DR and backup | 500000 | 0
GCP consumption (committed use discounts after stabilisation) | 0 | 2600000
Total | 6200000 | 3900000
Annual run-cost saving |  | 2300000
Hurdle rate (assumed WACC, to be confirmed by Finance) | 11%
Investment: total funding envelope (R m) | 8.1236
Annual BI / decision-making benefit (R m) | 1.8
Avoided hardware refresh in Year 1, base case only (R m) | 5.5
Year | Discount factor | Base case: net flow | Base case: PV | Conservative: net flow | Conservative: PV
0 | 1 | -8.1236 | -8.1236 | -8.1236 | -8.1236
1 | 0.9009 | 9.6 | 8.6486 | 4.1 | 3.6937
2 | 0.81162 | 4.1 | 3.3277 | 4.1 | 3.3277
3 | 0.73119 | 4.1 | 2.9979 | 4.1 | 2.9979
4 | 0.65873 | 4.1 | 2.7008 | 4.1 | 2.7008
5 | 0.59345 | 4.1 | 2.4332 | 4.1 | 2.4332
Metric | Base case | Conservative case
NPV (5 years) R m | 11.9845 | 7.0296
IRR | 77.03% | 41.61%
Payback (months after go-live) | 10.1545 | 23.7764
Benefit-cost ratio (PV benefits / investment) | 2.4753 | 1.8653
5-year ROI (undiscounted) | n/a | 152.4%
SPMP Table 12 reports NPV R11.99 m / R7.03 m, IRR about 77% / 41%, payback about 10 / 24 months, BCR 2.48 / 1.87 and ROI 152%.

## WBS
GCP ERP Migration: Work Breakdown Structure and Dictionary (Level 3)
Owner = accountable role; effort covers all roles working on the package. Total matches the 6,880 planned hours in SPMP Section 5.5. Blue = input (effort, start/end week); dates are formulas from the week numbers.
WBS ID | Level | Work package | Level-1 phase | Level-2 group | Owner | Effort (h) | Start week | End week | Start date | End date
1.1.1 | 3 | Charter and mandate approved | 1.0 Initiation and Planning | 1.1 Project initiation | PM | 40 | 1 | 2 | 2026-10-05 | 2026-10-16
1.1.2 | 3 | Stakeholder register and engagement plan | 1.0 Initiation and Planning | 1.1 Project initiation | BA | 40 | 1 | 2 | 2026-10-05 | 2026-10-16
1.1.3 | 3 | Governance set-up (SteerCo, CCB, RACI) | 1.0 Initiation and Planning | 1.1 Project initiation | PM | 30 | 1 | 2 | 2026-10-05 | 2026-10-16
1.2.1 | 3 | SPMP and management plans | 1.0 Initiation and Planning | 1.2 Project planning | PM | 120 | 1 | 3 | 2026-10-05 | 2026-10-23
1.2.2 | 3 | Schedule, cost and resource baselines | 1.0 Initiation and Planning | 1.2 Project planning | PM | 80 | 1 | 3 | 2026-10-05 | 2026-10-23
1.2.3 | 3 | Tooling and environments | 1.0 Initiation and Planning | 1.2 Project planning | CE | 50 | 1 | 3 | 2026-10-05 | 2026-10-23
1.3.1 | 3 | Onboarding and access provisioning | 1.0 Initiation and Planning | 1.3 Team mobilisation | CE | 30 | 1 | 2 | 2026-10-05 | 2026-10-16
1.3.2 | 3 | MSP and vendor RFQ issued | 1.0 Initiation and Planning | 1.3 Team mobilisation | PM | 30 | 1 | 2 | 2026-10-05 | 2026-10-16
2.1.1 | 3 | Migration Center discovery and inventory | 2.0 Discovery and Assessment | 2.1 Estate inventory | SA | 90 | 3 | 5 | 2026-10-19 | 2026-11-06
2.1.2 | 3 | Dependency and 14-interface mapping | 2.0 Discovery and Assessment | 2.1 Estate inventory | AD | 90 | 3 | 5 | 2026-10-19 | 2026-11-06
2.1.3 | 3 | Licence and support-status review | 2.0 Discovery and Assessment | 2.1 Estate inventory | SA | 30 | 3 | 5 | 2026-10-19 | 2026-11-06
2.2.1 | 3 | Data profiling and quality baseline | 2.0 Discovery and Assessment | 2.2 Data assessment | DE | 80 | 3 | 6 | 2026-10-19 | 2026-11-13
2.2.2 | 3 | POPIA data classification and DPIA scoping | 2.0 Discovery and Assessment | 2.2 Data assessment | SE | 50 | 3 | 6 | 2026-10-19 | 2026-11-13
2.2.3 | 3 | Volume, growth and cutover-window analysis | 2.0 Discovery and Assessment | 2.2 Data assessment | DE | 40 | 3 | 6 | 2026-10-19 | 2026-11-13
2.3.1 | 3 | Business and BI requirements | 2.0 Discovery and Assessment | 2.3 Requirements | BA | 90 | 3 | 5 | 2026-10-19 | 2026-11-06
2.3.2 | 3 | Non-functional requirements | 2.0 Discovery and Assessment | 2.3 Requirements | SA | 40 | 3 | 5 | 2026-10-19 | 2026-11-06
2.3.3 | 3 | Compliance requirements | 2.0 Discovery and Assessment | 2.3 Requirements | SE | 30 | 3 | 5 | 2026-10-19 | 2026-11-06
2.4.1 | 3 | 6R disposition per workload | 2.0 Discovery and Assessment | 2.4 Migration strategy | SA | 40 | 5 | 6 | 2026-11-02 | 2026-11-13
2.4.2 | 3 | TCO and GCP cost model | 2.0 Discovery and Assessment | 2.4 Migration strategy | SA | 40 | 5 | 6 | 2026-11-02 | 2026-11-13
2.4.3 | 3 | Migration and cutover approach | 2.0 Discovery and Assessment | 2.4 Migration strategy | SA | 30 | 5 | 6 | 2026-11-02 | 2026-11-13
2.4.4 | 3 | Assessment report and G2 pack | 2.0 Discovery and Assessment | 2.4 Migration strategy | PM | 50 | 5 | 6 | 2026-11-02 | 2026-11-13
3.1.1 | 3 | Solution architecture (HLD/LLD) | 3.0 Architecture and Landing Zone | 3.1 Target architecture | SA | 120 | 6 | 8 | 2026-11-09 | 2026-11-27
3.1.2 | 3 | Network and connectivity design | 3.0 Architecture and Landing Zone | 3.1 Target architecture | CE | 60 | 6 | 8 | 2026-11-09 | 2026-11-27
3.1.3 | 3 | Backup and DR design | 3.0 Architecture and Landing Zone | 3.1 Target architecture | CE | 40 | 6 | 8 | 2026-11-09 | 2026-11-27
3.1.4 | 3 | Security and identity architecture | 3.0 Architecture and Landing Zone | 3.1 Target architecture | SE | 60 | 6 | 8 | 2026-11-09 | 2026-11-27
3.2.1 | 3 | Resource hierarchy, Organization Policy, labelling | 3.0 Architecture and Landing Zone | 3.2 Landing zone build | CE | 80 | 7 | 9 | 2026-11-16 | 2026-12-04
3.2.2 | 3 | Hub-and-spoke network, firewall, DNS | 3.0 Architecture and Landing Zone | 3.2 Landing zone build | CE | 100 | 7 | 9 | 2026-11-16 | 2026-12-04
3.2.3 | 3 | Cloud VPN and Dedicated Interconnect connectivity | 3.0 Architecture and Landing Zone | 3.2 Landing zone build | CE | 60 | 7 | 9 | 2026-11-16 | 2026-12-04
3.2.4 | 3 | Monitoring, logging and Secret Manager | 3.0 Architecture and Landing Zone | 3.2 Landing zone build | CE | 70 | 7 | 9 | 2026-11-16 | 2026-12-04
3.2.5 | 3 | IaC pipelines and environments | 3.0 Architecture and Landing Zone | 3.2 Landing zone build | CE | 120 | 7 | 9 | 2026-11-16 | 2026-12-04
3.3.1 | 3 | Architecture Framework review | 3.0 Architecture and Landing Zone | 3.3 Landing zone validation | SA | 60 | 9 | 9 | 2026-11-30 | 2026-12-04
3.3.2 | 3 | Security baseline scan | 3.0 Architecture and Landing Zone | 3.3 Landing zone validation | SE | 80 | 9 | 9 | 2026-11-30 | 2026-12-04
3.3.3 | 3 | G3 approval | 3.0 Architecture and Landing Zone | 3.3 Landing zone validation | PM | 50 | 9 | 9 | 2026-11-30 | 2026-12-04
4.1.1 | 3 | Source-to-target mapping | 4.0 Build and Migration | 4.1 Data migration | DE | 160 | 9 | 11 | 2026-11-30 | 2026-12-18
4.1.2 | 3 | Replication and ETL pipelines | 4.0 Build and Migration | 4.1 Data migration | DE | 720 | 9 | 15 | 2026-11-30 | 2027-01-15
4.1.3 | 3 | Mock migration 1 | 4.0 Build and Migration | 4.1 Data migration | DE | 150 | 14 | 16 | 2027-01-04 | 2027-01-22
4.1.4 | 3 | Mock migration 2 (dress rehearsal) | 4.0 Build and Migration | 4.1 Data migration | DE | 150 | 17 | 20 | 2027-01-25 | 2027-02-19
4.1.5 | 3 | Reconciliation reports | 4.0 Build and Migration | 4.1 Data migration | DE | 80 | 14 | 20 | 2027-01-04 | 2027-02-19
4.2.1 | 3 | ERP application-tier replatform to Compute Engine | 4.0 Build and Migration | 4.2 Application modernisation | AD | 180 | 9 | 19 | 2026-11-30 | 2027-02-12
4.2.2 | 3 | Database replatform to Cloud SQL for SQL Server | 4.0 Build and Migration | 4.2 Application modernisation | CE | 120 | 9 | 19 | 2026-11-30 | 2027-02-12
4.2.3 | 3 | Integration layer for 14 interfaces | 4.0 Build and Migration | 4.2 Application modernisation | AD | 260 | 9 | 19 | 2026-11-30 | 2027-02-12
4.2.4 | 3 | CI/CD pipelines | 4.0 Build and Migration | 4.2 Application modernisation | AD | 80 | 9 | 19 | 2026-11-30 | 2027-02-12
4.2.5 | 3 | Reporting decoupled from OLTP | 4.0 Build and Migration | 4.2 Application modernisation | AD | 60 | 9 | 19 | 2026-11-30 | 2027-02-12
4.3.1 | 3 | Cloud Identity tenant and hybrid synchronisation | 4.0 Build and Migration | 4.3 Identity and access management | SE | 50 | 9 | 12 | 2026-11-30 | 2026-12-25
4.3.2 | 3 | MFA and Context-Aware Access | 4.0 Build and Migration | 4.3 Identity and access management | SE | 40 | 9 | 12 | 2026-11-30 | 2026-12-25
4.3.3 | 3 | RBAC, PAM and joiner-mover-leaver process | 4.0 Build and Migration | 4.3 Identity and access management | SE | 60 | 9 | 12 | 2026-11-30 | 2026-12-25
4.3.4 | 3 | ERP single sign-on | 4.0 Build and Migration | 4.3 Identity and access management | AD | 30 | 9 | 12 | 2026-11-30 | 2026-12-25
4.4.1 | 3 | BigQuery reporting dataset and semantic views | 4.0 Build and Migration | 4.4 Looker analytics layer | BI | 180 | 12 | 19 | 2026-12-21 | 2027-02-12
4.4.2 | 3 | Reports and dashboards | 4.0 Build and Migration | 4.4 Looker analytics layer | BI | 220 | 12 | 19 | 2026-12-21 | 2027-02-12
4.4.3 | 3 | Row-level security and governance | 4.0 Build and Migration | 4.4 Looker analytics layer | BI | 60 | 12 | 19 | 2026-12-21 | 2027-02-12
4.4.4 | 3 | Dataform pipeline and refresh scheduling | 4.0 Build and Migration | 4.4 Looker analytics layer | BI | 40 | 12 | 19 | 2026-12-21 | 2027-02-12
5.1.1 | 3 | Test strategy and cases | 5.0 Testing, Hardening and Readiness | 5.1 Test planning and SIT | QA | 100 | 16 | 19 | 2027-01-18 | 2027-02-12
5.1.2 | 3 | SIT execution | 5.0 Testing, Hardening and Readiness | 5.1 Test planning and SIT | QA | 180 | 16 | 19 | 2027-01-18 | 2027-02-12
5.1.3 | 3 | Defect triage and regression | 5.0 Testing, Hardening and Readiness | 5.1 Test planning and SIT | AD | 120 | 16 | 19 | 2027-01-18 | 2027-02-12
5.2.1 | 3 | CIS benchmark hardening | 5.0 Testing, Hardening and Readiness | 5.2 Security hardening | SE | 100 | 15 | 21 | 2027-01-11 | 2027-02-26
5.2.2 | 3 | Security Command Center findings remediation | 5.0 Testing, Hardening and Readiness | 5.2 Security hardening | SE | 80 | 15 | 21 | 2027-01-11 | 2027-02-26
5.2.3 | 3 | Independent penetration test and remediation | 5.0 Testing, Hardening and Readiness | 5.2 Security hardening | SE | 90 | 15 | 21 | 2027-01-11 | 2027-02-26
5.2.4 | 3 | POPIA compliance review and DPIA | 5.0 Testing, Hardening and Readiness | 5.2 Security hardening | SE | 50 | 15 | 21 | 2027-01-11 | 2027-02-26
5.3.1 | 3 | Performance and load testing | 5.0 Testing, Hardening and Readiness | 5.3 Performance and DR testing | CE | 80 | 20 | 21 | 2027-02-15 | 2027-02-26
5.3.2 | 3 | DR failover test | 5.0 Testing, Hardening and Readiness | 5.3 Performance and DR testing | CE | 60 | 20 | 21 | 2027-02-15 | 2027-02-26
5.3.3 | 3 | Backup and restore test | 5.0 Testing, Hardening and Readiness | 5.3 Performance and DR testing | CE | 30 | 20 | 21 | 2027-02-15 | 2027-02-26
5.4.1 | 3 | UAT execution | 5.0 Testing, Hardening and Readiness | 5.4 UAT and readiness | BA | 150 | 21 | 22 | 2027-02-22 | 2027-03-05
5.4.2 | 3 | End-user training and communications | 5.0 Testing, Hardening and Readiness | 5.4 UAT and readiness | BA | 90 | 21 | 22 | 2027-02-22 | 2027-03-05
5.4.3 | 3 | Operational readiness and runbooks | 5.0 Testing, Hardening and Readiness | 5.4 UAT and readiness | CE | 50 | 21 | 22 | 2027-02-22 | 2027-03-05
5.4.4 | 3 | Go/No-Go (G6) | 5.0 Testing, Hardening and Readiness | 5.4 UAT and readiness | PM | 20 | 21 | 22 | 2027-02-22 | 2027-03-05
6.1.1 | 3 | Cutover runbook (timed) | 6.0 Cutover and Go-Live | 6.1 Cutover planning | PM | 50 | 20 | 23 | 2027-02-15 | 2027-03-12
6.1.2 | 3 | Rollback plan and decision points | 6.0 Cutover and Go-Live | 6.1 Cutover planning | SA | 30 | 20 | 23 | 2027-02-15 | 2027-03-12
6.1.3 | 3 | Trading freeze and communications | 6.0 Cutover and Go-Live | 6.1 Cutover planning | BA | 20 | 20 | 23 | 2027-02-15 | 2027-03-12
6.2.1 | 3 | Final data synchronisation | 6.0 Cutover and Go-Live | 6.2 Cutover execution | DE | 80 | 23 | 23 | 2027-03-08 | 2027-03-12
6.2.2 | 3 | Integration and DNS switch | 6.0 Cutover and Go-Live | 6.2 Cutover execution | CE | 60 | 23 | 23 | 2027-03-08 | 2027-03-12
6.2.3 | 3 | Smoke tests and business sign-off | 6.0 Cutover and Go-Live | 6.2 Cutover execution | QA | 40 | 23 | 23 | 2027-03-08 | 2027-03-12
6.3.1 | 3 | Legacy set to read-only | 6.0 Cutover and Go-Live | 6.3 Legacy retirement preparation | DE | 10 | 23 | 23 | 2027-03-08 | 2027-03-12
6.3.2 | 3 | Archive and decommission plan | 6.0 Cutover and Go-Live | 6.3 Legacy retirement preparation | CE | 10 | 23 | 23 | 2027-03-08 | 2027-03-12
7.1.1 | 3 | Daily triage (command centre) | 7.0 Hypercare and Closure | 7.1 Hypercare | PM | 90 | 24 | 26 | 2027-03-15 | 2027-04-02
7.1.2 | 3 | Performance tuning and cost optimisation | 7.0 Hypercare and Closure | 7.1 Hypercare | CE | 60 | 24 | 26 | 2027-03-15 | 2027-04-02
7.1.3 | 3 | Parallel-run reconciliation | 7.0 Hypercare and Closure | 7.1 Hypercare | DE | 50 | 24 | 26 | 2027-03-15 | 2027-04-02
7.2.1 | 3 | Knowledge transfer | 7.0 Hypercare and Closure | 7.2 Transition to operations | SA | 50 | 24 | 26 | 2027-03-15 | 2027-04-02
7.2.2 | 3 | Support model and SLAs | 7.0 Hypercare and Closure | 7.2 Transition to operations | PM | 30 | 24 | 26 | 2027-03-15 | 2027-04-02
7.2.3 | 3 | Operations acceptance | 7.0 Hypercare and Closure | 7.2 Transition to operations | PM | 10 | 24 | 26 | 2027-03-15 | 2027-04-02
7.3.1 | 3 | Sponsor acceptance (G7) | 7.0 Hypercare and Closure | 7.3 Project closure | PM | 10 | 26 | 26 | 2027-03-29 | 2027-04-02
7.3.2 | 3 | Lessons learned | 7.0 Hypercare and Closure | 7.3 Project closure | PM | 30 | 26 | 26 | 2027-03-29 | 2027-04-02
7.3.3 | 3 | Benefits realisation plan | 7.0 Hypercare and Closure | 7.3 Project closure | BA | 30 | 26 | 26 | 2027-03-29 | 2027-04-02
7.3.4 | 3 | Final report and archive | 7.0 Hypercare and Closure | 7.3 Project closure | PM | 20 | 26 | 26 | 2027-03-29 | 2027-04-02
8.1.1 | 3 | Status reporting and SteerCo | 8.0 PM, Quality and Governance | 8.1 Project management | PM | 60 | 1 | 26 | 2026-10-05 | 2027-04-02
8.1.2 | 3 | Risk and issue management | 8.0 PM, Quality and Governance | 8.1 Project management | PM | 40 | 1 | 26 | 2026-10-05 | 2027-04-02
8.1.3 | 3 | Change control | 8.0 PM, Quality and Governance | 8.1 Project management | PM | 40 | 1 | 26 | 2026-10-05 | 2027-04-02
8.2.1 | 3 | Quality plan, reviews and audits | 8.0 PM, Quality and Governance | 8.2 Quality management | QA | 50 | 1 | 26 | 2026-10-05 | 2027-04-02
8.2.2 | 3 | Metrics collection and reporting | 8.0 PM, Quality and Governance | 8.2 Quality management | QA | 30 | 1 | 26 | 2026-10-05 | 2027-04-02
8.2.3 | 3 | Process-improvement actions | 8.0 PM, Quality and Governance | 8.2 Quality management | QA | 10 | 1 | 26 | 2026-10-05 | 2027-04-02
8.3.1 | 3 | Repositories and branching | 8.0 PM, Quality and Governance | 8.3 Configuration management | CE | 20 | 1 | 26 | 2026-10-05 | 2027-04-02
8.3.2 | 3 | Baselines and release management | 8.0 PM, Quality and Governance | 8.3 Configuration management | SA | 20 | 1 | 26 | 2026-10-05 | 2027-04-02
8.3.3 | 3 | Configuration audits (FCA/PCA) | 8.0 PM, Quality and Governance | 8.3 Configuration management | QA | 20 | 1 | 26 | 2026-10-05 | 2027-04-02
8.4.1 | 3 | RFQ, evaluation and award | 8.0 PM, Quality and Governance | 8.4 Procurement | PM | 30 | 1 | 26 | 2026-10-05 | 2027-04-02
8.4.2 | 3 | Contract and licence administration | 8.0 PM, Quality and Governance | 8.4 Procurement | PM | 10 | 1 | 26 | 2026-10-05 | 2027-04-02
8.4.3 | 3 | Vendor performance reviews | 8.0 PM, Quality and Governance | 8.4 Procurement | PM | 10 | 1 | 26 | 2026-10-05 | 2027-04-02
|  | Total planned effort |  |  |  | 6880 | Check | OK
|  | Effort by phase |  |  |  | Effort (h) | % of total | SPMP Table 15 | Check
|  | 1.0 Initiation and Planning |  |  |  | 420 | 6.105% | 420 | OK
|  | 2.0 Discovery and Assessment |  |  |  | 700 | 10.17% | 700 | OK
|  | 3.0 Architecture and Landing Zone |  |  |  | 900 | 13.08% | 900 | OK
|  | 4.0 Build and Migration |  |  |  | 2640 | 38.37% | 2640 | OK
|  | 5.0 Testing, Hardening and Readiness |  |  |  | 1200 | 17.44% | 1200 | OK
|  | 6.0 Cutover and Go-Live |  |  |  | 300 | 4.36% | 300 | OK
|  | 7.0 Hypercare and Closure |  |  |  | 380 | 5.523% | 380 | OK
|  | 8.0 PM, Quality and Governance |  |  |  | 340 | 4.942% | 340 | OK
|  | Total |  |  |  | 6880 | 100% | 6880 | OK
|  | Level-3 work packages (SPMP: 95) |  |  |  | 95
|  | Level-2 deliverable groups (SPMP: 28) |  |  |  | 28
|  | Check: Mock 1 ends at G4 (22 Jan 2027) |  |  |  | OK
|  | Check: Mock 2 ends at G5 (19 Feb 2027) |  |  |  | OK
Formulas:
Start date = DATE(2026,10,5)+([Start week]-1)*7
End date = DATE(2026,10,5)+([End week]-1)*7+4

## Gantt
GCP ERP Migration: Gantt Chart (26 weeks, 5 Oct 2026 to 2 Apr 2027)
Bars are drawn by conditional formatting from the Start/End week columns; change a week and the bar moves. Red = critical path. Can be imported into MS Project.
[5 empty] | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29
ID | Task | Start wk | End wk | Critical | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26
1.0 | Initiation and Planning | 1 | 3 | 1
1.1 | Project initiation | 1 | 2 | 1
1.2 | Project planning | 1 | 3 | 1
1.3 | Team mobilisation | 1 | 2 | 0
2.0 | Discovery and Assessment | 3 | 6 | 1
2.1 | Estate inventory | 3 | 5 | 1
2.2 | Data assessment | 3 | 6 | 1
2.3 | Requirements | 3 | 5 | 1
2.4 | Migration strategy | 5 | 6 | 1
3.0 | Architecture and Landing Zone | 6 | 9 | 1
3.1 | Target architecture | 6 | 8 | 1
3.2 | Landing zone build | 7 | 9 | 1
3.3 | Landing zone validation | 9 | 9 | 1
4.0 | Build and Migration | 9 | 20 | 1
4.1 | Data migration | 9 | 20 | 1
4.2 | Application modernisation | 9 | 19 | 0
4.3 | Identity and access management | 9 | 12 | 0
4.4 | Looker analytics layer | 12 | 19 | 0
5.0 | Testing, Hardening and Readiness | 15 | 22 | 1
5.1 | Test planning and SIT | 16 | 19 | 0
5.2 | Security hardening | 15 | 21 | 0
5.3 | Performance and DR testing | 20 | 21 | 0
5.4 | UAT and readiness | 21 | 22 | 1
6.0 | Cutover and Go-Live | 23 | 23 | 1
6.1 | Cutover planning | 20 | 23 | 1
6.2 | Cutover execution | 23 | 23 | 1
6.3 | Legacy retirement preparation | 23 | 23 | 1
7.0 | Hypercare and Closure | 24 | 26 | 1
7.1 | Hypercare | 24 | 26 | 1
7.2 | Transition to operations | 24 | 26 | 1
7.3 | Project closure | 26 | 26 | 1
8.0 | PM, Quality and Governance | 1 | 26 | 0
8.1 | Project management | 1 | 26 | 0
8.2 | Quality management | 1 | 26 | 0
8.3 | Configuration management | 1 | 26 | 0
8.4 | Procurement | 1 | 26 | 0
M1 | ◆ G1 SPMP approved | 3 | 3 | M
M2 | ◆ G2 Strategy approved | 6 | 6 | M
M3 | ◆ G3 Landing zone live | 9 | 9 | M
M4 | ◆ G4 Mock 1 | 16 | 16 | M
M5 | ◆ G5 Build complete, Mock 2 | 20 | 20 | M
M6 | ◆ G6 Go/No-Go | 22 | 22 | M
M7 | ◆ Go-live (12–14 Mar) | 23 | 23 | M
M8 | ◆ G7 Closure | 26 | 26 | M
Legend: blue = activity; red = critical path; gold = milestone. Critical column: 1 = critical, 0 = has float.

## PERT
GCP ERP Migration: PERT Three-Point Estimates, Critical Path and Float
Supports SPMP Section 5.4 and Appendix A.2 / A.3 (Tables 49 and 50). Durations in weeks.
Critical activity | o | m | p | te = (o+4m+p)/6 | σ = (p-o)/6 | Variance σ² | te (rounded)
1.0 Initiation and planning (to G1) | 1.5 | 2 | 2.5 | 2 | 0.16667 | 0.027778 | 2
2.0 Discovery and assessment | 2.5 | 3 | 3.5 | 3 | 0.16667 | 0.027778 | 3
3.0 Architecture and landing zone | 2 | 3 | 4 | 3 | 0.33333 | 0.11111 | 3
4.1 Data migration pipelines + Mock 1 | 7 | 8 | 9.5 | 8.0833 | 0.41667 | 0.17361 | 8
4.1.4 Mock 2 (dress rehearsal) | 3 | 4 | 5 | 4 | 0.33333 | 0.11111 | 4
5.4 SIT close, UAT and readiness | 1.5 | 2 | 2.5 | 2 | 0.16667 | 0.027778 | 2
6.0 Cutover (time-boxed weekend) | 1 | 1 | 1 | 1 | 0 | 0 | 1
7.0 Hypercare (contracted 3-week time-box) | 3 | 3 | 3 | 3 | 0 | 0 | 3
Critical path total |  |  |  | 26.0833 | 0.69222 | 0.47917 | 26
Expected weeks to go-live (to end of cutover week) |  |  |  | 23.0833
Planned go-live: end of week |  |  |  | 23
Fallback window: end of week |  |  |  | 24
Z (planned) |  |  |  | -0.12039
P(go-live by planned weekend) |  |  |  | 45.21%
Z (fallback) |  |  |  | 1.3242
P(go-live by fallback window) |  |  |  | 90.73%
Check: rounded critical path = 26-week baseline |  |  |  | OK
Non-critical activity | Dur. | ES | EF | LS | LF | TF = LS-ES | FF | Controlling successor
4.2 Application modernisation | 11 | 8 | 19 | 9 | 20 | 1 | 1 | 5.4 UAT (ES 20); 5.1 SIT start-to-start + 7 weeks
4.3 Identity and access management | 4 | 8 | 12 | 11 | 15 | 3 | 2 | 5.2 Security hardening (LS 15)
4.4 Looker analytics layer | 8 | 11 | 19 | 12 | 20 | 1 | 1 | 5.4 UAT (ES 20)
5.1 System integration testing | 4 | 15 | 19 | 16 | 20 | 1 | 0 | 5.3 Performance and DR testing (ES 19)
5.2 Security hardening and pen test | 7 | 14 | 21 | 15 | 22 | 1 | 1 | 6.0 Cutover (ES 22)
5.3 Performance and DR testing | 2 | 19 | 21 | 20 | 22 | 1 | 1 | 6.0 Cutover (ES 22)
ES/EF/LS/LF are week numbers from project start (week 0 = 5 Oct 2026). Critical activities have zero total float.

## Resources
GCP ERP Migration: Human Resource Plan and Labour Cost (ZAR, excl. VAT)
Supports SPMP Section 5.5 (Table 18), Section 13.2 (P9) and Appendix E. Blue = input; black = formula.
Capacity per full-time person (h) | 960 | 26 weeks x 40 h, less 6 public holidays and festive-leave / training allowance (SPMP 5.5)
Role | Abbrev. | Sourcing | Planned hours | Allocation of capacity | Rate (R/h) | Cost (R) | WBS hours as accountable owner
Project Manager | PM | Contractor | 960 | 100% | 750 | 720000 | 850
Solution Architect | SA | Contractor | 720 | 75% | 950 | 684000 | 550
Cloud Migration Engineer | CE | Contractor | 920 | 95.83% | 700 | 644000 | 1100
Data Migration Engineer | DE | Contractor | 870 | 90.62% | 700 | 609000 | 1520
App Modernisation Developer | AD | Secondee | 760 | 79.17% | 650 | 494000 | 820
Looker Developer | BI | Contractor | 570 | 59.38% | 650 | 370500 | 500
Security and IAM Engineer | SE | Contractor | 710 | 73.96% | 800 | 568000 | 690
QA / Test Lead | QA | Secondee | 650 | 67.71% | 550 | 357500 | 430
Business Analyst and Change Lead | BA | Secondee | 720 | 75% | 600 | 432000 | 420
Total (9-person team) |  |  | 6880 | 79.63% | 709.157 | 4879000 | 6880
Team capacity (h) |  |  | 8640
Team utilisation |  |  | 79.63%
Contractor labour (procured via agency panel, P9) | [5 empty] | 3595500
Secondee labour (internal recovery) | [5 empty] | 1283500
Check: planned hours = WBS total effort | [5 empty] | OK
Check: labour cost = Cash Flow labour total | [5 empty] | OK
Check: contractor + secondee = total | [5 empty] | OK
Note: Planned hours are what each person books across all work packages. Column H shows only the hours of packages where the role is the accountable owner in the WBS sheet, so the two columns differ by role but have the same total (6,880 h).

## Budget
GCP ERP Migration: Cost Estimate and Budget (ZAR, excl. VAT)
Supports SPMP Section 6.2 (Table 19), 6.3 (Table 20) and 6.4 (Table 21).
# | Non-labour item | Cost (R) | Basis of estimate
1 | GCP consumption during project | 620000 | Google Cloud Pricing Calculator; ramps with environments
2 | Google Cloud Partner (MSP) | 450000 | Bidder A RFQ price (Table 45)
3 | Connectivity | 180000 | Carrier quotations (Dedicated Interconnect + Cloud VPN)
4 | Security and identity licences | 140000 | Reseller quotation
5 | Looker licences | 95000 | 60 Looker Studio Pro users (D-09)
6 | Independent penetration test and POPIA review | 220000 | Fixed-price RFQ, 3 firms
7 | Training and certification | 160000 | Authorised training partner (Table 25)
8 | Migration, validation and DevOps tooling | 120000 | Quotation
9 | Load-shedding resilience | 60000 | UPS, inverters, LTE failover
10 | Travel (Cape Town and Johannesburg) | 90000 | Trip plan
11 | Project office and miscellaneous | 50000 | Allowance
| Non-labour subtotal | 2185000
| Budget component | Amount (R) | % of direct
| Labour (Resources sheet) | 4879000 | 69.07%
| Non-labour (above) | 2185000 | 30.93%
| Direct costs | 7064000 | 100%
| Contingency reserve | 706400 | 10%
| Cost baseline (BAC) | 7770400
| Management reserve (SteerCo controlled) | 353200 | 5%
| Total funding envelope | 8123600
WBS | Phase | Amount (R) | % of direct
1.0 | Initiation and Planning | 330000 | 4.672%
2.0 | Discovery and Assessment | 520000 | 7.361%
3.0 | Architecture and Landing Zone | 1000000 | 14.16%
4.0 | Build and Migration | 2264000 | 32.05%
5.0 | Testing, Hardening and Readiness | 1000000 | 14.16%
6.0 | Cutover and Go-Live | 420000 | 5.946%
7.0 | Hypercare and Closure | 640000 | 9.06%
8.0 | PM, Quality and Governance (PM labour, travel, PMO, tooling) | 890000 | 12.6%
| Total direct | 7064000 | 100%
Shared costs (GCP, MSP, licences) are apportioned to phases by effort share.
| Check: phase allocation = direct cost | OK
| Check: direct cost = Cash Flow direct total | OK
| Check: BAC = Cash Flow BAC | OK

## Cash Flow
GCP ERP Migration: Monthly Cash Flow Projection (ZAR, excluding VAT)
Karoo Retail Group ¦ 5 Oct 2026 to 2 Apr 2027 ¦ Matches SPMP Appendix B (Table 51). Blue = input; black = formula; green = link to another sheet.
Cost line | M1 (Oct) | M2 (Nov) | M3 (Dec) | M4 (Jan) | M5 (Feb) | M6 (Mar) | Total | Assumption | Value
Labour (9 roles) | 589000 | 760500 | 782500 | 856000 | 933000 | 958000 | 4879000 | Contingency rate (% of direct) | 10%
GCP consumption | 0 | 30000 | 90000 | 110000 | 150000 | 240000 | 620000 | Management reserve rate (% of direct) | 5%
Google Cloud Partner (MSP) | 0 | 100000 | 100000 | 60000 | 60000 | 130000 | 450000 | Approved BAC per SPMP (R) | 7770400
Connectivity | 0 | 40000 | 50000 | 30000 | 30000 | 30000 | 180000 | Approved funding envelope per SPMP (R) | 8123600
Security, identity and Looker licences | 0 | 20000 | 30000 | 60000 | 60000 | 65000 | 235000
Penetration test and POPIA review | 0 | 0 | 0 | 0 | 150000 | 70000 | 220000
Training and certification | 0 | 20000 | 20000 | 25000 | 35000 | 60000 | 160000
Tooling | 30000 | 20000 | 20000 | 20000 | 15000 | 15000 | 120000
Load-shedding resilience | 30000 | 20000 | 10000 | 0 | 0 | 0 | 60000
Travel | 15000 | 15000 | 10000 | 15000 | 15000 | 20000 | 90000
Project office and miscellaneous | 10000 | 8000 | 8000 | 8000 | 8000 | 8000 | 50000
Total direct cost | 674000 | 1033500 | 1120500 | 1184000 | 1456000 | 1596000 | 7064000
Contingency (10% of month's direct cost) | 67400 | 103350 | 112050 | 118400 | 145600 | 159600 | 706400
Planned spend incl. contingency | 741400 | 1136850 | 1232550 | 1302400 | 1601600 | 1755600 | 7770400
Cumulative (cost baseline) | 741400 | 1878250 | 3110800 | 4413200 | 6014800 | 7770400
Cumulative % of BAC | 9.541% | 24.17% | 40.03% | 56.8% | 77.41% | 100%
Cumulative direct only | 674000 | 1707500 | 2828000 | 4012000 | 5468000 | 7064000
Management reserve (5% of direct, SteerCo; outside BAC) | [6 empty] | 353200
Total funding envelope | [6 empty] | 8123600
Check: BAC equals approved baseline | [6 empty] | OK
Check: funding envelope equals approved figure | [6 empty] | OK
Check: labour total equals Resources sheet (hours x rate) | [6 empty] | OK
Check: non-labour total equals Budget sheet (Table 19) | [6 empty] | OK
Check: cumulative baseline ends at BAC | [6 empty] | OK

## Risk Register
GCP ERP Migration: Risk Register
Supports SPMP Section 11 and Appendix C (Table 52). Score = P x I. Low 1-4, Medium 5-9, High 10-14, Critical 15-25.
ID | Risk (cause → event → effect) | P | I | Score | Rating | Strategy | Response actions | Owner | EMV probability | EMV impact (R) | EMV (R)
R01 | Data loss or corruption during extract, transform and load → incorrect stock, financial or customer data | 3 | 5 | 15 | Critical | Mitigate | Two full mock migrations; checksums and row counts; financial control totals signed by Finance; immutable backups; legacy kept intact for rollback | Data Migration Engineer | 35% | 400000 | 140000
R02 | Cutover exceeds the approved window (slow sync, failed step) → trading disruption | 3 | 5 | 15 | Critical | Mitigate + contingency | Timed runbook rehearsed twice; delta-sync; checkpoints CP1-CP4; MSP surge; rollback; fallback window 19-22 Mar | Cloud Migration Engineer | 35% | 250000 | 87500
R03 | GCP cost overrun (oversized VMs, orphaned resources, data egress) → budget breach | 4 | 3 | 12 | High | Mitigate | Budgets and alerts (70/85/100%); mandatory tags; auto-shutdown; right-sizing each sprint; reserved capacity only after stabilisation; monthly FinOps review | Solution Architect | 60% | 150000 | 90000
R04 | Security breach or cloud misconfiguration (open storage, excessive privileges) → personal information exposed | 3 | 5 | 15 | Critical | Mitigate + transfer | Policy-as-code guardrails; MFA and Context-Aware Access; PAM; private endpoints; Security Command Center; CIS hardening; independent pen test; incident plan; cyber-insurance check | Security and IAM Engineer | 35% | 300000 | 105000
R05 | POPIA non-compliance (missing operator agreements, unlawful cross-border transfer, late breach notification) → regulatory action and reputational loss | 2 | 5 | 10 | High | Avoid + mitigate | Production data in africa-south1 only; DR copies in europe-west4 justified under POPIA s72(1)(a), encrypted with keys held in South Africa; operator agreements (s21) before data loads; DPIA; breach-response process; Information Officer sign-off at G3 and G6 | Project Manager
R06 | Skills gap in GCP, IaC, Looker and cloud operations → errors, delay and poor supportability | 4 | 3 | 12 | High | Mitigate | Certification and training plan; MSP knowledge transfer; pair working; runbooks; contractor replacement guarantee | BA and Change Lead
R07 | Vendor lock-in (GCP-specific PaaS, proprietary tooling, ERP vendor terms) → limited future options | 3 | 3 | 9 | Medium | Mitigate + accept | Terraform IaC; standard interfaces (SQL, REST); data-portability and exit clauses; documented exit strategy | Solution Architect
R08 | Undocumented ERP dependencies (batch jobs, hard-coded IPs, EDI, POS links) → failures after migration | 4 | 4 | 16 | Critical | Mitigate | Migration Center dependency analysis; capture network flows across a month-end; inventory of 14 interfaces; SIT for every interface; business walk-through | App Modernisation Developer | 55% | 200000 | 110000
R09 | Scope creep (new ERP features, extra BI reports) → schedule and cost overrun | 4 | 3 | 12 | High | Avoid + mitigate | Signed scope baseline; backlog swap rule; CCB; Product Owner prioritisation; visible change log | Project Manager
R10 | Load-shedding or power/connectivity failure during data sync, cutover or in the war-room → delay or data-transfer errors | 3 | 3 | 9 | Medium | Mitigate | UPS and inverters; LTE failover; GCP-hosted jump boxes; runbook power and connectivity checks; dual circuits | Cloud Migration Engineer
R11 | Loss of a key team member in a scarce-skills market → delay and knowledge loss | 3 | 4 | 12 | High | Mitigate + transfer | Backup pairs; documentation in repository; 5-day replacement guarantee; recognition and retention actions; MSP bench | Project Manager
R12 | Circuit delivery delay or inadequate bandwidth/latency → slow migration and poor performance | 3 | 4 | 12 | High | Mitigate | Order by 30 Oct; Cloud VPN fallback; compressed backup seeding and log shipping; latency tests to stores in Discovery; QoS | Cloud Migration Engineer
R13 | Business SMEs unavailable during Black Friday, festive trading and month-end → delayed UAT and requirements | 4 | 3 | 12 | High | Avoid + mitigate | Calendar aligned to trading; SME time committed by COO; early sessions in Nov and Jan-Feb; delegates; recorded demos | BA and Change Lead
R14 | Looker data-quality, performance or governance issues → loss of trust in reports | 3 | 3 | 9 | Medium | Mitigate | KPI definitions signed by owners; reconcile to ERP; row-level access policy test cases; incremental refresh; workspace governance rules | Looker Developer
R15 | MSP or vendor under-performance, or Google Cloud regional incident in a critical window → delay | 2 | 4 | 8 | Medium | Transfer + mitigate | SLAs with service credits; named deputy; milestone payments; zone-redundant design and DR; freeze windows | Project Manager
R16 | ZAR depreciation raises USD-linked GCP and licence costs → budget pressure | 3 | 3 | 9 | Medium | Transfer + accept | ZAR billing through Google Cloud reseller; contingency; Finance hedging; reserved capacity after stabilisation | Project Manager
R17 | Poor user adoption and resistance to change among ERP users and store managers → productivity loss | 3 | 3 | 9 | Medium | Mitigate | Change and communication plan; super-user network; role-based training; early demos; hypercare floorwalkers | BA and Change Lead
| Summary | Count
| Critical | 4
| High | 7
| Medium | 6
| Low | 0
| Total baseline exposure (sum of scores) | 196
| Target exposure by G6 (40% reduction) | 118
| EMV of top five risks (R) | 532500
| Contingency reserve (R) | 706400
| EMV as % of contingency | 75.38%
| Check: exposure = 196 (SPMP Appendix C) | OK

## RACI
GCP ERP Migration: RACI Matrix
Supports SPMP Appendix D (Table 53). R = Responsible; A = Accountable (exactly one per row); C = Consulted; I = Informed.
# | Activity / deliverable | PM | SA | CE | DE | AD | BI | SE | QA | BA | A count | Check
1 | Charter, SPMP and baselines | A/R | C | I | I | I | I | C | C | C | 1 | OK
2 | Requirements and scope baseline | A | C | I | C | C | C | C | C | R | 1 | OK
3 | Discovery and 6R migration strategy | A | R | C | C | C | I | C | I | C | 1 | OK
4 | Target architecture and security design | C | A/R | R | C | C | C | R | I | I | 1 | OK
5 | Landing zone and connectivity build | I | A | R | I | I | I | R | I | I | 1 | OK
6 | Identity and access management | I | C | C | I | C | C | A/R | I | C | 1 | OK
7 | Data migration (mapping, ETL, mocks, reconciliation) | I | C | C | A/R | C | C | C | R | C | 1 | OK
8 | Application replatform and integrations | I | C | R | C | A/R | I | C | C | C | 1 | OK
9 | Looker model and reports | I | C | I | R | C | A/R | C | C | R | 1 | OK
10 | Security hardening and pen-test coordination | I | C | R | I | C | I | A/R | C | I | 1 | OK
11 | POPIA compliance and DPIA | A | C | I | C | I | C | R | I | C | 1 | OK
12 | Test planning, SIT, UAT and defect management | I | C | C | C | C | C | C | A/R | R | 1 | OK
13 | Cutover planning and execution | A | C | R | R | R | C | C | R | C | 1 | OK
14 | Change control and configuration management | A | R | R | I | I | I | C | C | I | 1 | OK
15 | Risk and issue management | A/R | C | C | C | C | C | C | C | C | 1 | OK
16 | Quality assurance, reviews and audits | A | C | C | C | C | C | C | R | C | 1 | OK
17 | Training, communications and adoption | C | I | C | I | C | C | I | I | A/R | 1 | OK
18 | Procurement and vendor management | A/R | C | C | I | I | I | C | I | I | 1 | OK
19 | Hypercare and handover to operations | A | C | R | R | R | R | R | C | R | 1 | OK
20 | Project closure and lessons learned | A/R | C | C | C | C | C | C | C | C | 1 | OK
| Activities where role is Accountable | 11 | 2 | 0 | 1 | 1 | 1 | 2 | 1 | 1
| Activities where role is Responsible | 4 | 3 | 7 | 4 | 3 | 2 | 6 | 4 | 5
| Check: every activity has exactly one A | [10 empty] | OK

## EVM
GCP ERP Migration: Earned Value Worked Example (end of Month 3)
Supports SPMP Sections 6.5, 14.1 and 14.2. EV and AC are illustrative status-date inputs.
Measure | Value | Formula / source | Status
Budget at Completion (BAC) | 7770400 | Cash Flow sheet
Planned Value (PV), cumulative M3 | 3110800 | Cash Flow cumulative baseline, Dec
Earned Value (EV) | 3000000 | Input: value of work completed
Actual Cost (AC) | 3100000 | Input: cost booked to date
Cost Variance (CV) | -100000 | EV - AC
Schedule Variance (SV) | -110800 | EV - PV
CPI | 0.96774 | EV / AC | Green
SPI | 0.96438 | EV / PV | Green
Estimate at Completion (EAC) | 8029413.3333 | BAC / CPI
Variance at Completion (VAC) | -259013.3333 | BAC - EAC
TCPI (to BAC) | 1.0214 | (BAC - EV) / (BAC - AC)
EAC within funding envelope? | Yes | EAC vs total funding envelope
Thresholds (SPMP 6.5 / 14.1): CPI and SPI >= 0.95 green; 0.90-0.95 amber; < 0.90 red (SteerCo exception report).