# SOFTWARE PROJECT MANAGEMENT PLAN (SPMP)

Cloud Migration of a Mid-Sized Retail Company’s Legacy On-Premise ERP System to Google Cloud Platform (GCP)

(Including Looker Analytics Layer and Security Hardening)

Client:

Prepared in accordance with IEEE Std 1058-1998 (IEEE, 1998)

Assessment: Professional Development Assessment T3
Institution: Cape Peninsula University of Technology (CPUT)
Qualification: Advanced Diploma in ICT Applications Development
Prepared by: Thabiso Matsaba (Student No. 220296006) 
Module code: PFD473S (Professional Development 4) | Lecturer: T. Makhurane
Project Manager (role played): Senior Project Manager, Cloud Migration Programme
Document version: 1.0 (Baseline draft for Steering Committee approval)
Date: 09 October 2026
Chosen cloud provider: Google Cloud Platform (GCP)

Scenario note. The client, Karoo Retail Group (Pty) Ltd, is a fictitious mid-sized South African retailer created for this assessment. All figures are planning estimates in South African Rand (ZAR, excluding VAT at 15%) and are justified in the relevant sections.

## Declaration of Own Work and Use of Artificial Intelligence

I, Thabiso Matsaba (student number 220296006), declare that:

1. This Software Project Management Plan is my own individual submission for Professional Development 4 (PFD473S), Assessment T3, at the Cape Peninsula University of Technology.

2. Karoo Retail Group (Pty) Ltd is a fictitious client. The scenario, the figures and the names of people in the plan are planning assumptions made for this assessment.

3. I used a generative AI tool, Claude (Anthropic), in preparing this assignment. It helped me to structure the plan against the IEEE 1058 outline and the assessment rubric, to draft and edit text, to check calculations (weighted scoring, NPV, PERT, earned value and risk exposure), and to produce the charts and the supporting Excel workbook.

4. I reviewed, checked and edited the AI-assisted content. I understand all of it and take full responsibility for the accuracy and integrity of this submission.

5. All sources are acknowledged in the reference list (Appendix F) using the Harvard method.

6. I have not copied the work of another student, and I have not allowed anyone to copy my work.

Signature: ______________________________

Full name: Thabiso Matsaba

Student number: 220296006

Date: ______09 October 2026________________________

Table of Contents

Declaration of Own Work and Use of Artificial Intelligence	2

Document Control	6

List of Abbreviations	6

1. Project Charter / Project Mandate	7

1.1 Background and Mandate	7

1.2 Project Objectives (SMART)	7

1.3 Scope Statement	7

1.4 Key Deliverables	8

1.5 Summary Schedule and Budget	8

1.6 Assumptions, Constraints and Dependencies	8

1.7 Success Criteria and Project Manager Authority	9

1.8 Approvals	9

2. Business Justification and Project Selection	10

2.1 Problem Statement	10

2.2 Options Analysis	10

2.3 Financial Analysis	10

2.4 Non-Financial Benefits	11

3. Lifecycle and Delivery Approach	12

3.1 Selected Approach: Hybrid (Waterfall and Agile)	12

3.2 Lifecycle Structure and Stage Gates	13

4. Work Breakdown Structure (WBS)	14

4.1 WBS Approach	14

4.2 WBS Levels 1 and 2	14

4.3 Estimation Approach	14

5. Schedule, Milestones and Resource Planning	15

5.1 Schedule Development Method	15

5.2 Phase Schedule	15

5.3 Milestones	15

5.4 Critical Path and Schedule Reserve	16

5.5 Resource Plan	16

6. Cost and Budget Management	17

6.1 Estimating Method	17

6.2 Non-Labour Cost Estimate	17

6.3 Budget Summary and Reserves	17

6.4 Budget Allocation by Phase	18

6.5 Cost Control	18

7. Strategic and Tactical Management	19

7.1 Strategic Management	19

7.2 Tactical Management	19

8. Human Resource Management	21

8.1 Project Organisation	21

8.2 Roles, Responsibilities and Competencies	21

8.3 Staffing Plan	22

8.4 Training and Skills Development	22

8.5 Team Development and Performance Management	22

8.6 Key-Person Risk and Working Conditions	23

9. Configuration and Change Management	24

9.1 Configuration Items	24

9.2 Versioning and Baselines	24

9.3 Configuration Control Practices	25

9.4 Change Control Process	25

9.5 Status Accounting and Audits	26

10. Decision (Rationale) Management	27

10.1 Approach and Decision Process	27

10.2 Worked Examples: Migration Strategy (D-02) and Cutover Approach (D-06)	27

10.3 Decision Log	28

11. Risk Management	29

11.1 Approach and Scoring	29

11.2 Response Strategies	29

11.3 Contingency Reserve Link	29

11.4 Monitoring and Contingency Triggers	29

12. Quality Management	31

12.1 Quality Objectives	31

12.2 Quality Planning	31

12.3 Quality Assurance	31

12.4 Quality Control and Testing	31

12.5 Reviews and Audits	32

12.6 Quality Metrics	32

12.7 Go/No-Go Decision Points	33

13. Procurement Management	34

13.1 Procurement Approach	34

13.2 Procurement Register	34

13.3 Make-or-Buy Analysis	34

13.4 Supplier Selection and RFQ Evaluation	35

13.5 Contract Terms	35

13.6 Procurement Schedule and Supplier Management	35

14. Project Monitoring and Reporting	37

14.1 Key Performance Indicators	37

14.2 Earned Value: Worked Example	37

14.3 Reporting and Escalation	37

14.4 Communication Matrix	37

14.5 Project Closure	38

Appendix A: Gantt Chart and PERT Network Diagram	39

A.1 Gantt Chart	39

A.2 PERT Activity-on-Node Network and Float	39

A.3 PERT Three-Point Estimates	40

Appendix B: Monthly Cash Flow Projection (ZAR, excluding VAT)	42

Appendix C: Risk Register	44

Appendix D: RACI Matrix	46

Appendix E: Resource Histogram	47

Appendix F: References	48

## Document Control

Table 1: Document control

| Item | Detail |
| --- | --- |
| Document title | SPMP: ERP Cloud Migration to Google Cloud Platform (GCP) |
| Standard | IEEE Std 1058 (IEEE, 1998), supported by IEEE 828 (IEEE, 2012), IEEE 730 (IEEE, 2014) and IEEE 1028 (IEEE, 2008) |
| Status | Draft for approval at Gate G1 (23 Oct 2026) |
| Owner | Project Manager |
| Review cycle | Reviewed at every stage gate; re-baselined only via approved change request |
| Distribution | Steering Committee, project team, MSP, Information Officer |

Table 2: Version history

| Version | Date | Author | Change |
| --- | --- | --- | --- |
| 0.1 | 07 Sep 2026 | Project Manager | Initial outline |
| 0.9 | 15 Sep 2026 | Project Manager | Internal review complete |
| 1.0 | 20 Sep 2026 | Project Manager | Baseline draft |

## List of Abbreviations

Table 3: Abbreviations

| Abbrev. | Meaning | Abbrev. | Meaning |
| --- | --- | --- | --- |
| AD | Application Modernisation Developer | MSP | Managed Service Provider |
| BA | Business Analyst and Change Lead | MTTF / MTTR | Mean Time To Failure / To Repair |
| BAC | Budget at Completion | BI | Business intelligence. In this plan "Looker" means Looker Studio Pro on a BigQuery reporting dataset |
| CAF / WAF | Cloud Adoption / Google Cloud Architecture Framework | PM | Project Manager |
| CCB | Change Control Board | POPIA | Protection of Personal Information Act 4 of 2013 |
| CE | Cloud Migration Engineer | QA | Quality Assurance / QA Test Lead |
| CM | Configuration Management | RACI | Responsible, Accountable, Consulted, Informed |
| CPI / SPI | Cost / Schedule Performance Index | RPO / RTO | Recovery Point / Time Objective |
| Reseller | Google Cloud reseller programme | SA | Solution Architect |
| DE | Data Migration Engineer | SE | Security and IAM Engineer |
| EVM | Earned Value Management | SteerCo | Steering Committee |
| IaC | Infrastructure as Code | UAT / SIT | User Acceptance / System Integration Testing |
| KPA | Key Process Area (CMM) | WBS | Work Breakdown Structure |

# 1. Project Charter / Project Mandate

(IEEE 1058 §1 Overview; §4 Project Organisation)

## 1.1 Background and Mandate

Karoo Retail Group (Pty) Ltd runs 38 stores and an online shop. Head office and the company data centre are in Midrand, and online fulfilment and customer care are in Cape Town. The ERP system handles finance, stock, purchasing, sales orders and warehousing for about 380 users, and it exchanges data with 14 other systems, including POS, the online shop, payroll, the banks and courier partners.

The ERP is 11 years old. It runs on Windows Server 2012 R2 and SQL Server 2014, which no longer receive security updates, and the servers are out of warranty. Recovery after a major failure takes about 48 hours, and most management reports are still built by hand in spreadsheets.

Mandate. The Executive Committee has mandated the IT Division to migrate the ERP to Google Cloud Platform (GCP) within six months. The migration must modernise the platform, provide a governed Looker analytics layer, and harden security to POPIA standard, all without disrupting trading.

## 1.2 Project Objectives (SMART)

Table 4: SMART objectives

| # | Objective | Measure / Target | Due |
| --- | --- | --- | --- |
| O1 | Migrate all in-scope ERP modules and 14 integrations to GCP | 100% modules and interfaces live in GCP production | 14 Mar 2027 |
| O2 | Preserve data integrity | ≥ 99.99% record-count match; 100% financial balances (GL, sub-ledgers, stock valuation) reconcile | Mock 2 (19 Feb 2027) and go-live |
| O3 | Improve resilience | Availability ≥ 99.9% monthly during hypercare; RTO ≤ 4 h and RPO ≤ 15 min proven in a DR test | 26 Feb 2027 (test); 2 Apr 2027 (hypercare exit) |
| O4 | Deliver Looker analytics layer | ≥ 12 governed reports across 4 dashboards (sales, inventory, finance, e-commerce); ≥ 60 users trained | 5 Mar 2027 |
| O5 | POPIA-aligned security | 0 open critical/high pen-test findings at go-live; 0 open critical/high Security Command Center findings; ≥ 95% CIS Google Cloud Benchmark compliance; MFA on 100% of accounts | 5 Mar 2027 |
| O6 | Deliver within time and cost | Complete within 26 weeks; cost within ±5% of the R7,770,400 baseline | 2 Apr 2027 |
| O7 | Sustain benefits | Handover to operations with run-cost model and FinOps reporting | 2 Apr 2027 |

## 1.3 Scope Statement

In scope:

1. Discovery and assessment of the ERP, its data and its 14 interfaces.

2. A GCP landing zone: the base cloud environment (projects, security policies, network, a dedicated link to head office and monitoring), built from code so it can be rebuilt.

3. Migration of the ERP application to Compute Engine virtual machines and of the database to Cloud SQL for SQL Server, with the 14 interfaces rebuilt.

4. Data migration with cleansing, two full practice runs (mock migrations) and reconciliation of every financial balance.

5. Identity and security: single sign-on, multi-factor authentication (MFA), role-based access, CIS Benchmark settings (CIS, 2024), an independent penetration test and a review against POPIA (Republic of South Africa, 2013).

6. A Looker analytics layer: at least 12 reports on four dashboards (sales, stock, finance, online) for 60 users.

7. Testing, user training, cutover and three weeks of hypercare support after go-live.

Out of scope: new ERP functions, replacing POS hardware or store networks, Microsoft 365, a 24×7 security operations centre (deferred, see D-10), physical disposal of old hardware, and a full data warehouse.

## 1.4 Key Deliverables

Table 5: Key deliverables

| ID | Deliverable | Gate |
| --- | --- | --- |
| D1 | Approved SPMP and baselines | G1 |
| D2 | Discovery and Migration Strategy Report (6R disposition, TCO, POPIA data classification) | G2 |
| D3 | Target architecture (HLD/LLD) and operational GCP landing zone | G3 |
| D4 | Migrated ERP environments (Dev, SIT, UAT, Prod, DR) built as IaC | G4–G6 |
| D5 | Data migration toolkit, mapping, reconciliation reports | G4–G5 |
| D6 | Identity platform, security baseline, pen-test and POPIA reports | G6 |
| D7 | Looker solution (model, reports, row-level access policies, deployment pipeline) | G5–G6 |
| D8 | Test evidence pack, training material, runbooks, cutover plan | G6 |
| D9 | Production go-live, hypercare report, handover pack and lessons learned | G7 |

## 1.5 Summary Schedule and Budget

- Start: Monday 5 October 2026. Finish: Friday 2 April 2027 (26 weeks, exactly six months).

- Go-live: cutover weekend 12 to 14 March 2027.

- Total direct cost: R7,064,000. Contingency (10%): R706,400. Cost baseline (BAC): R7,770,400. Management reserve (5% of direct, held by the SteerCo): R353,200. Total funding envelope: R8,123,600.

## 1.6 Assumptions, Constraints and Dependencies

Table 6: Assumptions, constraints and dependencies

| Type | Statement |
| --- | --- |
| Assumption | The ERP vendor confirms support for Compute Engine VMs and Cloud SQL for SQL Server by end of Discovery (else fallback in D-03). |
| Assumption | Windows Server licences with Software Assurance can be brought to Compute Engine sole-tenant nodes (BYOL) for the ERP application tier. Cloud SQL for SQL Server is licence-included, so SQL Server licences are not reused on GCP. |
| Assumption | Client SMEs are available for 6 h per week each during UAT. |
| Assumption | GCP services required are available in africa-south1 (Johannesburg, primary) and europe-west4 (Netherlands) (DR); verified in Discovery. |
| Constraint | Fixed six-month duration; nine-person team; ZAR budget of R8,123,600. |
| Constraint | Black Friday (27 Nov 2026) and the festive trading period: no production-impacting changes or heavy extracts from the legacy system during peak windows. |
| Constraint | POPIA: personal information must remain protected, operator agreements must be in place, and cross-border transfers avoided or lawfully justified. |
| Dependency | Telecom provider delivers Dedicated Interconnect/Cloud VPN circuits by 27 Nov 2026 (lead-time risk R12). |
| Dependency | Google Cloud Partner (MSP) contract awarded by 6 Nov 2026. |

## 1.7 Success Criteria and Project Manager Authority

The project succeeds when objectives O1 to O7 are met, the Sponsor signs acceptance at G7, trading is not interrupted outside the cutover window, and the three-month review confirms the run cost and benefits.

The PM may approve changes up to R50,000 and 2 working days of schedule impact, direct the team day to day, escalate to the SteerCo, and stop work on quality or security grounds. Larger changes follow Section 9.

## 1.8 Approvals

Table 7: Approvals

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Executive Sponsor (CIO) | N. Dlamini |  |  |
| Business Owner (COO) | P. van der Merwe |  |  |
| Finance Director | A. Pillay |  |  |
| Information Officer (POPIA) | L. Mokoena |  |  |
| Project Manager | Thabiso (Student No. 220296006) |  |  |

# 2. Business Justification and Project Selection

## 2.1 Problem Statement

Table 8: Problem drivers

| Driver | Evidence | Consequence if unaddressed |
| --- | --- | --- |
| End-of-support platform | Windows Server 2012 R2 and SQL Server 2014 are outside extended support | Unpatched vulnerabilities, audit findings, POPIA s19 exposure |
| Hardware refresh due | Servers out of warranty; capex of about R5.5 m required | Large capex with no strategic benefit |
| Poor resilience | 48 h RTO; single data centre; diesel/UPS dependency during outages | Trading loss during failures and grid instability |
| Peak scalability | Black Friday load requires over-provisioning all year | Idle capacity cost, e-commerce slowdowns |
| Weak analytics | Manual, spreadsheet-based reporting | Slow decisions, stock-outs and shrinkage |
| Regulatory pressure | POPIA enforceable; Information Regulator active | Fines up to R10 m and reputational harm |

## 2.2 Options Analysis

Four options were evaluated with a weighted scoring model (1 = poor, 5 = excellent; for Risk, 5 = lowest risk).

Table 9: Weighted scoring of project options

| Criterion | Weight | A: Do nothing | B: On-prem refresh | C: GCP replatform (selected) | D: Replace with SaaS ERP |
| --- | --- | --- | --- | --- | --- |
| Strategic alignment | 25% | 1 | 2 | 5 | 5 |
| Financial return | 25% | 1 | 2 | 4 | 3 |
| Risk (5 = low) | 15% | 1 | 3 | 3 | 2 |
| Feasibility in 6 months | 15% | 5 | 4 | 4 | 1 |
| Compliance and security | 10% | 1 | 3 | 4 | 4 |
| Scalability and agility | 10% | 1 | 2 | 5 | 5 |
| Weighted score (out of 5) | 100% | 1.60 | 2.55 | 4.20 | 3.35 |

Working example, Option C: (5×25 + 4×25 + 3×15 + 4×15 + 4×10 + 5×10) / 100 = 420 / 100 = 4.20.

Option C is selected. Option D scores well strategically, but a SaaS ERP replacement cannot be delivered in six months and carries very high change and data-conversion risk. Option C is also a stepping stone to it.

## 2.3 Financial Analysis

Investment: R8,123,600 (full envelope including contingency and management reserve, the conservative case).

Table 10: Annual run-cost comparison

| Cost line | Current on-prem | Post-migration GCP |
| --- | --- | --- |
| Hardware maintenance and depreciation | R1,600,000 | R0 |
| Data centre, power, backup power | R1,200,000 | R0 |
| Infrastructure staff (allocated) / MSP managed services | R1,500,000 | R700,000 |
| Software licences (ERP, OS, DB) / cloud licences (Cloud Identity, Security Command Center, Looker) | R1,400,000 | R600,000 |
| DR and backup | R500,000 | Included in GCP |
| GCP consumption (committed use discounts after stabilisation) | n/a | R2,600,000 |
| Total | R6,200,000 | R3,900,000 |
| Annual run-cost saving |  | R2,300,000 |

Five-year cash flows (R million; benefits at year-end, hurdle rate 11%, an assumed WACC to be confirmed by Finance):

Table 11: Five-year discounted cash flows (R million)

| Year | Base case: net flow | Discount factor | PV | Conservative: net flow | PV |
| --- | --- | --- | --- | --- | --- |
| 0 | (8.124) | 1.0000 | (8.124) | (8.124) | (8.124) |
| 1 | 9.600* | 0.9009 | 8.649 | 4.100 | 3.694 |
| 2 | 4.100 | 0.8116 | 3.328 | 4.100 | 3.328 |
| 3 | 4.100 | 0.7312 | 2.998 | 4.100 | 2.998 |
| 4 | 4.100 | 0.6587 | 2.701 | 4.100 | 2.701 |
| 5 | 4.100 | 0.5935 | 2.433 | 4.100 | 2.433 |
| NPV |  |  | R11.99 m |  | R7.03 m |

*Year 1 base case = R2.3 m saving + R1.8 m BI benefit + R5.5 m avoided hardware refresh. The conservative case excludes the avoided capex.

Table 12: Financial metrics

| Metric | Base case | Conservative case |
| --- | --- | --- |
| NPV (5 years @ 11%) | R11.99 m | R7.03 m |
| IRR (approx.) | ≈ 77% | ≈ 41% |
| Payback (after go-live) | ≈ 10 months | ≈ 24 months |
| Benefit-cost ratio (PV benefits / investment) | 2.48 | 1.87 |
| 5-year ROI | n/a | 152% ((20.5 − 8.124) / 8.124) |

Even without the avoided capex, the project returns a positive NPV, so the decision holds.

## 2.4 Non-Financial Benefits

The project also gives a tested disaster recovery capability (RTO ≤ 4 h, RPO ≤ 15 min), capacity for peak trading, a supported platform, less dependence on the server room during load-shedding, POPIA-aligned controls and self-service reporting.

The Business Owner owns benefit tracking. A benefits register (run-cost, availability, report usage, stock-out rate) is baselined at go-live and reviewed at 3, 6 and 12 months after go-live.

3. Lifecycle and Delivery Approach

## 3.1 Selected Approach: Hybrid (Waterfall and Agile)

The project uses a hybrid approach: stage gates (Waterfall) for the plan-driven phases, and two-week Scrum sprints inside the Build phase. Build runs as six sprints from W9 to W20, with lower capacity over the festive weeks. The BA acts as Product Owner proxy and the PM runs sprint planning, a 15-minute daily stand-up, a sprint review with business users and a retrospective. Infrastructure and security work runs on a Kanban board with a limit of three items per engineer. A story is Ready when it has acceptance criteria and an estimate of 16 hours or less, and Done when it is peer-reviewed, tested, deployed through the pipeline and accepted by QA.

Table 13: Comparison of lifecycle approaches

| Criterion | Pure Waterfall | Pure Agile | Hybrid (selected) |
| --- | --- | --- | --- |
| Fixed end date and budget | Strong | Weak; scope floats | Strong: fixed gates, flexible build backlog |
| Migration has hard sequencing (network → identity → data → cutover) | Strong | Weak | Strong: gated sequence |
| Regulatory evidence (POPIA, audit trail) | Strong | Moderate | Strong: gate documents plus sprint evidence |
| Evolving requirements (BI reports, integration edge-cases) | Weak | Strong | Strong: backlog-driven |
| Early feedback and defect discovery | Weak (late testing) | Strong | Strong: sprint reviews, mock migrations |
| Cutover is a single high-risk event | Strong (formal planning) | Weak | Strong: formally planned and rehearsed |

Justification. Assessment, landing zone, cutover and closure are predictable and suit fixed gates. Integration work, data clean-up and report design will change as the team learns more, so short sprints reduce rework there. The fixed six-month end date rules out a fully Agile approach. The hybrid also follows the phases of the Google Cloud Adoption Framework (Google Cloud, n.d.).

South African constraints. No heavy extracts are taken from the legacy system in Black Friday week (23–30 Nov). Sprints S2 and S3 run at reduced capacity over the festive period, with a production change freeze from 14 Dec to 8 Jan, and six public holidays are removed from the calendar. Go-live avoids month-end close and Easter. Load-shedding is covered by UPS and LTE backup (Section 8.6), GCP-hosted jump boxes and power checks at every cutover checkpoint.

## 3.2 Lifecycle Structure and Stage Gates

Figure 1: Hybrid lifecycle: stage gates with Scrum sprints and Kanban inside Build

Table 14: Stage gates and exit criteria

| Gate | Date | Key exit criteria | Decision by |
| --- | --- | --- | --- |
| G1 Baseline | 23 Oct 2026 | SPMP, baselines, team mobilised, RFQ issued | SteerCo |
| G2 Strategy | 13 Nov 2026 | Inventory and dependencies complete; 6R strategy, TCO and POPIA classification approved | SteerCo |
| G3 Architecture | 4 Dec 2026 | HLD/LLD and security design approved; landing zone operational and scanned. | SteerCo, Information Officer |
| G4 Mock 1 | 22 Jan 2027 | Mock migration 1 complete; reconciliation ≥ 99.9%. | PM, SA |
| G5 Build complete | 19 Feb 2027 | Mock migration 2 (dress rehearsal) ≥ 99.99%; Looker in UAT. | SteerCo |
| G6 Go/No-Go | 5 Mar 2027 | UAT signed; no open Sev1/Sev2. | Sponsor, Business Owner |
| G7 Closure | 2 Apr 2027 | Hypercare exit criteria met; handover accepted. | Sponsor |

No phase starts until the previous gate is signed, so the SteerCo controls scope, spend and risk at each stage.

# 4. Work Breakdown Structure (WBS)

## 4.1 WBS Approach

The WBS is deliverable-based and follows the 100% rule: the work in each level adds up to the level above it. It has eight Level-1 phases, 28 Level-2 deliverable groups and 95 Level-3 work packages. Phases 1 to 7 run in sequence, and phase 8 (project management) runs for the whole project. Levels 1 and 2 are shown below. The full Level-3 dictionary, with an owner, effort and dates for every work package, is in the WBS sheet of the supporting Excel workbook.

## 4.2 WBS Levels 1 and 2

Table 15: WBS Levels 1 and 2 with effort

| Level 1 (phase) | Level 2 (deliverable groups) | Effort (h) |
| --- | --- | --- |
| 1.0 Initiation and Planning | 1.1 Project initiation; 1.2 Project planning; 1.3 Team mobilisation | 420 |
| 2.0 Discovery and Assessment | 2.1 Estate inventory; 2.2 Data assessment; 2.3 Requirements; 2.4 Migration strategy | 700 |
| 3.0 Architecture and Landing Zone | 3.1 Target architecture; 3.2 Landing zone build; 3.3 Landing zone validation | 900 |
| 4.0 Build and Migration | 4.1 Data migration; 4.2 Application modernisation; 4.3 Identity and access management; 4.4 Looker analytics layer | 2,640 |
| 5.0 Testing, Hardening and Readiness | 5.1 Test planning and SIT; 5.2 Security hardening; 5.3 Performance and DR testing; 5.4 UAT and readiness | 1,200 |
| 6.0 Cutover and Go-Live | 6.1 Cutover planning; 6.2 Cutover execution; 6.3 Legacy retirement preparation | 300 |
| 7.0 Hypercare and Closure | 7.1 Hypercare; 7.2 Transition to operations; 7.3 Project closure | 380 |
| 8.0 Project Management and Governance | 8.1 Project management; 8.2 Quality management; 8.3 Configuration management; 8.4 Procurement | 340 |
| Total | 28 Level-2 groups; 95 Level-3 work packages | 6,880 |

## 4.3 Estimation Approach

Effort is estimated bottom-up for each Level-3 package with three-point (PERT) estimates, E = (O + 4M + P) / 6 (PMI, 2021). For the data-migration pipelines (WBS 4.1.2), O = 520 h, M = 700 h and P = 1,000 h, so E = (520 + 2,800 + 1,000) ÷ 6 = 720 h. Estimates were checked against the MSP’s experience and are treated as −10% to +15% accurate at baseline. The WBS is baselined at G1, and any new work package after that needs a change request (Section 9.4).

# 5. Schedule, Milestones and Resource Planning

(IEEE 1058 §5.2 Work Plan: schedule allocation, resource allocation)

## 5.1 Schedule Development Method

The schedule was built from the Level-3 work packages, using the three-point durations, finish-to-start dependencies and a calendar that excludes six public holidays (16 Dec, 25 Dec, 1 Jan, 22 Mar, 26 Mar and 29 Mar) and festive leave. Resources were then levelled and the critical path found. The project runs for 26 weeks (124 working days), from Monday 5 October 2026 to Friday 2 April 2027.

## 5.2 Phase Schedule

Table 16: Phase schedule

| WBS | Phase | Start | Finish | Weeks | Working days |
| --- | --- | --- | --- | --- | --- |
| 1.0 | Initiation and Planning | 5 Oct 2026 | 23 Oct 2026 | W1–3 | 15 |
| 2.0 | Discovery and Assessment | 19 Oct 2026 | 13 Nov 2026 | W3–6 | 20 |
| 3.0 | Architecture and Landing Zone | 9 Nov 2026 | 4 Dec 2026 | W6–9 | 20 |
| 4.0 | Build and Migration | 30 Nov 2026 | 19 Feb 2027 | W9–20 | 57 |
| 5.0 | Testing, Hardening and Readiness | 11 Jan 2027 | 5 Mar 2027 | W15–22 | 40 |
| 6.0 | Cutover and Go-Live | 8 Mar 2027 | 14 Mar 2027 | W23 | 5 (plus weekend) |
| 7.0 | Hypercare and Closure | 15 Mar 2027 | 2 Apr 2027 | W24–26 | 12 |
| 8.0 | PM, Quality and Governance | 5 Oct 2026 | 2 Apr 2027 | W1–26 | 124 |

## 5.3 Milestones

Table 17: Milestones

| ID | Milestone | Date | Gate |
| --- | --- | --- | --- |
| M1 | SPMP and baselines approved | Fri 23 Oct 2026 | G1 |
| M2 | Migration strategy and assessment approved | Fri 13 Nov 2026 | G2 |
| M3 | Architecture approved; landing zone and connectivity operational | Fri 4 Dec 2026 | G3 |
| M4 | Mock migration 1 complete | Fri 22 Jan 2027 | G4 |
| M5 | Build complete; mock migration 2 done; Looker in UAT | Fri 19 Feb 2027 | G5 |
| M6 | UAT and security sign-off; Go/No-Go decision | Fri 5 Mar 2027 | G6 |
| M7 | Production go-live (cutover complete) | Sun 14 Mar 2027 | n/a |
| M8 | Hypercare exit and project closure | Fri 2 Apr 2027 | G7 |

## 5.4 Critical Path and Schedule Reserve

Critical path (Appendix A, Figure 4): initiation → discovery → architecture and landing zone → data migration pipelines and Mock 1 → Mock 2 → UAT and Go/No-Go → cutover → hypercare. Durations: 2 + 3 + 3 + 8 + 4 + 2 + 1 + 3 = 26 weeks. Any slip on these activities moves go-live day for day, so the PM tracks them weekly against the baseline.

Looker, application modernisation, SIT, security hardening and performance testing each have about one week of float; IAM has three weeks (Appendix A, Table 49).

Schedule reserve: W22 (1–5 March) is a defect-fix and readiness week, and the fallback cutover window is 19–22 March 2027.

Why 26 weeks remains the baseline. The PERT analysis (Appendix A.3) gives a 45% chance of go-live in the planned weekend and 91% by the fallback window. The team works to the most-likely dates so that float is not used up early. The SteerCo commitment is the 2 April closure date: if the fallback window is used, hypercare shrinks from three weeks to two, so closure still falls in W26. The Sponsor accepts this at G1 under risk R02.

## 5.5 Resource Plan

Table 18: Human resource plan and labour cost

| Role | Planned hours | Allocation of 960 h | Rate (R/h) | Cost (R) |
| --- | --- | --- | --- | --- |
| Project Manager (PM) | 960 | 100% | 750 | 720,000 |
| Solution Architect (SA) | 720 | 75% | 950 | 684,000 |
| Cloud Migration Engineer (CE) | 920 | 96% | 700 | 644,000 |
| Data Migration Engineer (DE) | 870 | 91% | 700 | 609,000 |
| App Modernisation Developer (AD) | 760 | 79% | 650 | 494,000 |
| Looker Developer (BI) | 570 | 59% | 650 | 370,500 |
| Security and IAM Engineer (SE) | 710 | 74% | 800 | 568,000 |
| QA / Test Lead (QA) | 650 | 68% | 550 | 357,500 |
| Business Analyst and Change Lead (BA) | 720 | 75% | 600 | 432,000 |
| Total | 6,880 | 79.6% of 8,640 h |  | R4,879,000 |

Capacity basis: 960 h per full-time person = 26 weeks × 40 h, less six public holidays and a festive-leave and training allowance. Team utilisation is 79.6% (6,880 of 8,640 h), leaving a buffer for absences. The resource histogram is in Appendix E, and the effort for every work package and the week-by-week Gantt chart are in the WBS and Gantt sheets of the supporting Excel workbook.

Non-human resources: GCP projects for each environment, GitHub and Cloud Build, 60 Looker Studio Pro licences, the dedicated network link to head office, an MSP, a penetration-testing firm, a training provider, and UPS and LTE backup for load-shedding.

Team load rises from 56% of capacity in M1 to 95% in M6 (Appendix E). The peak is managed by starting Looker and test preparation early, using MSP support at cutover, allowing overtime only at cutover, and naming backup pairs (Section 8.6).

# 6. Cost and Budget Management

(IEEE 1058 §5.2 Work Plan: budget allocation)

## 6.1 Estimating Method

Costs were estimated bottom-up: labour from the WBS effort (three-point PERT estimates for the larger work packages, Section 4.3) at the hourly rates in Section 5.5, and non-labour items from quotations, the Google Cloud Pricing Calculator and MSP indications. All amounts are in rand, excluding VAT, and rates are fixed at contract award.

## 6.2 Non-Labour Cost Estimate

Table 19: Non-labour costs

| # | Item | Cost (R) |
| --- | --- | --- |
| 1 | GCP consumption during project | 620,000 |
| 2 | Google Cloud Partner (MSP) | 450,000 |
| 3 | Connectivity | 180,000 |
| 4 | Security and identity licences | 140,000 |
| 5 | Looker licences | 95,000 |
| 6 | Independent penetration test and POPIA review | 220,000 |
| 7 | Training and certification | 160,000 |
| 8 | Migration, validation and DevOps tooling | 120,000 |
| 9 | Load-shedding resilience | 60,000 |
| 10 | Travel (Cape Town and Johannesburg) | 90,000 |
| 11 | Project office and miscellaneous | 50,000 |
|  | Non-labour subtotal | 2,185,000 |

## 6.3 Budget Summary and Reserves

Table 20: Budget summary

| Component | Amount (R) | % of direct |
| --- | --- | --- |
| Labour (Section 5.5) | 4,879,000 | 69.1% |
| Non-labour (Section 6.2) | 2,185,000 | 30.9% |
| Direct costs | 7,064,000 | 100% |
| Contingency reserve (10% of direct) | 706,400 | 10.0% |
| Cost baseline (BAC) | 7,770,400 |  |
| Management reserve (5% of direct; SteerCo controlled) | 353,200 | 5.0% |
| Total funding envelope | 8,123,600 |  |

Justification of reserves. The 10% contingency covers the known risks in the register (Section 11.3) and the estimate range. The 5% management reserve covers unknown risks and can only be released by the SteerCo, following PMBOK practice (PMI, 2021). Contingency is released only through an approved risk trigger or change request, so the BAC of R7,770,400 cannot be exceeded without SteerCo approval.

## 6.4 Budget Allocation by Phase

Table 21: Budget allocation by phase

| WBS | Phase | Amount (R) | % of direct (rounded) |
| --- | --- | --- | --- |
| 1.0 | Initiation and Planning | 330,000 | 4.7% |
| 2.0 | Discovery and Assessment | 520,000 | 7.4% |
| 3.0 | Architecture and Landing Zone | 1,000,000 | 14.2% |
| 4.0 | Build and Migration | 2,264,000 | 32.0% |
| 5.0 | Testing, Hardening and Readiness | 1,000,000 | 14.2% |
| 6.0 | Cutover and Go-Live | 420,000 | 5.9% |
| 7.0 | Hypercare and Closure | 640,000 | 9.1% |
| 8.0 | PM, Quality and Governance (PM labour, travel, PMO, tooling) | 890,000 | 12.6% |
|  | Total direct | 7,064,000 |  |

Shared costs (GCP, MSP, licences) are apportioned to phases by effort share. Time-phased spend is in Appendix B.

## 6.5 Cost Control

- Method: Earned Value Management at Level 2 WBS, reported weekly. EAC = BAC / CPI; TCPI monitors the efficiency needed to finish within budget.

- Thresholds: CPI ≥ 0.95 green; 0.90–0.95 amber (PM corrective action); < 0.90 red (SteerCo exception report). Variance of ±5% to the PM, up to ±10% to the CCB, and above that to the SteerCo.

- Contingency governance: drawdown requires an approved change request or an owned risk trigger; it is logged and reported monthly.

- Cloud FinOps controls: Cloud Billing reports budgets with alerts at 70/85/100%; mandatory tags (CostCentre, Environment, Owner, DataClass); auto-shutdown of Dev/Test out of hours; right-sizing reviews at each sprint review; committed use discounts purchased only after two weeks of stable hypercare data.

- Currency and VAT: costs are quoted excluding VAT; GCP is billed in ZAR through the Google Cloud reseller channel to limit exchange-rate exposure (risk R16); Finance may hedge USD-linked licence costs.

Together these controls mean that a forecast overrun above 5% reaches the CCB within a week, before it can use up the contingency.

# 7. Strategic and Tactical Management

## 7.1 Strategic Management

Strategic alignment. The project supports three company strategies: online growth (capacity for peaks), data-driven buying (Looker) and compliance (POPIA and supported platforms). Each objective O1 to O7 maps to at least one of them.

Table 22: Governance structure

| Body | Members | Frequency | Authority |
| --- | --- | --- | --- |
| Steering Committee | Sponsor (CIO, chair), COO (Business Owner), Finance Director, Information Officer, IT Operations Manager; PM (secretary); SA and MSP account lead by invitation | Monthly plus gate reviews | Approves baselines, gates, management reserve, scope change above CCB limits |
| Change Control Board | PM (chair), SA, SE, QA, BA, IT Ops representative | Weekly (Tuesdays) plus emergency CAB | Approves changes within thresholds (Section 9.4) |
| Project team | PM and 8 specialists | Daily / weekly | Delivers work packages |

SteerCo decision rights. Only the SteerCo can pass a gate (G1–G7), release the management reserve (R353,200), approve changes above R250,000 or five working days, or change an objective. The PM and CCB act within these limits (Section 9.4), which keeps authority clear.

Table 23: Stakeholder analysis

| Stakeholder | Influence | Strategy |
| --- | --- | --- |
| Executive Sponsor (CIO) | High | Manage closely; monthly SteerCo; weekly 1-to-1 |
| COO / Business Owner | High | Manage closely; co-owns backlog priorities and cutover date |
| Finance Director | High | Manage closely; sign-off of financial reconciliation |
| Information Officer | High | Manage closely; approves DPIA and operator agreements |
| Store and warehouse managers | Medium | Keep informed; trading-freeze calendar; training |
| ERP super-users / SMEs | Medium | Involve in UAT and sprint reviews |
| IT Operations | Medium | Consult; embed in hypercare |
| Google Cloud / MSP / telco | Medium | Contract management; joint reviews |
| Information Regulator and external auditors | Low (but consequential) | Keep informed through Information Officer; evidence pack |
| Customers and suppliers | Low | Notify via business; interface testing with key suppliers |

## 7.2 Tactical Management

- Tactical controls. Weekly status report and RAG; change control; risk review (weekly for scores ≥ 12); quality gates; EVM thresholds.

- Cutover command structure. A “war-room” in Johannesburg with PM as cutover commander, SA as technical authority, CE/DE/AD as execution leads, SE for security checks, QA for smoke tests, BA for business sign-off and a business observer. Decision points are pre-defined (Section 12.7).

- Escalation path. Team member → Workstream lead (4 h) → PM (same day) → Sponsor (next business day) → SteerCo (exception report within 48 h). Critical security and production incidents skip levels immediately.

8. Human Resource Management

(IEEE 1058 §4 Project Organisation; §5.1 Staffing plan and training)

## 8.1 Project Organisation

Figure 2: Project organisation chart

Client-side SMEs, the Information Officer and IT Operations are supporting stakeholders and are not counted in the team of nine.

## 8.2 Roles, Responsibilities and Competencies

Table 24: Roles, responsibilities and competencies

| Role | Key responsibilities | Required competencies |
| --- | --- | --- |
| Project Manager | Plan, baselines, integration, risk, communication, vendor management, cutover command | PMP or PRINCE2; cloud programme experience; stakeholder management |
| Solution Architect | Target architecture, migration strategy, technical decisions, Google Cloud Architecture Framework reviews | Google Cloud Professional Cloud Architect; enterprise ERP architecture |
| Cloud Migration Engineer | Landing zone, networking, VM and Cloud SQL migration, IaC, cutover execution | Associate Cloud Engineer / Professional Cloud Architect; Terraform; Migration Center |
| Data Migration Engineer | Mapping, ETL/replication, cleansing, reconciliation, mock migrations | Google Cloud Professional Cloud Database Engineer; SQL Server; data-quality tooling |
| App Modernisation Developer | Integration layer, CI/CD, refactoring, ERP configuration, SIT fixes | ERP platform knowledge; .NET; APIs; GitHub and Cloud Build |
| Looker Developer | BigQuery semantic views, reports, row-level access policies, Dataform pipeline | BigQuery SQL and Dataform; Looker Studio Pro; dimensional data modelling |
| Security and IAM Engineer | Cloud Identity, Context-Aware Access, PAM, hardening, Security Command Center, pen-test coordination, POPIA controls | Google Cloud Professional Cloud Security Engineer; CIS benchmarks |
| QA / Test Lead | Test strategy, SIT/UAT, defect management, metrics, quality reviews and audits | ISTQB; test automation |
| Business Analyst and Change Lead | Requirements, backlog, UAT coordination, training, communications, adoption | CBAP or equivalent; change management |

The RACI is in Appendix D.

## 8.3 Staffing Plan

Six roles (PM, SA, CE, DE, BI, SE) are contractors sourced through local IT recruitment agencies. The other three (AD, QA, BA) are seconded from the client’s IT and business teams because they know the ERP. Contractors start on 5 October 2026, and the BI Developer joins part-time from W6 and full-time from W9. Contracts include a 5-day replacement guarantee, and secondees’ line managers sign a release agreement so they are not pulled back to other work.

## 8.4 Training and Skills Development

Table 25: Training plan

| Gap | Action | Timing | Budget |
| --- | --- | --- | --- |
| GCP fundamentals and landing zone practices | Associate Cloud Engineer / Professional Cloud Architect exam preparation for AD and QA; workshops by the MSP | M1–M3 | Within R160,000 training budget |
| Security engineering | Professional Cloud Security Engineer preparation for SE; Professional Cloud Network Engineer modules for CE | M2–M3 | ” |
| Looker and governance | Google Cloud Skills Boost courses on BigQuery and Looker Studio for BA and BI; report-author training for 10 power users | M3–M5 | ” |
| End users (about 380 ERP users, 60 BI users) | Role-based training, quick-reference guides, super-user network | M5–M6 | ” |
| IT Operations | Shadowing and runbook workshops during hypercare | M6 | ” |

Training effectiveness is tracked as completion rate (target ≥ 90%) and a post-training assessment score (target ≥ 80%).

## 8.5 Team Development and Performance Management

Team formation. A kick-off workshop and a team charter (working agreements and the Definition of Done) help the team through Tuckman’s forming and norming stages, and fortnightly retrospectives deal with friction early.

Performance management. The PM gives each person fortnightly feedback against the criteria below and a scored review (1 = well below, 3 = meets, 5 = well above) at each gate. Scores go to secondees’ line managers and to the contractors’ agency. Two reviews in a row below 3 trigger a two-week improvement plan, then escalation.

Table 26: Performance criteria by role

| Role | Performance criteria | Target |
| --- | --- | --- |
| Project Manager | Schedule and cost performance; gates on time; stakeholder satisfaction | SPI and CPI ≥ 0.95; all gates within 3 days; survey ≥ 4/5 |
| Solution Architect | Timely, sound design decisions | ADR within 5 working days of the question; 0 design-caused Sev1 defects |
| Cloud Migration Engineer | Landing-zone quality and pipeline reliability | Policy compliance ≥ 95%; drift fixed within 1 day; pipeline success ≥ 95% |
| Data Migration Engineer | Data integrity | Mock 1 ≥ 99.9%; Mock 2 ≥ 99.99%; 100% financial balances |
| App Modernisation Developer | Interface quality | 14/14 interfaces pass SIT; ≤ 3 defects per KLOC; change failure ≤ 15% |
| Looker Developer | Report delivery and accuracy | ≥ 12 reports UAT-approved; 100% KPIs reconcile; refresh ≥ 99% |
| Security and IAM Engineer | Security posture | 0 open critical/high findings at G6; 100% MFA; PAM live by G4 |
| QA / Test Lead | Test effectiveness and audits | ≥ 95% of planned tests run; DRE ≥ 95%; audits on schedule |
| Business Analyst and Change Lead | Backlog readiness and adoption | Two sprints of Ready stories; training completion ≥ 90%; UAT satisfaction ≥ 4/5 |

## 8.6 Key-Person Risk and Working Conditions

Key-person risk (R11) is reduced in three ways. Each key role has a backup pair (SA and CE, DE and BI, AD and CE, SE and SA, QA and BA) who attend each other’s design sessions. All runbooks, code and decisions are kept in the repository, so no knowledge sits with one person. The MSP bench and the agencies’ 5-day replacement guarantee cover a sudden loss, and formal handover sessions run in W24–26.

- Working hours and labour law. Planning hours are 40 per week, below the 45-hour ordinary-hours limit of the Basic Conditions of Employment Act (Republic of South Africa, 1997). Overtime is voluntary, agreed in writing where the Act applies, limited to the cutover weekend and compensated by time off in lieu (secondees) or the contract terms (contractors).

- Load-shedding and connectivity. Engineers with a laptop, mobile hotspot/LTE failover and, where needed, an inverter for the router; the Johannesburg war-room has UPS backing. Critical cutover steps run from GCP-hosted jump boxes, not from individuals’ home connections.

The PM checks these measures at each gate together with risks R10 and R11.

# 9. Configuration and Change Management

(IEEE 1058 §7.1 Configuration Management Plan; aligned with IEEE 828 and CMM KPA “Software Configuration Management”)

## 9.1 Configuration Items

To identify, control, record and audit every item that defines the cloud environment and the migrated solution, so that any environment can be recreated and every change is traceable, authorised and reversible.

Table 27: Configuration items

| Category | Examples | Repository / tool |
| --- | --- | --- |
| Infrastructure as Code | Terraform modules for network, VMs, Cloud SQL instances, Secret Manager, policies | GitHub and Cloud Build Repos (Git) |
| Cloud governance configuration | Resource hierarchy (organisation, folders, projects), Organization Policy Service and initiatives, RBAC assignments, tag standards | IaC plus Organization Policy Service |
| Security configuration | Context-Aware Access policies, PAM roles, VPC firewall rules, Security Command Center settings, CIS benchmark profile | IaC, exported and versioned |
| Application and integration | ERP customisations, Apigee API Management definitions, Cloud Workflows definitions, service configurations | Git |
| Database | Schema scripts, stored procedures, reference data, migration scripts and mappings | Git |
| Looker | Semantic models, reports and BigQuery view definitions (SQL, managed in Dataform), row-level access policies and roles, deployment-pipeline definitions | Git and Dataform pipelines |
| Documentation | SPMP, HLD/LLD, runbooks, test evidence, decision log | SharePoint / wiki (version-controlled) |

## 9.2 Versioning and Baselines

IaC modules and releases use semantic version numbers (MAJOR.MINOR.PATCH), and documents are numbered 0.x while in draft and 1.0 once approved. The baselines below are set at the stage gates.

Table 28: Baselines

| Baseline | Content | Established | Controlled by |
| --- | --- | --- | --- |
| BL0: Project baseline | SPMP: scope, schedule, cost | 23 Oct 2026 (G1) | SteerCo / CCB |
| BL1: Functional baseline | Requirements, NFRs, migration strategy | 13 Nov 2026 (G2) | CCB |
| BL2: Architecture baseline | HLD/LLD and security design | 4 Dec 2026 (G3) | CCB (SA chairs technical review) |
| BL3: Landing-zone / cloud configuration baseline v1.0 | Deployed folders and projects, organisation policies, network, IAM and security settings, exported from IaC | 4 Dec 2026 (G3) | CCB; drift monitored continuously |
| BL4: Data migration baseline | Approved mapping, scripts, reconciliation rules | 22 Jan 2027 (G4) | CCB |
| BL5: Release candidate baseline (RC1 → RC2) | Application, integration and Looker packages tested in SIT/UAT | 19 Feb 2027 (G5) and 5 Mar 2027 (G6) | CCB |
| BL6: Production operational baseline | Configuration at go-live, handed to operations | 14 Mar 2027 | IT Operations CAB |

After each baseline, changes are made only through the change process. The baseline is cloud-native: environment state is defined by code, so the repository is the baseline, and any manual portal change is a policy violation.

## 9.3 Configuration Control Practices

- IaC only. Changes are made in code, reviewed through pull requests (minimum one reviewer; two for security-relevant changes), and deployed by pipeline with an approval gate for UAT and Production.

- Environment promotion. Dev → Test/SIT → UAT → Prod, with identical code and environment-specific parameters. DR is built from the same code.

- Drift detection. Scheduled pipeline (plan comparison), Organization Policy Service compliance scans, and Security Command Center recommendations. Drift creates an incident for the owning engineer within one business day.

## 9.4 Change Control Process

Table 29: Change control steps

| Step | Activity | Responsible |
| --- | --- | --- |
| 1 | Change request (CR) raised: description, reason, items affected, urgency | Any team member or stakeholder |
| 2 | Logging and triage: unique ID, classification (Standard / Normal / Emergency) | PM / QA |
| 3 | Impact analysis: scope, schedule, cost, risk, quality, security and POPIA, rollback | SA with workstream leads |
| 4 | Decision at CCB (weekly, Tuesdays) or SteerCo per thresholds | CCB / SteerCo |
| 5 | Implementation via pipeline; peer review; test evidence | Assigned engineer |
| 6 | Verification and closure; baseline and register updated | QA / PM |

Change classes. Standard changes are pre-approved and low risk. Normal changes follow the steps above, with a decision within 3 working days. Emergency changes are approved within 2 hours by the PM, SA and SE and ratified by the CCB afterwards.

Table 30: Change approval authority

| Impact | Approver |
| --- | --- |
| ≤ R50,000 and ≤ 2 working days (non-critical path), no security/POPIA impact | Project Manager |
| ≤ R250,000 and ≤ 5 working days | CCB |
| > R250,000, > 5 days, change of objectives, use of management reserve, or any change weakening security posture or POPIA compliance | SteerCo (POPIA matters also need the Information Officer) |

Scope discipline. New requests go to the backlog and either replace work of equal effort or become a CR. No production changes are made from 14 Dec to 8 Jan, and only the release candidate is deployed from 5 March to go-live.

## 9.5 Status Accounting and Audits

- Status accounting: GitHub and Cloud Build and Cloud Asset Inventory reports show the versions deployed per environment, open CRs, and drift items. Reported weekly.

- Functional Configuration Audit (FCA): verifies the release candidate meets approved requirements (traceability matrix). Performed before G6.

- Physical Configuration Audit (PCA): verifies that what is deployed in production matches the released and baselined code and IaC. Performed before go-live and at hypercare exit.

Together these practices cover the CMM Level 2 key process area for software configuration management (Paulk et al., 1993).

# 10. Decision (Rationale) Management

## 10.1 Approach and Decision Process

Decisions are recorded with the Question–Options–Criteria model (Bruegge and Dutoit, 2010): each decision is written as an issue, the options are scored against agreed criteria, and the choice and its assumptions are logged. This lets the team explain decisions to auditors and revisit them if an assumption fails.

Table 31: Decision process

| Step | Activity |
| --- | --- |
| 1. Frame | State the issue, constraints and deadline; identify the decision owner |
| 2. Options | Identify at least two credible options (including “do nothing” where relevant) |
| 3. Criteria | Agree criteria and weights before scoring (cost, schedule, risk, security/POPIA, quality, skills, lock-in) |
| 4. Evaluate | Score options; run a sensitivity check; involve the MSP or an SME where evidence is needed |
| 5. Decide | Decision made at the level in the authority table; dissent recorded |
| 6. Record | Entry in the Decision Log (ID, date, options, rationale, assumptions, owner, review trigger) |
| 7. Review | Revisit if a stated assumption fails (for example, ERP vendor does not support the target) |

## 10.2 Worked Examples: Migration Strategy (D-02) and Cutover Approach (D-06)

Issue: Which migration strategy should be used for the ERP within a fixed six-month window?

Table 32: Migration strategy options (D-02)

| Criterion | Weight | Rehost (lift and shift) | Replatform + targeted refactor | Refactor to cloud-native | Replace with SaaS ERP |
| --- | --- | --- | --- | --- | --- |
| Fit to 6-month timeline and risk | 30% | 5 | 4 | 1 | 1 |
| Cost | 20% | 4 | 4 | 2 | 2 |
| Business value / modernisation | 20% | 2 | 4 | 5 | 5 |
| Security and POPIA | 15% | 3 | 4 | 4 | 4 |
| Skills and sustainability | 15% | 4 | 4 | 2 | 3 |
| Weighted score | 100% | 3.75 | 4.00 | 2.60 | 2.75 |

Calculation (replatform): 4×0.30 + 4×0.20 + 4×0.20 + 4×0.15 + 4×0.15 = 1.2 + 0.8 + 0.8 + 0.6 + 0.6 = 4.00.

Sensitivity check: if the timeline weight rises to 40%, Rehost scores 3.95 and Replatform still scores 4.00, so the choice holds. Decision: replatform the application to Compute Engine and the database to Cloud SQL, with targeted changes to integrations and reporting.

Example 2 (D-06): should the ERP go live in one weekend (big bang) or module by module (phased)?

Table 33: Cutover approach options (D-06)

| Criterion | Weight | Big-bang weekend | Phased by module |
| --- | --- | --- | --- |
| Data consistency (finance and stock in one snapshot) | 30% | 5 | 2 |
| Interface complexity (no temporary bridges) | 25% | 4 | 2 |
| Business disruption | 20% | 3 | 4 |
| Rollback simplicity | 15% | 4 | 2 |
| Exposure if a rehearsal fails | 10% | 2 | 4 |
| Weighted score | 100% | 3.90 | 2.60 |

Big bang: 5×0.30 + 4×0.25 + 3×0.20 + 4×0.15 + 2×0.10 = 3.90. The big-bang cutover is chosen. Its main weakness, high exposure if something fails, is reduced by two full mock migrations, a timed runbook and the rollback checkpoints in Section 12.7.

## 10.3 Decision Log

Table 34: Decision log

| ID | Date | Decision | Alternatives considered | Rationale | Approved by |
| --- | --- | --- | --- | --- | --- |
| D-01 | 23 Oct 2026 | Hybrid lifecycle (stage gates plus Scrum in Build) | Pure Waterfall; pure Agile | Fixed end date and sequenced work, with room for discovery in Build (Section 3.1) | SteerCo |
| D-02 | 13 Nov 2026 | Replatform with targeted refactoring | Rehost; refactor; SaaS ERP | Highest weighted score (4.00) and fits six months (Section 10.2) | SteerCo |
| D-03 | 13 Nov 2026 | Cloud SQL for SQL Server as ERP database | SQL Server on Compute Engine VMs | Managed patching and HA with low rework; VM fallback if the vendor does not certify Cloud SQL | SA, CCB |
| D-04 | 4 Dec 2026 | Production in africa-south1; DR in europe-west4 | Single-region HA only; on-premise DR | Only one South African GCP region; EU transfer lawful under POPIA s72(1)(a); keys held in South Africa | SteerCo, Information Officer |
| D-06 | 13 Nov 2026 | Big-bang weekend cutover with rollback point | Phased by module | Weighted score 3.90 vs 2.60; one consistent data snapshot (Section 10.2) | SteerCo |
| D-09 | 13 Nov 2026 | Looker Studio Pro on BigQuery for 60 users | Full Looker platform; free Looker Studio | Fits the R95,000 licence budget; row-level security in BigQuery | BA, SteerCo |
| D-10 | 13 Nov 2026 | Security Command Center at go-live; SOC deferred | Full SIEM and 24×7 SOC at go-live | SOC cost and skills exceed scope; MSP alerting covers the interim | SteerCo |
| D-11 | 23 Oct 2026 | Go-live 12–14 Mar 2027; fallback 19–22 Mar | February; April | Avoids Black Friday, festive trading, month-end close and Easter | SteerCo |

The Decision Log is a controlled document (Section 9), reviewed at each gate. Decisions that change the baselines follow change control. Retrospectives include a check that decisions still hold, and the lessons-learned report analyses decision quality.

# 11. Risk Management

(IEEE 1058 §5.4 Risk Management Plan)

## 11.1 Approach and Scoring

Risk management follows the PMBOK risk cycle (PMI, 2021): identify, analyse, plan responses, implement and monitor. Risks come from Discovery workshops, MSP checklists, lessons learned and the WBS. The register (Appendix C) is reviewed weekly for risks scoring 12 or more, and in full at every gate.

Table 35: Probability and impact scales

| Score | Probability | Impact (worst dimension) |
| --- | --- | --- |
| 1 | Rare (< 10%) | Negligible: < 1 day slip; < R25k |
| 2 | Unlikely (10–30%) | Minor: 1–3 days; R25k–R75k |
| 3 | Possible (30–50%) | Moderate: 3–5 days; R75k–R200k; minor quality effect |
| 4 | Likely (50–70%) | Major: 1–2 weeks; R200k–R500k; major control failure |
| 5 | Almost certain (> 70%) | Severe: go-live missed; > R500k; data loss, breach or regulatory action |

Risk score = Probability × Impact (1–25). Low 1–4; Medium 5–9; High 10–14; Critical 15–25.

## 11.2 Response Strategies

Four response types are used: avoid (for example, no large data extracts in Black Friday week), mitigate, transfer (MSP SLAs, a fixed-price pen test, cyber insurance) and accept with a contingency plan. Each risk in Appendix C has one named owner.

## 11.3 Contingency Reserve Link

Expected monetary value (EMV) of the top five risks: R01 (35% × R400,000) + R02 (35% × R250,000) + R03 (60% × R150,000) + R04 (35% × R300,000) + R08 (55% × R200,000) = R140,000 + R87,500 + R90,000 + R105,000 + R110,000 = R532,500. This is about 75% of the R706,400 contingency; the rest covers the other risks and estimating error. Contingency is released only when a risk trigger is approved.

## 11.4 Monitoring and Contingency Triggers

Target: total exposure falls from 196 at baseline to 118 or less by G6 (a 40% reduction), with no Critical risk open at G6. The PM reports exposure and contingency use together at each gate, so the SteerCo can see whether the remaining R706,400 contingency is still needed.

Table 36: Risk triggers and contingency plans

| Risk | Trigger | Contingency |
| --- | --- | --- |
| R02 Cutover overrun | Runbook step > 30 min behind at any checkpoint | Invoke decision point: continue, compress or roll back to legacy; use fallback window 19–22 Mar |
| R01 Data corruption | Mock reconciliation < 99.9% | Halt; root-cause analysis; repeat mock before proceeding |
| R04 Security incident | Security Command Center critical alert or suspicious privileged sign-in | Isolate, revoke, invoke incident plan; notify Information Officer (POPIA s22 within required timeframes) |
| R03 Cost overrun | Forecast > 105% of monthly budget | Freeze non-essential environments; right-size; CCB review |
| R10 Load-shedding or outage | Loss of power or connectivity at war-room | Switch to UPS/LTE and GCP jump boxes; move step ownership to remote engineer |

# 12. Quality Management

(IEEE 1058 §7.2 Verification and Validation, §7.4 Quality Assurance, §7.5 Reviews and Audits, §7.6 Problem Resolution; aligned with IEEE 730 and IEEE 1028)

## 12.1 Quality Objectives

The project delivers a migrated ERP that is correct (data integrity), reliable (availability and recoverability), secure (POPIA-compliant) and usable. Quality is planned in, not inspected in at the end.

Table 37: Quality objectives

| Quality objective | Target |
| --- | --- |
| Data integrity | ≥ 99.99% records match; 100% financial reconciliation |
| Availability | ≥ 99.9% monthly during hypercare (≤ 43 min unplanned downtime per 30 days) |
| Recoverability | RTO ≤ 4 h; RPO ≤ 15 min, proven by DR test |
| Defect density at SIT exit | ≤ 3 defects per KLOC of new/changed code; 0 open Sev1/Sev2 |
| Escaped defects in hypercare | ≤ 0.5 defects per KLOC |
| Defect removal efficiency (DRE) | ≥ 95% |
| Security | 0 open critical/high pen-test findings; 0 open critical/high Security Command Center findings; ≥ 95% CIS Google Cloud Benchmark compliance |
| User acceptance | UAT satisfaction ≥ 4/5; 100% critical scenarios passed |

## 12.2 Quality Planning

Quality requirements come from stakeholder needs and the non-functional requirements (WBS 2.3), written as measurable acceptance criteria and traced from requirement to test case and release. Four ISO 9001 principles shape the plan (ISO, 2015): customer focus (the Business Owner co-owns acceptance criteria), process approach (a defined lifecycle and pipelines), evidence-based decisions (metrics and reconciliation reports drive every gate) and improvement (retrospectives and root-cause analysis).

The QA/Test Lead owns the quality plan, metrics and audits and reports directly to the Sponsor on quality for independence. The SA owns design quality and the SE owns security quality. Improvement runs as a plan-do-check-act loop: every sprint retrospective and gate review ends with no more than three actions, each with an owner, and every Sev1 or Sev2 defect gets a root-cause analysis whose fix is added to the checklists and the pipeline.

## 12.3 Quality Assurance

QA checks that the agreed processes are followed. The QA/Test Lead runs process audits in W8, W16 and W22, checks the exit criteria at every gate, and makes sure every change passes the pipeline controls (peer review, automated tests and security scans). Non-conformances are logged with an owner and a due date and must be closed before the next gate.

The quality processes aim for CMM Level 2 (Repeatable). Requirements management, project planning, tracking, subcontract management, quality assurance and configuration management are all covered in this plan. Peer reviews and root-cause analysis of serious defects, which are higher-level CMM practices, are also used because they pay back quickly on a short project (Paulk et al., 1993).

## 12.4 Quality Control and Testing

QC verifies the products against requirements.

Table 38: Test levels and exit criteria

| Test level / activity | Entry → exit criteria | Owner |
| --- | --- | --- |
| Unit and component tests | Coverage ≥ 70% of new custom code; all critical paths tested | AD, CE |
| System Integration Testing (SIT) | Build deployed via pipeline → 100% critical cases run; ≥ 95% pass; 0 Sev1/Sev2; defect density ≤ 3/KLOC | QA |
| Data validation and reconciliation | Mock 1 ≥ 99.9%; Mock 2 and cutover ≥ 99.99%; 100% financial balances | DE, QA |
| Performance and load | Response times within NFRs; no throttling | CE, QA |
| Security testing | 0 open critical/high; medium items risk-accepted by the SE | SE |
| DR and backup/restore tests | Pass in W20–21 | CE |
| Looker validation | 100% of KPIs reconciled; refresh success ≥ 99% | BI, QA |
| UAT | 100% critical scenarios pass; no open Sev1/Sev2; satisfaction ≥ 4/5 | BA, business |

Defect management. Sev1 (system down, data loss or breach) is triaged within 30 minutes and fixed or worked around within 4 hours; Sev2 (major function fails) within one business day. Sev3 and Sev4 are fixed in normal sprints.

## 12.5 Reviews and Audits

Table 39: Reviews and audits

| Review type | Artefacts | Participants | Timing |
| --- | --- | --- | --- |
| Management review | SPMP, status, gate packs | Sponsor, SteerCo, PM | Monthly and at each gate |
| Technical review | Architecture (HLD/LLD), security design, migration strategy | SA, SE, CE, MSP, QA | Before G2, G3 |
| Inspection (formal, Fagan-style) | Data mapping specifications, cutover runbook, IaC security modules | Author, reader, moderator, inspector; QA as moderator | W10–12, W20–22 |
| Walk-through | Test cases, training material, Looker reports | Author and business SMEs | Sprint |
| Peer review (pull request) | Code, IaC, scripts | Second engineer (two for security changes) | Every change |
| Audits | Process audits (Section 12.3); FCA/PCA (Section 9.5); security and POPIA compliance audit; client Internal Audit observation of financial reconciliation | QA, Internal Audit, Information Officer | W8, W16, W22 |

Review outcomes (defects found, effort, rework) are recorded for defect-removal-efficiency analysis.

## 12.6 Quality Metrics

Table 40: Quality metrics

| Metric | Definition / formula | Target | Frequency |
| --- | --- | --- | --- |
| Defect density | Confirmed defects ÷ size (KLOC of new or changed code; for data, defects per 1,000 records migrated) | ≤ 3 per KLOC at SIT exit; ≤ 0.5 per KLOC in hypercare | Per sprint / release |
| Defect removal efficiency | Pre-release defects ÷ (pre-release + post-release defects) | ≥ 95% | At G6 and G7 |
| MTTF | Total operating time ÷ number of failures (Sev1/Sev2 incidents) | ≥ 1,000 h in hypercare (extrapolated) | Daily in hypercare |
| MTTR | Total repair time ÷ number of failures | ≤ 1 h (Sev1); ≤ 4 h (Sev2) | Per incident |
| Availability | MTTF ÷ (MTTF + MTTR) or (uptime ÷ total time) | ≥ 99.9% monthly | Continuous monitoring |
| Data reconciliation rate | Matched records ÷ source records | ≥ 99.99% (Mock 2, cutover) | Each mock and cutover |
| Security posture | CIS Benchmark compliance (SCC compliance view); Organization Policy compliance %; open critical/high SCC findings | ≥ 95%; ≥ 95%; 0 | Weekly |
| User satisfaction | UAT and training survey (1–5) | ≥ 4.0 | UAT and after hypercare |
| Test pass rate | Passed ÷ executed test cases | ≥ 95% at SIT exit; 100% of critical cases | Weekly in test |
| Requirements coverage | Requirements with a passed test ÷ total requirements | 100% critical; ≥ 95% overall | At G5 and G6 |

Worked examples. SIT finds 24 defects in 12 KLOC of changed code: 24 ÷ 12 = 2.0 defects per KLOC, which meets the ≤ 3 target. With MTTF = 1,000 h and MTTR = 1 h, availability = 1,000 ÷ 1,001 = 99.90%, which meets the target. With 190 defects found before release and 8 after, DRE = 190 ÷ 198 = 96%.

## 12.7 Go/No-Go Decision Points

Table 41: Go/No-Go and rollback checkpoints

| Checkpoint | Decision criteria |
| --- | --- |
| G6 Go/No-Go (5 Mar) | All must be true: Mock 2 reconciliation ≥ 99.99% and 100% of financial balances; UAT signed with 100% of critical scenarios passed; no open Sev1/Sev2; pen-test critical/high findings closed; DR test met RTO ≤ 4 h and RPO ≤ 15 min; runbook rehearsed inside the window; support rota and hypercare desk ready; Business Owner and Information Officer sign-off. Any failure = No-Go and move to the fallback window. |
| CP1: Freeze complete (Fri 20:00) | Legacy quiesced; backups verified; team and power/connectivity checks done |
| CP2: Final sync complete (Sat 06:00) | Row counts and checksums match; financial control totals agree |
| CP3: Point of no return (Sat 14:00) | Smoke tests 100%; integrations verified; if not met → roll back to legacy (retained intact) |
| CP4: Business sign-off (Sun 12:00) | Finance, warehouse and e-commerce sign-off; trading resumes Monday |
| Rollback trigger (any time before CP3) | A checkpoint missed by more than 60 minutes, reconciliation below 99.99%, financial control totals that do not agree, or any open Sev1. The PM (cutover commander) and Sponsor decide; legacy is reopened within 4 hours and cutover moves to 19–22 March. |

These criteria are fixed at G5 and cannot be relaxed on the cutover weekend without Sponsor approval.

# 13. Procurement Management

(IEEE 1058 §7.7 Subcontractor Management Plan)

## 13.1 Procurement Approach

External skills, cloud services and licences that the team cannot supply are bought through competitive quotations, with POPIA clauses, clear acceptance criteria and exit terms. Karoo Retail Group is a private company, so its own procurement policy applies.

## 13.2 Procurement Register

Table 42: Procurement register

| ID | Item | Route | Est. value (R) | Needed by |
| --- | --- | --- | --- | --- |
| P1 | GCP projects | Google Cloud reseller through Google Cloud Partner (ZAR billing) | 620,000 | M2 onward |
| P2 | Google Cloud Partner (MSP) | RFQ, 3 shortlisted partners | 450,000 | 9 Nov 2026 |
| P3 | Connectivity | RFQ, 2 to 3 carriers | 180,000 | Live by 27 Nov 2026 (order by 30 Oct) |
| P4 | Security and identity licences | Reseller | 140,000 | 16 Nov 2026 |
| P5 | Looker licences | Reseller | 95,000 | 4 Jan 2027 |
| P6 | Penetration test and POPIA review | RFQ, 3 firms | 220,000 | Test 1–26 Feb 2027 (award by 8 Jan) |
| P7 | Training | Google Cloud authorised training partner | 160,000 | From M2 |
| P8 | Tooling | Quotation | 120,000 | 30 Nov 2026 |
| P9 | Contract specialists (6 roles) | Agency panel | Included in labour (R3,595,500*) | 5 Oct 2026 |

*Contractor labour: PM 720,000 + SA 684,000 + CE 644,000 + DE 609,000 + BI 370,500 + SE 568,000 = R3,595,500. (Secondee costs, AD 494,000 + QA 357,500 + BA 432,000 = R1,283,500, are internal recoveries.) Total = R4,879,000.

## 13.3 Make-or-Buy Analysis

Table 43: Make-or-buy analysis

| Work | Decision | Rationale |
| --- | --- | --- |
| Landing zone build | Make, with MSP design review | Builds internal capability and control; MSP reduces risk |
| ERP replatform and integrations | Make | Knowledge of the ERP is internal; MSP is not required for functional logic |
| Migration tooling (Migration Center, database migration service) | Buy/use platform tools | Low or no cost; proven |
| Independent penetration test | Buy | Independence and specialist skills required for credibility with the Information Regulator and auditors |
| Cutover and hypercare surge | Buy (MSP) | Peak demand for short period; cheaper than permanent staff |
| Training delivery | Mixed | Vendor certification courses purchased; internal super-users train end users |

## 13.4 Supplier Selection and RFQ Evaluation

Table 44: RFQ scoring criteria

| Criterion | Weight |
| --- | --- |
| Technical approach and relevant GCP/ERP migration experience | 40% |
| Price and commercial terms | 25% |
| References and certifications (Google Cloud Partner designation, ISO 27001) | 15% |
| B-BBEE contribution level and skills transfer | 10% |
| Local support, response times and SLAs | 10% |

The RFQ evaluation has eight steps and uses two envelopes, so prices are opened only after the technical scoring. (1) Pass/fail compliance check: Google Cloud Partner status, acceptance of a POPIA operator agreement, a B-BBEE certificate, tax compliance and insurance. (2) Panel members declare any conflict of interest. (3) Each member scores the technical criteria on a 1–5 scale. (4) Scores that differ by more than one point are discussed and agreed. (5) Bids below 3.0 on the technical criterion are excluded. (6) Prices are scored as 5 × lowest price ÷ bidder price. (7) Two client references are checked. (8) The Sponsor signs the award and unsuccessful bidders are debriefed.

All three bidders passed the compliance check and the technical threshold.

Table 45: Worked example: MSP bid evaluation (bids anonymised)

| Criterion | Weight | Bidder A (R450,000) | Bidder B (R420,000) | Bidder C (R520,000) |
| --- | --- | --- | --- | --- |
| Technical approach and GCP/ERP experience | 40% | 4.5 | 3.5 | 4.0 |
| Price (5 × lowest ÷ bid) | 25% | 4.67 | 5.00 | 4.04 |
| References and certifications | 15% | 4.0 | 3.0 | 5.0 |
| B-BBEE level and skills transfer | 10% | 4.0 (Level 2) | 5.0 (Level 1) | 3.0 (Level 4) |
| Local support and SLAs | 10% | 4.0 | 3.0 | 4.0 |
| Weighted score (out of 5) | 100% | 4.37 | 3.90 | 4.06 |

Bidder A: 4.5×0.40 + 4.67×0.25 + 4.0×0.15 + 4.0×0.10 + 4.0×0.10 = 4.37. Bidder A is recommended. Bidder B is cheaper but scored lower on technical approach and references, which matters for a fixed-date cutover.

## 13.5 Contract Terms

- POPIA operator agreement (s21) with every supplier that processes personal information, covering security safeguards, confidentiality, breach notification to the responsible party without delay, and sub-processor controls.

- SLAs and remedies: response and resolution times, service credits, milestone acceptance criteria.

- Exit and lock-in protection: data portability, return and secure deletion of data, IaC and documentation ownership by the client, transition assistance.

## 13.6 Procurement Schedule and Supplier Management

Table 46: Procurement schedule

| Date | Activity |
| --- | --- |
| 12–16 Oct 2026 (W2) | Issue RFQs for MSP and connectivity |
| 26–30 Oct (W4) | Evaluation; connectivity order placed |
| 6 Nov (W5) | MSP award and contract signature |
| 9 Nov (W6) | MSP mobilised |
| 27 Nov (W8) | Connectivity live |
| 7 Dec–8 Jan (W10–14) | Pen-test RFQ, evaluation and award |
| 1–26 Feb (W18–21) | Pen test execution; re-test and closure of findings by 5 Mar |

The PM reviews each supplier monthly against its SLA and milestones and approves invoices only for accepted deliverables. The MSP must name a deputy for its lead consultant.

# 14. Project Monitoring and Reporting

(IEEE 1058 §5.3 Control Plan)

## 14.1 Key Performance Indicators

Table 47: Key performance indicators

| Dimension | KPI | Green | Amber | Red |
| --- | --- | --- | --- | --- |
| Schedule | SPI (EV ÷ PV) | ≥ 0.95 | 0.90–0.95 | < 0.90 |
| Cost | CPI (EV ÷ AC) | ≥ 0.95 | 0.90–0.95 | < 0.90 |
| Milestones | Milestones met on the date | 100% | ≤ 3 days late | > 3 days late |
| Quality | Defect density; open Sev1/Sev2; reconciliation % | Within targets | Slight miss with plan | Miss with no plan |
| Risk | Total exposure trend; critical risks | Falling; 0 critical after G3 | Flat | Rising or critical open |
| Cloud cost | GCP forecast vs monthly budget | ≤ 100% | 100–105% | > 105% |
| Security | CIS Benchmark compliance; open critical/high SCC findings | ≥ 95%; 0 | 90–94%; ≤ 2 | < 90%; > 2 |

## 14.2 Earned Value: Worked Example

Illustration at the end of Month 3 (cumulative planned value from Appendix B: R3,110,800): Suppose EV = R3,000,000 and AC = R3,100,000.

CPI = EV ÷ AC = 3,000,000 ÷ 3,100,000 = 0.968 (green)

SPI = EV ÷ PV = 3,000,000 ÷ 3,110,800 = 0.964 (green)

EAC = BAC ÷ CPI = 7,770,400 ÷ 0.968 ≈ R8.03 m; VAC = BAC − EAC ≈ −R0.26 m (inside the total funding envelope of R8.12 m, so the PM raises an early warning and corrective actions).

TCPI = (BAC − EV) ÷ (BAC − AC) = 4,770,400 ÷ 4,670,400 = 1.02 (achievable).

## 14.3 Reporting and Escalation

Status definitions. Green = on track; Amber = variance within tolerance with recovery plan; Red = out of tolerance and needs SteerCo action.

Issues are logged with owner, priority and due date. An issue unresolved for 3 working days escalates to the PM, and 5 working days escalates to the Sponsor. Security or production Sev1 incidents are escalated immediately (Section 7.2).

## 14.4 Communication Matrix

Table 48: Communication matrix

| Message type | Owner | Audience | Channel | Timing |
| --- | --- | --- | --- | --- |
| SteerCo pack | PM | SteerCo | Meeting and PDF pack | Monthly; 3 days before meeting |
| Weekly status report | PM | Sponsor, Business Owner, leads | Email and Looker dashboard | Friday 12:00 |
| Gate pack | PM, QA | SteerCo | Meeting and document | G1–G7 |
| Exception report | PM | SteerCo | Email and call | Within 48 h of breach |
| Change decision notice | PM | Requester, affected leads | Email; CR log | Within 1 day of CCB |
| Trading-freeze and cutover notice | BA | Store and warehouse managers | Email bulletin and Teams briefing | 4 weeks, 1 week and 1 day before |
| Training invitation | BA | ERP and BI users | Email and calendar invite | From M5 |
| Go-live and hypercare bulletin | PM, BA | All ERP users | Email and intranet | Daily during hypercare |
| Security or data incident notice | SE with Information Officer | Sponsor, Information Officer; Regulator if required | Phone, then written report | Immediately; written within 24 h |
| Interface change notice | AD | Suppliers, couriers, banks | Email and joint test call | M4–M6 |
| Sprint review invitation | BA | Business SMEs | Teams meeting | Fortnightly |
| Lessons-learned report | PM | SteerCo, PMO | Workshop and document | At G7 |

## 14.5 Project Closure

At G7 the PM confirms that all deliverables are accepted, contracts are closed and documents are archived. A lessons-learned workshop follows, and a review three months after go-live checks the benefits in Section 2.

# Appendix A: Gantt Chart and PERT Network Diagram

The project runs for 26 weeks, from 5 October 2026 to 2 April 2027. M1 = W1–4 (Oct), M2 = W5–8 (Nov), M3 = W9–13 (Dec), M4 = W14–17 (Jan), M5 = W18–21 (Feb), M6 = W22–26 (Mar). The Gantt chart, WBS dictionary and cash flow are also provided as editable sheets in the supporting Excel workbook (GCP_ERP_Migration_Supporting_Workbook.xlsx).

## A.1 Gantt Chart

Figure 3: High-level project Gantt chart

## A.2 PERT Activity-on-Node Network and Float

Figure 4 expresses the same schedule as an activity-on-node network, with Early Start (ES) and Early Finish (EF) week numbers derived from the forward pass, and the critical path (zero total float) highlighted in bold red.

Figure 4: PERT activity-on-node network diagram with critical path highlighted

Critical path: 1.0 → 2.0 → 3.0 → 4.1 (pipelines and Mock 1) → Mock 2 → 5.4 UAT and readiness → 6.0 Cutover → 7.0 Hypercare, the same path as Section 5.4. Non-critical activities have dashed grey arrows, and their float is in Table 49.

LS = LF − duration; total float (TF) = LS − ES; free float (FF) = earliest ES of the successors − EF.

Table 49: Float analysis for non-critical activities (weeks)

| Activity | Dur. | ES | EF | LS | LF | TF | FF | Controlling successor |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4.2 Application modernisation | 11 | 8 | 19 | 9 | 20 | 1 | 1 | 5.4 UAT (ES 20); 5.1 SIT starts start-to-start + 7 weeks |
| 4.3 Identity and access management | 4 | 8 | 12 | 11 | 15 | 3 | 2 | 5.2 Security hardening (LS 15) |
| 4.4 Looker analytics layer | 8 | 11 | 19 | 12 | 20 | 1 | 1 | 5.4 UAT (ES 20) |
| 5.1 System integration testing | 4 | 15 | 19 | 16 | 20 | 1 | 0 | 5.3 Performance and DR testing (ES 19) |
| 5.2 Security hardening and pen test | 7 | 14 | 21 | 15 | 22 | 1 | 1 | 6.0 Cutover (ES 22) |
| 5.3 Performance and DR testing | 2 | 19 | 21 | 20 | 22 | 1 | 1 | 6.0 Cutover (ES 22) |
| Critical activities (1.0, 2.0, 3.0, 4.1, Mock 2, 5.4, 6.0, 7.0) | 26 | 0 | 26 | 0 | 26 | 0 | 0 | Zero float by definition |

## A.3 PERT Three-Point Estimates

Expected duration is calculated using the standard PERT formula te = (o + 4m + p) / 6, with standard deviation σ = (p - o) / 6, where o = optimistic, m = most likely, p = pessimistic (weeks).

Table 50: PERT three-point estimates for critical activities (weeks)

| Activity | o | m | p | te (weeks) | σ | te (rounded) |
| --- | --- | --- | --- | --- | --- | --- |
| 1.0 Initiation & planning (to G1) | 1.5 | 2 | 2.5 | 2.00 | 0.17 | 2 |
| 2.0 Discovery & assessment | 2.5 | 3 | 3.5 | 3.00 | 0.17 | 3 |
| 3.0 Architecture & landing zone | 2 | 3 | 4 | 3.00 | 0.33 | 3 |
| 4.1 Data migration pipelines + Mock 1 | 7 | 8 | 9.5 | 8.08 | 0.42 | 8 |
| 4.1.4 Mock 2 (dress rehearsal) | 3 | 4 | 5 | 4.00 | 0.33 | 4 |
| 5.4 SIT close, UAT & readiness | 1.5 | 2 | 2.5 | 2.00 | 0.17 | 2 |
| 6.0 Cutover (time-boxed weekend) | 1 | 1 | 1 | 1.00 | 0.00 | 1 |
| 7.0 Hypercare (contracted 3-week time-box) | 3 | 3 | 3 | 3.00 | 0.00 | 3 |
| Critical path total |  |  |  | 26.08 | 0.69 | 26 |

Critical path duration: Σte = 2.00 + 3.00 + 3.00 + 8.08 + 4.00 + 2.00 + 1.00 + 3.00 = 26.08 weeks, which matches the 26-week baseline. Variance = Σσ² = 0.479, so σ ≈ 0.69 weeks. Cutover and hypercare are fixed time-boxes, so all the uncertainty sits in the 23.08 weeks before go-live. Chance of go-live in the planned weekend (end of W23): Z = (23 − 23.08) ÷ 0.69 = −0.12, P ≈ 45%. Chance by the fallback window (end of W24): Z = (24 − 23.08) ÷ 0.69 = 1.33, P ≈ 91%.

# Appendix B: Monthly Cash Flow Projection (ZAR, excluding VAT)

Table 51: Monthly cash flow projection

| Cost line | M1 (Oct) | M2 (Nov) | M3 (Dec) | M4 (Jan) | M5 (Feb) | M6 (Mar) | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Labour (9 roles) | 589,000 | 760,500 | 782,500 | 856,000 | 933,000 | 958,000 | 4,879,000 |
| GCP consumption | 0 | 30,000 | 90,000 | 110,000 | 150,000 | 240,000 | 620,000 |
| Google Cloud Partner (MSP) | 0 | 100,000 | 100,000 | 60,000 | 60,000 | 130,000 | 450,000 |
| Connectivity (Dedicated Interconnect and Cloud VPN) | 0 | 40,000 | 50,000 | 30,000 | 30,000 | 30,000 | 180,000 |
| Security/identity and Looker licences | 0 | 20,000 | 30,000 | 60,000 | 60,000 | 65,000 | 235,000 |
| Penetration test and POPIA review | 0 | 0 | 0 | 0 | 150,000 | 70,000 | 220,000 |
| Training and certification | 0 | 20,000 | 20,000 | 25,000 | 35,000 | 60,000 | 160,000 |
| Tooling | 30,000 | 20,000 | 20,000 | 20,000 | 15,000 | 15,000 | 120,000 |
| Load-shedding resilience | 30,000 | 20,000 | 10,000 | 0 | 0 | 0 | 60,000 |
| Travel | 15,000 | 15,000 | 10,000 | 15,000 | 15,000 | 20,000 | 90,000 |
| Project office and miscellaneous | 10,000 | 8,000 | 8,000 | 8,000 | 8,000 | 8,000 | 50,000 |
| Total direct cost | 674,000 | 1,033,500 | 1,120,500 | 1,184,000 | 1,456,000 | 1,596,000 | 7,064,000 |
| Contingency (10% of month’s direct cost) | 67,400 | 103,350 | 112,050 | 118,400 | 145,600 | 159,600 | 706,400 |
| Planned spend incl. contingency | 741,400 | 1,136,850 | 1,232,550 | 1,302,400 | 1,601,600 | 1,755,600 | 7,770,400 |
| Cumulative (cost baseline, BAC) | 741,400 | 1,878,250 | 3,110,800 | 4,413,200 | 6,014,800 | 7,770,400 |  |
| Cumulative direct only | 674,000 | 1,707,500 | 2,828,000 | 4,012,000 | 5,468,000 | 7,064,000 |  |
| Cumulative % of BAC | 9.5% | 24.2% | 40.0% | 56.8% | 77.4% | 100% |  |

Management reserve: R353,200 is held by the SteerCo outside the baseline and is not scheduled. Total funding envelope = R7,770,400 + R353,200 = R8,123,600.

Figure 5: Monthly and cumulative planned spend

Basis and assumptions:

- Labour is derived from Appendix E (hours × rate). GCP consumption ramps as environments and the parallel run come online; MSP and pen-test payments follow milestone acceptance.

- Suppliers invoice monthly in arrears, so cash out lags spend by about 30 days. Finance should treat the table as accrual-based and add the lag when planning bank funding. GCP is billed in ZAR through the Google Cloud reseller channel.

# Appendix C: Risk Register

Scale: Probability (P) 1–5 × Impact (I) 1–5 = Score. Rating: Low 1–4, Medium 5–9, High 10–14, Critical 15–25. Reviewed weekly (scores ≥ 12) and at each gate. Baseline total exposure = 196.

Table 52: Risk register

| ID | Risk (cause → event → effect) | P | I | Score | Strategy | Response actions | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R01 | Data loss or corruption during extract, transform and load → incorrect stock, financial or customer data | 3 | 5 | 15 | Mitigate | Two full mock migrations; checksums and row counts; financial control totals signed by Finance; immutable backups; legacy kept intact for rollback | Data Migration Engineer |
| R02 | Cutover exceeds the approved window (slow sync, failed step) → trading disruption | 3 | 5 | 15 | Mitigate + contingency | Timed runbook rehearsed twice; delta-sync; checkpoints CP1–CP4; MSP surge; rollback; fallback window 19–22 Mar | Cloud Migration Engineer |
| R03 | GCP cost overrun (oversized VMs, orphaned resources, data egress) → budget breach | 4 | 3 | 12 | Mitigate | Budgets and alerts (70/85/100%); mandatory tags; auto-shutdown; right-sizing each sprint; reserved capacity only after stabilisation; monthly FinOps review | Solution Architect |
| R04 | Security breach or cloud misconfiguration (open storage, excessive privileges) → personal information exposed | 3 | 5 | 15 | Mitigate + transfer | Policy-as-code guardrails; MFA and Context-Aware Access; PAM; private endpoints; Security Command Center; CIS hardening; independent pen test; incident plan; cyber-insurance check | Security and IAM Engineer |
| R05 | POPIA non-compliance (missing operator agreements, unlawful cross-border transfer, late breach notification) → regulatory action and reputational loss | 2 | 5 | 10 | Avoid + mitigate | Production data in africa-south1 only; offshore DR copies in europe-west4 justified under POPIA s72(1)(a) and covered by the Cloud Data Processing Addendum, encrypted with keys held in South Africa; operator agreements (s21) before data loads; DPIA; breach-response process; Information Officer sign-off at G3 and G6 | Project Manager |
| R06 | Skills gap in GCP, IaC, Looker and cloud operations → errors, delay and poor supportability | 4 | 3 | 12 | Mitigate | Certification and training plan; MSP knowledge transfer; pair working; runbooks; contractor replacement guarantee | BA and Change Lead |
| R07 | Vendor lock-in (GCP-specific PaaS, proprietary tooling, ERP vendor terms) → limited future options and bargaining power | 3 | 3 | 9 | Mitigate + accept | Terraform IaC; standard interfaces (SQL, REST); data-portability and exit clauses; documented exit strategy; avoid unneeded proprietary features | Solution Architect |
| R08 | Undocumented ERP dependencies (batch jobs, hard-coded IPs, EDI, POS links) → failures after migration | 4 | 4 | 16 | Mitigate | Migration Center dependency analysis; capture network flows across a month-end; inventory of 14 interfaces; SIT for every interface; business walk-through | App Modernisation Developer |
| R09 | Scope creep (new ERP features, extra BI reports) → schedule and cost overrun | 4 | 3 | 12 | Avoid + mitigate | Signed scope baseline; backlog swap rule; CCB; Product Owner prioritisation; visible change log | Project Manager |
| R10 | Load-shedding or power/connectivity failure during data sync, cutover or in the war-room → delay or data-transfer errors | 3 | 3 | 9 | Mitigate | UPS and inverters; LTE failover; GCP-hosted jump boxes; runbook power and connectivity checks; dual circuits | Cloud Migration Engineer |
| R11 | Loss of a key team member (illness, resignation, poaching) in a scarce-skills market → delay and knowledge loss | 3 | 4 | 12 | Mitigate + transfer | Backup pairs; documentation in repository; 5-day replacement guarantee; recognition and retention actions; MSP bench | Project Manager |
| R12 | Circuit delivery delay or inadequate bandwidth/latency for bulk sync and POS traffic → slow migration and poor performance | 3 | 4 | 12 | Mitigate | Order by 30 Oct; Cloud VPN fallback; compressed backup seeding and log shipping; latency tests to stores in Discovery; QoS | Cloud Migration Engineer |
| R13 | Business SMEs unavailable during Black Friday, festive trading and month-end → delayed UAT and requirements | 4 | 3 | 12 | Avoid + mitigate | Calendar aligned to trading; SME time committed by COO; early sessions in Nov and Jan–Feb; delegates; recorded demos | BA and Change Lead |
| R14 | Looker data-quality, performance or governance issues (wrong KPIs, row-level access policies gaps, refresh failures) → loss of trust in reports | 3 | 3 | 9 | Mitigate | KPI definitions signed by owners; reconcile to ERP; row-level access policies test cases; incremental refresh; workspace governance rules | Looker Developer |
| R15 | MSP or vendor under-performance, or Google Cloud regional service incident in a critical window → delay | 2 | 4 | 8 | Transfer + mitigate | SLAs with service credits; named deputy; milestone payments; zone-redundant design and DR; freeze windows | Project Manager |
| R16 | ZAR depreciation raises USD-linked GCP and licence costs → budget pressure | 3 | 3 | 9 | Transfer + accept | ZAR billing through Google Cloud reseller; contingency; Finance hedging; reserved capacity after stabilisation | Project Manager |
| R17 | Poor user adoption and resistance to change among ERP users and store managers → productivity loss after go-live | 3 | 3 | 9 | Mitigate | Change and communication plan; super-user network; role-based training; early demos; hypercare floorwalkers | BA and Change Lead |

Summary: 4 Critical (R01, R02, R04, R08), 7 High (R03, R05, R06, R09, R11, R12, R13), 6 Medium (R07, R10, R14, R15, R16, R17); total exposure 196. Target after G3: ≤ 118 by G6 (a 40% reduction).

# Appendix D: RACI Matrix

R = Responsible (does the work); A = Accountable (one per activity; final approval); C = Consulted; I = Informed. The Sponsor and SteerCo approve baselines and gates and are outside the nine-person team.

Table 53: RACI matrix

| # | Activity / deliverable | PM | SA | CE | DE | AD | BI | SE | QA | BA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Charter, SPMP and baselines | A/R | C | I | I | I | I | C | C | C |
| 2 | Requirements and scope baseline | A | C | I | C | C | C | C | C | R |
| 3 | Discovery and 6R migration strategy | A | R | C | C | C | I | C | I | C |
| 4 | Target architecture and security design | C | A/R | R | C | C | C | R | I | I |
| 5 | Landing zone and connectivity build | I | A | R | I | I | I | R | I | I |
| 6 | Identity and access management | I | C | C | I | C | C | A/R | I | C |
| 7 | Data migration (mapping, ETL, mocks, reconciliation) | I | C | C | A/R | C | C | C | R | C |
| 8 | Application replatform and integrations | I | C | R | C | A/R | I | C | C | C |
| 9 | Looker model and reports | I | C | I | R | C | A/R | C | C | R |
| 10 | Security hardening and pen-test coordination | I | C | R | I | C | I | A/R | C | I |
| 11 | POPIA compliance and DPIA | A | C | I | C | I | C | R | I | C |
| 12 | Test planning, SIT, UAT and defect management | I | C | C | C | C | C | C | A/R | R |
| 13 | Cutover planning and execution | A | C | R | R | R | C | C | R | C |
| 14 | Change control and configuration management | A | R | R | I | I | I | C | C | I |
| 15 | Risk and issue management | A/R | C | C | C | C | C | C | C | C |
| 16 | Quality assurance, reviews and audits | A | C | C | C | C | C | C | R | C |
| 17 | Training, communications and adoption | C | I | C | I | C | C | I | I | A/R |
| 18 | Procurement and vendor management | A/R | C | C | I | I | I | C | I | I |
| 19 | Hypercare and handover to operations | A | C | R | R | R | R | R | C | R |
| 20 | Project closure and lessons learned | A/R | C | C | C | C | C | C | C | C |

Checks: every row has exactly one A; PM carries the most A’s (11 of 20 activities as A or A/R), reflecting integration accountability, while technical A’s sit with the relevant specialist.

# Appendix E: Resource Histogram

Figure 6: Resource histogram by role and month

Capacity line: 1,440 hours per month (9 people × 160 h).

- Peak load: M5 and M6 reach 93–95% of nominal capacity. Responses: the MSP provides cutover and hypercare surge (R450,000, in budget); Looker and test preparation start early; overtime is limited to the cutover weekend.

# Appendix F: References

- Bruegge, B. and Dutoit, A.H. (2010) Object-Oriented Software Engineering: Using UML, Patterns, and Java. 3rd edn. Upper Saddle River, NJ: Prentice Hall.

- CIS (Center for Internet Security) (2024) CIS Google Cloud Platform Foundation Benchmark. East Greenbush, NY: CIS.

- Google Cloud (n.d.) Google Cloud Adoption Framework. Available at: https://cloud.google.com/adoption-framework (Accessed: 20 September 2026).

- IEEE (1998) IEEE Std 1058-1998: IEEE Standard for Software Project Management Plans. New York: IEEE.

- IEEE (2008) IEEE Std 1028-2008: IEEE Standard for Software Reviews and Audits. New York: IEEE.

- IEEE (2012) IEEE Std 828-2012: IEEE Standard for Configuration Management in Systems and Software Engineering. New York: IEEE.

- IEEE (2014) IEEE Std 730-2014: IEEE Standard for Software Quality Assurance Processes. New York: IEEE.

- ISO (2015) ISO 9001:2015 Quality management systems: Requirements. Geneva: International Organization for Standardization.

- Paulk, M.C., Curtis, B., Chrissis, M.B. and Weber, C.V. (1993) Capability Maturity Model for Software, Version 1.1. Technical Report CMU/SEI-93-TR-024. Pittsburgh, PA: Software Engineering Institute, Carnegie Mellon University.

- PMI (Project Management Institute) (2021) A Guide to the Project Management Body of Knowledge (PMBOK Guide). 7th edn. Newtown Square, PA: PMI.

- Republic of South Africa (1997) Basic Conditions of Employment Act 75 of 1997. Pretoria: Government Printer.

- Republic of South Africa (2013) Protection of Personal Information Act 4 of 2013. Government Gazette 37067. Pretoria: Government Printer.

End of document.