## Cash Flow
GCP ERP Migration: Monthly Cash Flow Projection (ZAR, excluding VAT)
Karoo Retail Group ¦ 5 Oct 2026 to 2 Apr 2027 ¦ Matches SPMP Appendix B
Cost line | M1 (Oct) | M2 (Nov) | M3 (Dec) | M4 (Jan) | M5 (Feb) | M6 (Mar) | Total
Labour (9 roles) | 589000 | 760500 | 782500 | 856000 | 933000 | 958000 | 4879000
GCP consumption | 0 | 30000 | 90000 | 110000 | 150000 | 240000 | 620000
Google Cloud Partner (MSP) | 0 | 100000 | 100000 | 60000 | 60000 | 130000 | 450000
Connectivity | 0 | 40000 | 50000 | 30000 | 30000 | 30000 | 180000
Security, identity and Looker licences | 0 | 20000 | 30000 | 60000 | 60000 | 65000 | 235000
Penetration test and POPIA review | 0 | 0 | 0 | 0 | 150000 | 70000 | 220000
Training and certification | 0 | 20000 | 20000 | 25000 | 35000 | 60000 | 160000
Tooling | 30000 | 20000 | 20000 | 20000 | 15000 | 15000 | 120000
Load-shedding resilience | 30000 | 20000 | 10000 | 0 | 0 | 0 | 60000
Travel | 15000 | 15000 | 10000 | 15000 | 15000 | 20000 | 90000
Project office and miscellaneous | 10000 | 8000 | 8000 | 8000 | 8000 | 8000 | 50000
Total direct cost | 674000 | 1033500 | 1120500 | 1184000 | 1456000 | 1596000 | 7064000
Contingency (10% of direct) | 67400 | 103350 | 112050 | 118400 | 145600 | 159600 | 706400
Planned spend incl. contingency | 741400 | 1136850 | 1232550 | 1302400 | 1601600 | 1755600 | 7770400
Cumulative (cost baseline) | 741400 | 1878250 | 3110800 | 4413200 | 6014800 | 7770400
Cumulative % of BAC | 9.541% | 24.17% | 40.03% | 56.8% | 77.41% | 100%
Management reserve (5% of direct, SteerCo) | [6 empty] | 353200
Total funding envelope | [6 empty] | 8123600
Check: BAC should equal R7,770,400 | [6 empty] | OK

## WBS
GCP ERP Migration: Work Breakdown Structure and Dictionary (Level 3)
Owner = accountable role; effort covers all roles working on the package. Total matches the 6,880 planned hours in SPMP Section 5.5.
WBS ID | Level | Work package | Level-1 phase | Level-2 group | Owner | Effort (h) | Start week | End week | Start date | End date
1.1.1 | 3 | Charter and mandate approved | 1.0 Initiation and Planning | 1.1 Project initiation | PM | 40 | 1 | 2 | 2026-10-05 | 2026-10-16
1.1.2 | 3 | Stakeholder register and engagement plan | 1.0 Initiation and Planning | 1.1 Project initiation | BA | 40 | 1 | 2 | 2026-10-05 | 2026-10-16
1.1.3 | 3 | Governance set-up (SteerCo, CCB, RACI) | 1.0 Initiation and Planning | 1.1 Project initiation | PM | 30 | 1 | 2 | 2026-10-05 | 2026-10-16
1.2.1 | 3 | SPMP and management plans | 1.0 Initiation and Planning | 1.2 Project planning | PM | 120 | 1 | 3 | 2026-10-05 | 2026-10-23
1.2.2 | 3 | Schedule, cost and resource baselines | 1.0 Initiation and Planning | 1.2 Project planning | PM | 80 | 1 | 3 | 2026-10-05 | 2026-10-23
1.2.3 | 3 | Tooling and environments | 1.0 Initiation and Planning | 1.2 Project planning | CE | 50 | 1 | 3 | 2026-10-05 | 2026-10-23
1.3.1 | 3 | Onboarding and access provisioning | 1.0 Initiation and Planning | 1.3 Team mobilisation | CE | 30 | 1 | 2 | 2026-10-05 | 2026-10-16
1.3.2 | 3 | MSP and vendor RFQ issued | 1.0 Initiation and Planning | 1.3 Team mobilisation | PM | 30 | 1 | 2 | 2026-10-05 | 2026-10-16
2.1.1 | 3 | Migration Center discovery and inventory | 2.0 Discovery and Assessment | 2.1 Estate inventory | SA | 90 | 3 | 5 | 2026-10-19 | 2026-11-06
2.1.2 | 3 | Dependency and 14-interface mapping | 2.0 Discovery and Assessment | 2.1 Estate inventory | AD | 90 | 3 | 5 | 2026-10-19 | 2026-11-06
2.1.3 | 3 | Licence and support-status review | 2.0 Discovery and Assessment | 2.1 Estate inventory | SA | 30 | 3 | 5 | 2026-10-19 | 2026-11-06
2.2.1 | 3 | Data profiling and quality baseline | 2.0 Discovery and Assessment | 2.2 Data assessment | DE | 80 | 3 | 6 | 2026-10-19 | 2026-11-13
2.2.2 | 3 | POPIA data classification and DPIA scoping | 2.0 Discovery and Assessment | 2.2 Data assessment | SE | 50 | 3 | 6 | 2026-10-19 | 2026-11-13
2.2.3 | 3 | Volume, growth and cutover-window analysis | 2.0 Discovery and Assessment | 2.2 Data assessment | DE | 40 | 3 | 6 | 2026-10-19 | 2026-11-13
2.3.1 | 3 | Business and BI requirements | 2.0 Discovery and Assessment | 2.3 Requirements | BA | 90 | 3 | 5 | 2026-10-19 | 2026-11-06
2.3.2 | 3 | Non-functional requirements | 2.0 Discovery and Assessment | 2.3 Requirements | SA | 40 | 3 | 5 | 2026-10-19 | 2026-11-06
2.3.3 | 3 | Compliance requirements | 2.0 Discovery and Assessment | 2.3 Requirements | SE | 30 | 3 | 5 | 2026-10-19 | 2026-11-06
2.4.1 | 3 | 6R disposition per workload | 2.0 Discovery and Assessment | 2.4 Migration strategy | SA | 40 | 5 | 6 | 2026-11-02 | 2026-11-13
2.4.2 | 3 | TCO and GCP cost model | 2.0 Discovery and Assessment | 2.4 Migration strategy | SA | 40 | 5 | 6 | 2026-11-02 | 2026-11-13
2.4.3 | 3 | Migration and cutover approach | 2.0 Discovery and Assessment | 2.4 Migration strategy | SA | 30 | 5 | 6 | 2026-11-02 | 2026-11-13
2.4.4 | 3 | Assessment report and G2 pack | 2.0 Discovery and Assessment | 2.4 Migration strategy | PM | 50 | 5 | 6 | 2026-11-02 | 2026-11-13
3.1.1 | 3 | Solution architecture (HLD/LLD) | 3.0 Architecture and Landing Zone | 3.1 Target architecture | SA | 120 | 6 | 8 | 2026-11-09 | 2026-11-27
3.1.2 | 3 | Network and connectivity design | 3.0 Architecture and Landing Zone | 3.1 Target architecture | CE | 60 | 6 | 8 | 2026-11-09 | 2026-11-27
3.1.3 | 3 | Backup and DR design | 3.0 Architecture and Landing Zone | 3.1 Target architecture | CE | 40 | 6 | 8 | 2026-11-09 | 2026-11-27
3.1.4 | 3 | Security and identity architecture | 3.0 Architecture and Landing Zone | 3.1 Target architecture | SE | 60 | 6 | 8 | 2026-11-09 | 2026-11-27
3.2.1 | 3 | Resource hierarchy, Organization Policy, labelling | 3.0 Architecture and Landing Zone | 3.2 Landing zone build | CE | 80 | 7 | 9 | 2026-11-16 | 2026-12-04
3.2.2 | 3 | Hub-and-spoke network, firewall, DNS | 3.0 Architecture and Landing Zone | 3.2 Landing zone build | CE | 100 | 7 | 9 | 2026-11-16 | 2026-12-04
3.2.3 | 3 | Cloud VPN and Dedicated Interconnect connectivity | 3.0 Architecture and Landing Zone | 3.2 Landing zone build | CE | 60 | 7 | 9 | 2026-11-16 | 2026-12-04
3.2.4 | 3 | Monitoring, logging and Secret Manager | 3.0 Architecture and Landing Zone | 3.2 Landing zone build | CE | 70 | 7 | 9 | 2026-11-16 | 2026-12-04
3.2.5 | 3 | IaC pipelines and environments | 3.0 Architecture and Landing Zone | 3.2 Landing zone build | CE | 120 | 7 | 9 | 2026-11-16 | 2026-12-04
3.3.1 | 3 | Architecture Framework review | 3.0 Architecture and Landing Zone | 3.3 Landing zone validation | SA | 60 | 9 | 9 | 2026-11-30 | 2026-12-04
3.3.2 | 3 | Security baseline scan | 3.0 Architecture and Landing Zone | 3.3 Landing zone validation | SE | 80 | 9 | 9 | 2026-11-30 | 2026-12-04
3.3.3 | 3 | G3 approval | 3.0 Architecture and Landing Zone | 3.3 Landing zone validation | PM | 50 | 9 | 9 | 2026-11-30 | 2026-12-04
4.1.1 | 3 | Source-to-target mapping | 4.0 Build and Migration | 4.1 Data migration | DE | 160 | 9 | 20 | 2026-11-30 | 2027-02-19
4.1.2 | 3 | Replication and ETL pipelines | 4.0 Build and Migration | 4.1 Data migration | DE | 720 | 9 | 20 | 2026-11-30 | 2027-02-19
4.1.3 | 3 | Mock migration 1 | 4.0 Build and Migration | 4.1 Data migration | DE | 150 | 9 | 20 | 2026-11-30 | 2027-02-19
4.1.4 | 3 | Mock migration 2 (dress rehearsal) | 4.0 Build and Migration | 4.1 Data migration | DE | 150 | 9 | 20 | 2026-11-30 | 2027-02-19
4.1.5 | 3 | Reconciliation reports | 4.0 Build and Migration | 4.1 Data migration | DE | 80 | 9 | 20 | 2026-11-30 | 2027-02-19
4.2.1 | 3 | ERP application-tier replatform to Compute Engine | 4.0 Build and Migration | 4.2 Application modernisation | AD | 180 | 9 | 19 | 2026-11-30 | 2027-02-12
4.2.2 | 3 | Database replatform to Cloud SQL for SQL Server | 4.0 Build and Migration | 4.2 Application modernisation | CE | 120 | 9 | 19 | 2026-11-30 | 2027-02-12
4.2.3 | 3 | Integration layer for 14 interfaces | 4.0 Build and Migration | 4.2 Application modernisation | AD | 260 | 9 | 19 | 2026-11-30 | 2027-02-12
4.2.4 | 3 | CI/CD pipelines | 4.0 Build and Migration | 4.2 Application modernisation | AD | 80 | 9 | 19 | 2026-11-30 | 2027-02-12
4.2.5 | 3 | Reporting decoupled from OLTP | 4.0 Build and Migration | 4.2 Application modernisation | AD | 60 | 9 | 19 | 2026-11-30 | 2027-02-12
4.3.1 | 3 | Cloud Identity tenant and hybrid synchronisation | 4.0 Build and Migration | 4.3 Identity and access management | SE | 50 | 9 | 12 | 2026-11-30 | 2026-12-25
4.3.2 | 3 | MFA and Context-Aware Access | 4.0 Build and Migration | 4.3 Identity and access management | SE | 40 | 9 | 12 | 2026-11-30 | 2026-12-25
4.3.3 | 3 | RBAC, PAM and joiner-mover-leaver process | 4.0 Build and Migration | 4.3 Identity and access management | SE | 60 | 9 | 12 | 2026-11-30 | 2026-12-25
4.3.4 | 3 | ERP single sign-on | 4.0 Build and Migration | 4.3 Identity and access management | AD | 30 | 9 | 12 | 2026-11-30 | 2026-12-25
4.4.1 | 3 | BigQuery reporting dataset and semantic views | 4.0 Build and Migration | 4.4 Looker analytics layer | BI | 180 | 12 | 19 | 2026-12-21 | 2027-02-12
4.4.2 | 3 | Reports and dashboards | 4.0 Build and Migration | 4.4 Looker analytics layer | BI | 220 | 12 | 19 | 2026-12-21 | 2027-02-12
4.4.3 | 3 | Row-level security and governance | 4.0 Build and Migration | 4.4 Looker analytics layer | BI | 60 | 12 | 19 | 2026-12-21 | 2027-02-12
4.4.4 | 3 | Dataform pipeline and refresh scheduling | 4.0 Build and Migration | 4.4 Looker analytics layer | BI | 40 | 12 | 19 | 2026-12-21 | 2027-02-12
5.1.1 | 3 | Test strategy and cases | 5.0 Testing, Hardening and Readiness | 5.1 Test planning and SIT | QA | 100 | 16 | 19 | 2027-01-18 | 2027-02-12
5.1.2 | 3 | SIT execution | 5.0 Testing, Hardening and Readiness | 5.1 Test planning and SIT | QA | 180 | 16 | 19 | 2027-01-18 | 2027-02-12
5.1.3 | 3 | Defect triage and regression | 5.0 Testing, Hardening and Readiness | 5.1 Test planning and SIT | AD | 120 | 16 | 19 | 2027-01-18 | 2027-02-12
5.2.1 | 3 | CIS benchmark hardening | 5.0 Testing, Hardening and Readiness | 5.2 Security hardening | SE | 100 | 15 | 21 | 2027-01-11 | 2027-02-26
5.2.2 | 3 | Security Command Center findings remediation | 5.0 Testing, Hardening and Readiness | 5.2 Security hardening | SE | 80 | 15 | 21 | 2027-01-11 | 2027-02-26
5.2.3 | 3 | Independent penetration test and remediation | 5.0 Testing, Hardening and Readiness | 5.2 Security hardening | SE | 90 | 15 | 21 | 2027-01-11 | 2027-02-26
5.2.4 | 3 | POPIA compliance review and DPIA | 5.0 Testing, Hardening and Readiness | 5.2 Security hardening | SE | 50 | 15 | 21 | 2027-01-11 | 2027-02-26
5.3.1 | 3 | Performance and load testing | 5.0 Testing, Hardening and Readiness | 5.3 Performance and DR testing | CE | 80 | 20 | 21 | 2027-02-15 | 2027-02-26
5.3.2 | 3 | DR failover test | 5.0 Testing, Hardening and Readiness | 5.3 Performance and DR testing | CE | 60 | 20 | 21 | 2027-02-15 | 2027-02-26
5.3.3 | 3 | Backup and restore test | 5.0 Testing, Hardening and Readiness | 5.3 Performance and DR testing | CE | 30 | 20 | 21 | 2027-02-15 | 2027-02-26
5.4.1 | 3 | UAT execution | 5.0 Testing, Hardening and Readiness | 5.4 UAT and readiness | BA | 150 | 21 | 22 | 2027-02-22 | 2027-03-05
5.4.2 | 3 | End-user training and communications | 5.0 Testing, Hardening and Readiness | 5.4 UAT and readiness | BA | 90 | 21 | 22 | 2027-02-22 | 2027-03-05
5.4.3 | 3 | Operational readiness and runbooks | 5.0 Testing, Hardening and Readiness | 5.4 UAT and readiness | CE | 50 | 21 | 22 | 2027-02-22 | 2027-03-05
5.4.4 | 3 | Go/No-Go (G6) | 5.0 Testing, Hardening and Readiness | 5.4 UAT and readiness | PM | 20 | 21 | 22 | 2027-02-22 | 2027-03-05
6.1.1 | 3 | Cutover runbook (timed) | 6.0 Cutover and Go-Live | 6.1 Cutover planning | PM | 50 | 20 | 23 | 2027-02-15 | 2027-03-12
6.1.2 | 3 | Rollback plan and decision points | 6.0 Cutover and Go-Live | 6.1 Cutover planning | SA | 30 | 20 | 23 | 2027-02-15 | 2027-03-12
6.1.3 | 3 | Trading freeze and communications | 6.0 Cutover and Go-Live | 6.1 Cutover planning | BA | 20 | 20 | 23 | 2027-02-15 | 2027-03-12
6.2.1 | 3 | Final data synchronisation | 6.0 Cutover and Go-Live | 6.2 Cutover execution | DE | 80 | 23 | 23 | 2027-03-08 | 2027-03-12
6.2.2 | 3 | Integration and DNS switch | 6.0 Cutover and Go-Live | 6.2 Cutover execution | CE | 60 | 23 | 23 | 2027-03-08 | 2027-03-12
6.2.3 | 3 | Smoke tests and business sign-off | 6.0 Cutover and Go-Live | 6.2 Cutover execution | QA | 40 | 23 | 23 | 2027-03-08 | 2027-03-12
6.3.1 | 3 | Legacy set to read-only | 6.0 Cutover and Go-Live | 6.3 Legacy retirement preparation | DE | 10 | 23 | 23 | 2027-03-08 | 2027-03-12
6.3.2 | 3 | Archive and decommission plan | 6.0 Cutover and Go-Live | 6.3 Legacy retirement preparation | CE | 10 | 23 | 23 | 2027-03-08 | 2027-03-12
7.1.1 | 3 | Daily triage (command centre) | 7.0 Hypercare and Closure | 7.1 Hypercare | PM | 90 | 24 | 26 | 2027-03-15 | 2027-04-02
7.1.2 | 3 | Performance tuning and cost optimisation | 7.0 Hypercare and Closure | 7.1 Hypercare | CE | 60 | 24 | 26 | 2027-03-15 | 2027-04-02
7.1.3 | 3 | Parallel-run reconciliation | 7.0 Hypercare and Closure | 7.1 Hypercare | DE | 50 | 24 | 26 | 2027-03-15 | 2027-04-02
7.2.1 | 3 | Knowledge transfer | 7.0 Hypercare and Closure | 7.2 Transition to operations | SA | 50 | 24 | 26 | 2027-03-15 | 2027-04-02
7.2.2 | 3 | Support model and SLAs | 7.0 Hypercare and Closure | 7.2 Transition to operations | PM | 30 | 24 | 26 | 2027-03-15 | 2027-04-02
7.2.3 | 3 | Operations acceptance | 7.0 Hypercare and Closure | 7.2 Transition to operations | PM | 10 | 24 | 26 | 2027-03-15 | 2027-04-02
7.3.1 | 3 | Sponsor acceptance (G7) | 7.0 Hypercare and Closure | 7.3 Project closure | PM | 10 | 26 | 26 | 2027-03-29 | 2027-04-02
7.3.2 | 3 | Lessons learned | 7.0 Hypercare and Closure | 7.3 Project closure | PM | 30 | 26 | 26 | 2027-03-29 | 2027-04-02
7.3.3 | 3 | Benefits realisation plan | 7.0 Hypercare and Closure | 7.3 Project closure | BA | 30 | 26 | 26 | 2027-03-29 | 2027-04-02
7.3.4 | 3 | Final report and archive | 7.0 Hypercare and Closure | 7.3 Project closure | PM | 20 | 26 | 26 | 2027-03-29 | 2027-04-02
8.1.1 | 3 | Status reporting and SteerCo | 8.0 PM, Quality and Governance | 8.1 Project management | PM | 60 | 1 | 26 | 2026-10-05 | 2027-04-02
8.1.2 | 3 | Risk and issue management | 8.0 PM, Quality and Governance | 8.1 Project management | PM | 40 | 1 | 26 | 2026-10-05 | 2027-04-02
8.1.3 | 3 | Change control | 8.0 PM, Quality and Governance | 8.1 Project management | PM | 40 | 1 | 26 | 2026-10-05 | 2027-04-02
8.2.1 | 3 | Quality plan, reviews and audits | 8.0 PM, Quality and Governance | 8.2 Quality management | QA | 50 | 1 | 26 | 2026-10-05 | 2027-04-02
8.2.2 | 3 | Metrics collection and reporting | 8.0 PM, Quality and Governance | 8.2 Quality management | QA | 30 | 1 | 26 | 2026-10-05 | 2027-04-02
8.2.3 | 3 | Process-improvement actions | 8.0 PM, Quality and Governance | 8.2 Quality management | QA | 10 | 1 | 26 | 2026-10-05 | 2027-04-02
8.3.1 | 3 | Repositories and branching | 8.0 PM, Quality and Governance | 8.3 Configuration management | CE | 20 | 1 | 26 | 2026-10-05 | 2027-04-02
8.3.2 | 3 | Baselines and release management | 8.0 PM, Quality and Governance | 8.3 Configuration management | SA | 20 | 1 | 26 | 2026-10-05 | 2027-04-02
8.3.3 | 3 | Configuration audits (FCA/PCA) | 8.0 PM, Quality and Governance | 8.3 Configuration management | QA | 20 | 1 | 26 | 2026-10-05 | 2027-04-02
8.4.1 | 3 | RFQ, evaluation and award | 8.0 PM, Quality and Governance | 8.4 Procurement | PM | 30 | 1 | 26 | 2026-10-05 | 2027-04-02
8.4.2 | 3 | Contract and licence administration | 8.0 PM, Quality and Governance | 8.4 Procurement | PM | 10 | 1 | 26 | 2026-10-05 | 2027-04-02
8.4.3 | 3 | Vendor performance reviews | 8.0 PM, Quality and Governance | 8.4 Procurement | PM | 10 | 1 | 26 | 2026-10-05 | 2027-04-02
|  | Total planned effort |  |  |  | 6880 | Check | OK
Effort by phase
|  | 1.0 Initiation and Planning |  |  |  | 420
|  | 2.0 Discovery and Assessment |  |  |  | 700
|  | 3.0 Architecture and Landing Zone |  |  |  | 900
|  | 4.0 Build and Migration |  |  |  | 2640
|  | 5.0 Testing, Hardening and Readiness |  |  |  | 1200
|  | 6.0 Cutover and Go-Live |  |  |  | 300
|  | 7.0 Hypercare and Closure |  |  |  | 380
|  | 8.0 PM, Quality and Governance |  |  |  | 340
Formulas:
Start date = DATE(2026,10,5)+([Start week]-1)*7
End date = DATE(2026,10,5)+([End week]-1)*7+4

## Gantt
GCP ERP Migration: Gantt Chart (26 weeks, 5 Oct 2026 to 2 Apr 2027)
Bars are drawn by conditional formatting from the Start/End week columns; change a week and the bar moves. Red = critical path. Can be imported into MS Project.
[5 empty] | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29
ID | Task | Start wk | End wk | Critical | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26
1.0 | Initiation and Planning | 1 | 3 | 1
1.1 | Project initiation | 1 | 2 | 1
1.2 | Project planning | 1 | 3 | 1
1.3 | Team mobilisation | 1 | 2 | 0
2.0 | Discovery and Assessment | 3 | 6 | 1
2.1 | Estate inventory | 3 | 5 | 1
2.2 | Data assessment | 3 | 6 | 1
2.3 | Requirements | 3 | 5 | 1
2.4 | Migration strategy | 5 | 6 | 1
3.0 | Architecture and Landing Zone | 6 | 9 | 1
3.1 | Target architecture | 6 | 8 | 1
3.2 | Landing zone build | 7 | 9 | 1
3.3 | Landing zone validation | 9 | 9 | 1
4.0 | Build and Migration | 9 | 20 | 1
4.1 | Data migration | 9 | 20 | 1
4.2 | Application modernisation | 9 | 19 | 0
4.3 | Identity and access management | 9 | 12 | 0
4.4 | Looker analytics layer | 12 | 19 | 0
5.0 | Testing, Hardening and Readiness | 15 | 22 | 1
5.1 | Test planning and SIT | 16 | 19 | 0
5.2 | Security hardening | 15 | 21 | 0
5.3 | Performance and DR testing | 20 | 21 | 0
5.4 | UAT and readiness | 21 | 22 | 1
6.0 | Cutover and Go-Live | 23 | 23 | 1
6.1 | Cutover planning | 20 | 23 | 1
6.2 | Cutover execution | 23 | 23 | 1
6.3 | Legacy retirement preparation | 23 | 23 | 1
7.0 | Hypercare and Closure | 24 | 26 | 1
7.1 | Hypercare | 24 | 26 | 1
7.2 | Transition to operations | 24 | 26 | 1
7.3 | Project closure | 26 | 26 | 1
8.0 | PM, Quality and Governance | 1 | 26 | 0
8.1 | Project management | 1 | 26 | 0
8.2 | Quality management | 1 | 26 | 0
8.3 | Configuration management | 1 | 26 | 0
8.4 | Procurement | 1 | 26 | 0
M1 | ◆ G1 SPMP approved | 3 | 3 | M
M2 | ◆ G2 Strategy approved | 6 | 6 | M
M3 | ◆ G3 Landing zone live | 9 | 9 | M
M4 | ◆ G4 Mock 1 | 16 | 16 | M
M5 | ◆ G5 Build complete, Mock 2 | 20 | 20 | M
M6 | ◆ G6 Go/No-Go | 22 | 22 | M
M7 | ◆ Go-live (12–14 Mar) | 23 | 23 | M
M8 | ◆ G7 Closure | 26 | 26 | M
Legend: blue = activity; red = critical path; gold = milestone. Critical column: 1 = critical, 0 = has float.