CAPE PENINSULA UNIVERSITY OF TECHNOLOGY

Faculty of Informatics & Design  |  Department of Information Technology

PROJECT CHARTER

&

WORK BREAKDOWN STRUCTURE

AI-Driven Model Engineering:

A Systematic Literature Review of Intelligent Model Generation,

Transformation, Validation, and Software Synthesis

| Course Code | APT470S — Applications Development Theory 4 |
| --- | --- |
| NQF Level | 7 |
| Subject Guide Year | 2026 ¦ Term 3 Research Project |
| Team Size | 7 Members (strictly equal workload distribution) |
| Submission Deadline | Close of Business (CoB) — 27 August 2026 |
| Document Version | 1.0 ¦ Living document — update after each milestone review |
| Document Owner | Project Manager (rotating) ¦ All team members accountable |

This charter establishes the formal agreement among the seven team members on purpose, scope,

roles, deliverables, schedule, quality gates, and equal workload allocation for the SLR research project.

# 1. Project Purpose & Strategic Alignment

## 1.1 Purpose Statement

The purpose of this project is to conduct a rigorous, transparent, and reproducible Systematic Literature Review (SLR) that systematically identifies, classifies, and critically evaluates the application of artificial intelligence across the complete model-engineering lifecycle. The review will produce an evidence-based multidimensional taxonomy, maturity model, evaluation hierarchy, verifier-guided reference architecture, and prioritised research agenda for AI-Driven Model Engineering (AI-DME).

## 1.2 Strategic Alignment

This project directly addresses the research problem articulated in the APT470S Term 3 brief: traditional Model-Driven Engineering (MDE) remains constrained by specialist skill requirements, rigid transformation rules, tool complexity, and weak model-code synchronisation, while AI techniques applied to modelling remain fragmented across disconnected tasks. The SLR will consolidate this fragmented evidence base and provide a scientifically defensible foundation for trustworthy, verifier-guided, human-accountable AI-DME.

## 1.3 Research Aim (from Brief)

To systematically identify, classify, and critically evaluate the application of artificial intelligence across the model-engineering lifecycle and to develop an evidence-based taxonomy, maturity model, reference architecture, and future research agenda for AI-Driven Model Engineering.

# 2. Project Objectives & Success Criteria

## 2.1 SMART Project Objectives

- Complete a PRISMA-compliant SLR protocol, multi-database search, dual-reviewer screening, full-text eligibility, data extraction, and quality assessment of all included studies by the scheduled milestone dates.

- Synthesise evidence across the 15 research questions (RQ1–RQ15) covering landscape, lifecycle, intelligence/automation, quality/validation, transformation, trustworthiness, and scholarly contribution.

- Produce original scholarly artefacts: multidimensional taxonomy, 6-level automation continuum, seven-level model-quality hierarchy, verifier-guided reference architecture, gap matrix, and prioritised research agenda.

- Deliver a 20–30 page academic paper (APA 7th, Times New Roman 11 pt, 1.5 spacing) plus supporting Excel evidence repository, PRISMA flowchart, comparison tables, and oral presentation slides.

- Maintain strict equal workload across all seven members and achieve a minimum Competent (60–74%) band, targeting Excellent (75–100%) on the official assessment rubric.

## 2.2 Success Criteria (Mapped to Rubric)

| # | Rubric Criterion | Marks | Team Success Target |
| --- | --- | --- | --- |
| 1 | Research Significance | 2 | Compelling, well-contextualised significance with recent high-quality citations |
| 2 | Research Objectives | 3 | Fully aligned RQs covering the complete AI-DME lifecycle |
| 3 | Review Protocol & Methodological Rigour | 5 | Complete reproducible protocol + PRISMA reporting |
| 4 | Search Strategy, Selection & Eligibility | 5 | Comprehensive strings, explicit I/E criteria, full PRISMA flow |
| 5 | Quality Assessment & Risk of Bias | 10 | 18-item checklist applied; scores used in evidence weighting |
| 6 | Data Extraction, Coding & Traceability | 10 | Pilot-tested framework; full traceability to primary studies |
| 7 | Evidence Synthesis & Critical Analysis | 15 | Descriptive + thematic + comparative synthesis; no unsupported claims |
| 8 | Taxonomy, Maturity Model, Evaluation Hierarchy & Framework | 15 | Original, evidence-grounded artefacts with clear relationships |
| 9 | Reference Architecture, Research Agenda & Contribution | 5 | Verifier-guided architecture + prioritised actionable gaps |
| 10 | Academic Writing, Referencing & Visuals | 5 | APA 7th, polished formatting, ethical AI declaration |
| 11 | Quality of Academic Paper + Data Extraction (Excel) | 10 | Complete, consistent Excel evidence repository |
| 12 | Oral Professional Presentation & Slides | 10 | Professional delivery with high-quality visual aids |
| 13 | Others (participation, engagement) | 5 | Consistent participation and collaborative contribution |
| TOTAL |  | 100 | Target band: Excellent (75–100) |

# 3. Project Scope

## 3.1 In-Scope

- Complete model-engineering lifecycle (requirements understanding → runtime adaptation & self-adaptive systems).

- AI technologies: LLMs, ML, DL, multimodal foundation models, knowledge graphs, reinforcement learning, neuro-symbolic AI, intelligent agents.

- Modelling languages & artefacts: UML, SysML, BPMN, DSLs, architectural models, metamodels.

- Publication window: January 2015 – final search date (2026).

- Primary databases: Scopus, Web of Science, IEEE Xplore, ACM Digital Library, ScienceDirect, SpringerLink (+ Google Scholar snowballing).

- Production of taxonomy, maturity model (Levels 1–6), evaluation hierarchy, reference architecture, gap matrix, research agenda, PRISMA flow, and Excel evidence repository.

- Critical comparative synthesis (AI vs human, LLM-only vs verifier-guided, textbook vs industrial, etc.).

## 3.2 Out-of-Scope

- Purely conceptual discussion of AI or MDE without a technical contribution.

- Use of the word “model” solely to mean a predictive machine-learning model.

- Code generation that does not use or produce a software model.

- Non-software CAD models outside systems engineering.

- Editorials, abstracts, posters, or tutorials without full results.

- Primary empirical experiments or tool implementation (this is a secondary study).

## 3.3 Assumptions

- All seven members have institutional access to the six primary databases.

- Team members will apply dual independent screening and resolve conflicts through discussion.

- A pilot extraction and quality-assessment round will be performed on two shared papers before full workload split.

- The team will declare the type and level of any AI assistance used in writing.

## 3.4 Constraints

- Hard deadline: CoB 27 August 2026.

- Paper length: 20–30 pages excluding references and appendices.

- Formatting: Times New Roman 11 pt, 1.5 line spacing, 1-inch margins, fully justified, APA 7th.

- Equal workload distribution is mandatory.

# 4. Team Organisation & Equal Workload Model

## 4.1 Role Architecture

Roles are designed so that every member owns a primary database lane, participates in dual screening, shares data-extraction and quality-assessment load, and co-authors specific paper sections. A rotating Project Manager (weekly) ensures coordination without creating a permanent hierarchy.

| Member | Primary Database / Role | Core Responsibilities | Paper Sections Owned |
| --- | --- | --- | --- |
| Person 1 | IEEE Xplore | Search, dual screening, extraction, QA | Introduction + RQ1–RQ2 (Landscape) |
| Person 2 | ACM Digital Library | Search, dual screening, extraction, QA | Methodology (Protocol, Search, I/E, PRISMA) |
| Person 3 | ScienceDirect | Search, dual screening, extraction, QA | RQ3–RQ5 (Lifecycle & Requirements-to-Model) |
| Person 4 | SpringerLink | Search, dual screening, extraction, QA | RQ6–RQ7 (Intelligence & Automation Continuum) |
| Person 5 | Scopus | Search, dual screening, extraction, QA | RQ8–RQ9 (Quality, Validation & Hierarchy) |
| Person 6 | Web of Science | Search, dual screening, extraction, QA | RQ10–RQ11 (Transformation & Comparative Synthesis) |
| Person 7 | Google Scholar Snowball + Floating Support | Backward/forward snowballing, gap filling, extraction, QA | RQ12–RQ15 (Trust, Adoption, Taxonomy, Architecture, Agenda) |

## 4.2 Equal Workload Principles

- Every database search result is dual-screened (Reviewer 1 + Reviewer 2).

- Included papers are split evenly for full-text eligibility, data extraction, and quality assessment after pilot testing.

- Each member owns approximately equal page-count and synthesis depth for the final paper.

- Presentation slides and oral delivery are shared; each member presents their owned sections.

- Tracker maintenance (Excel) is a shared duty; Person 7 acts as floating capacity when any lane falls behind.

## 4.3 Dual-Reviewer Pairing Matrix (Screening)

| Database | Primary Reviewer | Second Reviewer | Conflict Resolver |
| --- | --- | --- | --- |
| IEEE Xplore | Person 1 | Person 2 | Person 7 |
| ACM DL | Person 2 | Person 3 | Person 7 |
| ScienceDirect | Person 3 | Person 4 | Person 1 |
| SpringerLink | Person 4 | Person 5 | Person 2 |
| Scopus | Person 5 | Person 6 | Person 3 |
| Web of Science | Person 6 | Person 1 | Person 4 |
| Snowball (GS) | Person 7 | Person 5 | Person 6 |

# 5. Key Deliverables

| ID | Deliverable | Format / Standard | Owner(s) |
| --- | --- | --- | --- |
| D1 | SLR Protocol (pre-registered if possible) | Word / PDF | Person 2 (lead) + all |
| D2 | Team Tracker (Screening, Eligibility, Extraction, QA, PRISMA) | Excel (.xlsx) | All (Person 7 maintains) |
| D3 | PRISMA 2020 Flow Diagram | Figure (vector preferred) | Person 2 + Person 7 |
| D4 | Complete Data-Extraction & Quality-Assessment Sheets | Excel tabs | All (equal split) |
| D5 | Multidimensional Taxonomy Diagram | Figure | Person 7 (lead) |
| D6 | AI-DME Maturity / Automation Continuum (Levels 1–6) | Table + Figure | Person 4 (lead) |
| D7 | Seven-Level Model-Quality & Assurance Hierarchy | Table + Figure | Person 5 (lead) |
| D8 | Verifier-Guided Reference Architecture | Architecture diagram | Person 7 (lead) |
| D9 | Gap Matrix (Covered vs Under-explored) | Table | Person 7 + Person 3 |
| D10 | Final Academic Paper (20–30 pages) | Word (.docx) APA 7th | All (section owners) |
| D11 | Oral Presentation Slides + Delivery | PowerPoint / PDF | All (shared) |
| D12 | AI-Usage Declaration | Statement in paper | Project Manager |

# 6. Work Breakdown Structure (WBS)

The WBS decomposes the project into six major phases. Each work package is assigned so that total effort is balanced across the seven members. Effort estimates are relative (person-days) assuming a typical student working week.

## Phase 0 — Project Initiation & Protocol (Days 1–5)

| WP ID | Work Package | Effort (pd) | Owner(s) |
| --- | --- | --- | --- |
| 0.1 | Kick-off meeting, role confirmation, shared drive setup | 0.5 | All |
| 0.2 | Draft & agree SLR protocol (databases, strings, I/E, QA checklist) | 2.0 | Person 2 (lead) + All review |
| 0.3 | Pilot-test search string on one database; refine synonyms | 1.0 | Person 1 + Person 5 |
| 0.4 | Configure Team Tracker Excel; freeze column definitions | 0.5 | Person 7 |
| 0.5 | Protocol sign-off & (optional) registration | 0.5 | All |

## Phase 1 — Multi-Database Search & Title/Abstract Screening (Days 6–14)

| WP ID | Work Package | Effort (pd) | Owner(s) |
| --- | --- | --- | --- |
| 1.1 | Execute search on IEEE Xplore; export & log in Tracker | 1.5 | Person 1 |
| 1.2 | Execute search on ACM Digital Library; export & log | 1.5 | Person 2 |
| 1.3 | Execute search on ScienceDirect; export & log | 1.5 | Person 3 |
| 1.4 | Execute search on SpringerLink; export & log | 1.5 | Person 4 |
| 1.5 | Execute search on Scopus; export & log | 1.5 | Person 5 |
| 1.6 | Execute search on Web of Science; export & log | 1.5 | Person 6 |
| 1.7 | Deduplication across all databases | 1.0 | Person 7 + Person 2 |
| 1.8 | Dual title/abstract screening (all records) | 4.0 total | All (paired) |
| 1.9 | Conflict resolution meetings & Final Decision column | 1.0 | All |

## Phase 2 — Full-Text Eligibility & Snowballing (Days 15–22)

| WP ID | Work Package | Effort (pd) | Owner(s) |
| --- | --- | --- | --- |
| 2.1 | Full-text retrieval & eligibility decisions (equal split) | 3.5 total | All |
| 2.2 | Document exclusion reasons (feeds PRISMA) | 0.5 | All |
| 2.3 | Backward snowballing on included set | 1.5 | Person 7 |
| 2.4 | Forward snowballing (citations) on included set | 1.5 | Person 7 + Person 5 |
| 2.5 | Screen snowball results; final Include list freeze | 1.0 | All |
| 2.6 | Update PRISMA Counts tab & draft flow diagram | 0.5 | Person 2 + Person 7 |

## Phase 3 — Data Extraction & Quality Assessment (Days 23–32)

| WP ID | Work Package | Effort (pd) | Owner(s) |
| --- | --- | --- | --- |
| 3.1 | Pilot extraction + QA on 2 shared papers; calibrate coding | 1.5 | All (pair cross-check) |
| 3.2 | Full data extraction (equal split of final papers) | 5.0 total | All |
| 3.3 | 18-item Quality Assessment scoring (0 / 0.5 / 1) | 3.5 total | All (cross-check pairs) |
| 3.4 | Consistency audit of extraction & QA scores | 1.0 | Person 2 + Person 7 |
| 3.5 | Assign maturity levels (1–6) to each study | 0.5 | Person 4 (lead) + All |

## Phase 4 — Evidence Synthesis & Scholarly Artefacts (Days 33–42)

| WP ID | Work Package | Effort (pd) | Owner(s) |
| --- | --- | --- | --- |
| 4.1 | Descriptive analysis (trends, venues, AI tech, domains) | 1.5 | Person 1 |
| 4.2 | Thematic synthesis — Lifecycle & Requirements-to-Model | 1.5 | Person 3 |
| 4.3 | Thematic synthesis — Roles, Automation Continuum | 1.5 | Person 4 |
| 4.4 | Thematic synthesis — Quality, Validation, Hierarchy | 1.5 | Person 5 |
| 4.5 | Comparative synthesis — Transformation, productivity, baselines | 1.5 | Person 6 |
| 4.6 | Trustworthiness, adoption, gap matrix, research agenda | 2.0 | Person 7 |
| 4.7 | Build Taxonomy, Maturity Model, Hierarchy, Architecture figures | 2.0 | Person 4, 5, 7 |
| 4.8 | Cross-team synthesis workshop & evidence-strength discussion | 1.0 | All |

## Phase 5 — Paper Writing, Visuals, Presentation & Submission (Days 43–55)

| WP ID | Work Package | Effort (pd) | Owner(s) |
| --- | --- | --- | --- |
| 5.1 | Write Introduction, Background, Aim, RQs | 1.5 | Person 1 |
| 5.2 | Write Methodology (Protocol, Search, I/E, PRISMA, QA) | 2.0 | Person 2 |
| 5.3 | Write Results — Landscape & Lifecycle sections | 1.5 | Person 1 + Person 3 |
| 5.4 | Write Results — Intelligence, Quality, Transformation | 2.0 | Person 4 + Person 5 + Person 6 |
| 5.5 | Write Discussion, Taxonomy, Architecture, Agenda, Conclusion | 2.0 | Person 7 |
| 5.6 | Integrate all sections; enforce APA 7th, formatting, citations | 1.5 | Person 2 (lead editor) + All |
| 5.7 | Produce all figures/tables (PRISMA, Taxonomy, Gap Matrix, etc.) | 1.5 | Person 7 + Person 4 + Person 5 |
| 5.8 | Final proof-read, plagiarism check, AI-declaration | 1.0 | All |
| 5.9 | Prepare presentation slides & rehearse oral delivery | 1.5 | All (shared) |
| 5.10 | Package & submit (paper + Excel + slides) by CoB 27 Aug 2026 | 0.5 | Project Manager of the week |

# 7. High-Level Schedule & Milestones

| Milestone | Target Date Window | Exit Criteria | Rubric Link |
| --- | --- | --- | --- |
| M0 — Protocol Signed | Day 5 | Protocol agreed; Tracker ready; pilot string tested | C3, C4 |
| M1 — Screening Complete | Day 14 | All DBs searched; dual screening done; Final Decisions logged | C4 |
| M2 — Include List Frozen | Day 22 | Full-text + snowball finished; PRISMA counts final | C4 |
| M3 — Extraction & QA Done | Day 32 | Every included paper extracted & scored; maturity assigned | C5, C6 |
| M4 — Synthesis Artefacts | Day 42 | Taxonomy, maturity model, hierarchy, architecture, gap matrix ready | C7, C8, C9 |
| M5 — Full Draft Paper | Day 48 | All sections drafted; figures integrated; APA applied | C10, C11 |
| M6 — Submission Ready | Day 55 / 27 Aug 2026 | Final paper + Excel + slides + AI declaration submitted | All criteria |

# 8. Risk Register & Mitigation

| ID | Risk | Impact | Mitigation |
| --- | --- | --- | --- |
| R1 | Uneven database hit rates (some DBs return far more records) | High | Person 7 provides floating capacity; re-balance screening load mid-phase |
| R2 | Low inter-rater agreement on screening or QA | High | Pilot calibration on 2 papers; conflict-resolution protocol; third reviewer |
| R3 | Insufficient industrial / large-scale studies | Med | Explicitly surface as a gap; strengthen snowballing; note in limitations |
| R4 | Member dropout or illness | High | All work logged in shared Tracker; Person 7 + remaining members absorb load |
| R5 | Time overrun on synthesis / writing | High | Hard internal deadlines 5 days before final; daily stand-ups in final week |
| R6 | Plagiarism or unacknowledged AI use | Critical | Mandatory originality check; transparent AI declaration; critical analysis required |
| R7 | Inconsistent coding of extraction fields | Med | Pilot on shared papers; codebook freeze; consistency audit (WP 3.4) |

# 9. Quality Management & Governance

## 9.1 Quality Gates

- Gate 0: Protocol signed by all members before any full search.

- Gate 1: Dual-reviewer agreement rate ≥ 80 % after calibration; remaining conflicts resolved.

- Gate 2: Every exclusion has a documented reason; PRISMA counts reconcile.

- Gate 3: Extraction completeness check — no empty mandatory fields; maturity level assigned.

- Gate 4: Synthesis artefacts reviewed against evidence; no unsupported generalisations.

- Gate 5: Final paper passes formatting, APA, originality, and AI-declaration checks.

## 9.2 Communication Cadence

- Weekly 45-minute stand-up (rotating facilitator).

- Shared Excel Tracker is the single source of truth for status.

- WhatsApp / Teams channel for rapid blockers; decisions logged in Tracker notes.

- Mid-phase and pre-submission formal reviews.

## 9.3 Decision Rights

- Methodological decisions (I/E borderline cases, QA score disputes): dual reviewers + third resolver.

- Paper structure / artefact design: consensus of section owners; Project Manager breaks ties.

- Final submission package: unanimous sign-off.

# 10. Equal Workload Summary (Target Balance)

The following table summarises the intended relative effort distribution. All figures are approximate person-days across the full project lifecycle and are designed to be within ±10 % of the team mean.

| Member | Primary Focus | Search + Screen | Extract + QA | Synthesis + Write | Total (pd) |
| --- | --- | --- | --- | --- | --- |
| Person 1 | IEEE + Landscape | ~3.0 | ~2.5 | ~3.0 | ~8.5 |
| Person 2 | ACM + Methodology | ~3.0 | ~2.5 | ~3.5 | ~9.0 |
| Person 3 | ScienceDirect + Lifecycle | ~3.0 | ~2.5 | ~3.0 | ~8.5 |
| Person 4 | Springer + Automation | ~3.0 | ~2.5 | ~3.5 | ~9.0 |
| Person 5 | Scopus + Quality | ~3.0 | ~2.5 | ~3.0 | ~8.5 |
| Person 6 | WoS + Transformation | ~3.0 | ~2.5 | ~3.0 | ~8.5 |
| Person 7 | Snowball + Taxonomy/Arch | ~2.5 | ~2.5 | ~4.0 | ~9.0 |

Total estimated team effort ≈ 61 person-days. Mean ≈ 8.7 person-days per member. Variation is deliberately kept within a narrow band so that no member carries a materially heavier load.

# 11. Charter Approval & Sign-Off

By signing below, each team member confirms that they have read, understood, and accept the purpose, scope, roles, equal-workload model, schedule, quality gates, and success criteria defined in this Project Charter and Work Breakdown Structure.

| Member | Role / Database | Signature | Date |
| --- | --- | --- | --- |
| Person 1 | IEEE Xplore |  |  |
| Person 2 | ACM Digital Library |  |  |
| Person 3 | ScienceDirect |  |  |
| Person 4 | SpringerLink |  |  |
| Person 5 | Scopus |  |  |
| Person 6 | Web of Science |  |  |
| Person 7 | Snowball + Floating Support |  |  |

— End of Project Charter & Work Breakdown Structure —

Document controlled under the team shared drive. Update version number after any material change.