## Slide 1: PERT calculation process summary
Draw the network using the AON or AOA convention.
Calculate the expected durations and use these as the durations on the network. (Hint: Use the ceiling(ED), i.e. e.g. given a number like 5.1 make it 6.
Calculate the early start and early finish times via the forward-pass and backward pass as usual.
For the activities or tasks that lie on the critical path; calculate the variances for each ; and add these variances to find .

## Slide 2
Calculate the z value using the formula , where x is a particular end date.
Look up the probability using the z-table.
Alternatively, if given a probability, and required to determine an end time, then the formula must be utilised as follows:
Look up the z value associated with the probability using the z-table.
Calculate the duration or end time using .