PFD473S

Professional Development Methods 4

Comprehensive Practice Paper Answers

With Concept Explanations & Step-by-Step Workings

| Topic | Coverage |
| --- | --- |
| Theory | Mintzberg, Fayol, Lifecycle Models, IEEE Standards |
| Finance | Payback Period, NPV, IRR — fully worked |
| PERT | Network, Expected Times, Confidence, Probability |
| Gantt & Costs | Gantt chart logic + full resource cost calculation |

Cape Peninsula University of Technology  |  NQF Level 7  |  2026

# SECTION 1: Theory Questions

These questions test your understanding of project management concepts and software lifecycle models. Think of this section as the 'big picture' — the human and methodological side of running a software project.

## Q1.1 — Mintzberg's Managerial Roles [8 marks]

Henry Mintzberg argued that managers don't just 'plan and control' — they actually wear many hats throughout the working day. He grouped these hats into three role families.

| Role Family | Specific Role | What the PM actually does |
| --- | --- | --- |
| Interpersonal | Figurehead | Performs ceremonial duties — representing the project at formal events, signing official documents |
| Interpersonal | Leader | Motivates the team, hires/fires staff, resolves conflicts, sets the pace and culture |
| Interpersonal | Liaison | Builds relationships outside the team — other departments, clients, vendors, stakeholders |
| Informational | Monitor | Scans for information: reads reports, attends meetings, tracks industry trends relevant to the project |
| Informational | Disseminator | Passes relevant information DOWN to the team — translates client expectations into developer tasks |
| Informational | Spokesperson | Communicates project status UPWARD/OUTWARD — reports to executives or the client |
| Decisional | Entrepreneur | Identifies opportunities to improve — initiates new sub-projects or process improvements |
| Decisional | Disturbance Handler | Reacts to crises: a key developer leaving, a server crash, a missed deadline |
| Decisional | Resource Allocator | Decides how budget, people, and time are split across tasks |
| Decisional | Negotiator | Negotiates scope, deadlines, or budget with clients or management in real time |

💡 Why does this matter? In practice, a project manager spends very little time formally 'planning'. Most of their day is reacting (Disturbance Handler), communicating (Disseminator, Spokesperson) and negotiating (Negotiator). Mintzberg's model reflects reality better than any textbook definition of management.

## Q1.2 — Henri Fayol's Five Functions of Management [6 marks]

While Mintzberg describes what managers DO, Fayol describes what management IS. His five functions are timeless and still form the backbone of most management curricula.

| Function | Simple Name | What it means for a software project |
| --- | --- | --- |
| Prevoyance (Planning) | Plan | Define the project's goals, milestones, budget, and schedule before work begins. In software: write the SPMP. |
| Organiser (Organising) | Organise | Build the team structure — who reports to whom, which team handles which module, how information flows. |
| Commander (Commanding) | Direct | Give clear instructions and keep the team active and productive. Leadership in action. |
| Coordination | Coordinate | Ensure that all teams' outputs fit together — the front-end team's interface matches what the back-end delivers. |
| Contrôle (Controlling) | Control | Compare actual progress to the plan. If off-track, take corrective action. In software: Project Monitoring & Control. |

💡 Memory trick Use the acronym PODCC: Plan → Organise → Direct → Coordinate → Control.

## Q1.3 — Archetypal Role Players in Software Development [6 marks]

A software system is never built by one person. Here are the key players and why each one is essential:

| Role | Responsibility | Why they're necessary |
| --- | --- | --- |
| Client / Customer | Owns the problem; funds the project | Without them there's no project and no direction |
| Users (End Users) | Will actually use the system daily | Their needs define whether the system succeeds or fails in the real world |
| Project Manager | Plans, monitors, controls the project | Someone must keep time, budget, and scope in check |
| Systems Analyst | Bridges client needs and technical solutions | Translates business language into technical requirements |
| Software Architect | Designs the high-level system structure | Ensures the system is scalable, maintainable and coherent |
| Developers (Programmers) | Write the actual code | They turn designs into working software |
| Testers (QA) | Find defects before users do | Quality cannot be added after the fact — it must be verified |
| Technical Writers | Document the system and user guides | Undocumented software cannot be maintained or used effectively |
| Domain Experts | Provide expert knowledge of the problem area | Ensures the system behaves correctly in its specific context (e.g., medical, financial) |

# SECTION 2: Software Lifecycle Models

## Q2.1 — Waterfall vs. Unified Process (USDP) [10 marks]

### The Waterfall Model

Think of the Waterfall model as a relay race — each runner (phase) must finish and hand the baton before the next one starts. You cannot go backwards.

| Phase | What happens |
| --- | --- |
| Requirements | All system requirements gathered upfront and frozen |
| Design | Full system architecture designed |
| Implementation | All code written |
| Verification & Validation | System tested for the first time |
| Installation & Operation | Delivered to client |

- Strength: Simple, easy to manage, clear milestones — good for small projects with stable requirements.

- Weakness: Changes are expensive and difficult. Testing happens too late. Clients only see the product at the very end.

### The Unified Software Development Process (USDP)

Think of USDP as a spiral staircase — you keep going around (iterating) but each loop takes you higher (more complete and refined). It was created by the same team who invented UML.

| Phase | Focus | Key output |
| --- | --- | --- |
| Inception | Is this project worth doing? | Business case, initial risk list |
| Elaboration | What are the requirements and architecture? | Stable architecture, refined requirements |
| Construction | Build the system, iteration by iteration | Working software releases |
| Transition | Get the system to users | Deployed system, trained users, bug fixes |

### Direct Comparison

| Feature | Waterfall | USDP |
| --- | --- | --- |
| Development approach | Sequential (one phase at a time) | Iterative and incremental |
| Requirements | Fixed upfront | Refined throughout |
| Testing | Late (only after coding) | Continuous across all phases |
| Risk management | Implicit / assumed | Explicit — addressed in Elaboration |
| Client involvement | At the start and end only | Ongoing throughout iterations |
| Good for | Small, stable, well-understood projects | Large, complex, evolving projects |
| Integration | All at the end (big bang) | Progressive — continuous integration |

💡 Simple analogy Waterfall is like building a house — you lay the foundation, frame it, roof it, finish it in strict order. USDP is like writing a novel — you draft, review, revise, draft again, polish, and refine until it's great.

## Q2.2 — IEEE 1074 Standard [10 marks]

The IEEE 1074 standard does NOT define a specific lifecycle model to follow. Instead, it defines which processes MUST be present in whichever model you choose to use.

Think of it as a quality checklist for lifecycle models. An organisation is free to choose Waterfall, Spiral, USDP or any other model — but the model must include all the activities specified by IEEE 1074.

| Process Group | What it covers |
| --- | --- |
| Life Cycle Modelling | Choosing the right lifecycle model for the project |
| Project Management | Initiation, Monitoring & Control, Quality Management |
| Pre-development | Concept Exploration, System Allocation |
| Development | Requirements, Design, Implementation |
| Post-development | Installation, Operation & Support, Maintenance, Retirement |
| Integral (cross-cutting) | Verification & Validation, Configuration Management, Documentation, Training |

Why was this standard necessary? Before IEEE 1074, different organisations used wildly different lifecycle processes, making it impossible to compare, evaluate, or audit software projects consistently. The standard provides a common framework that any organisation managing software projects can adopt, regardless of the specific lifecycle model they prefer.

💡 Key insight IEEE 1074 is about completeness — ensuring no critical activity (like Quality Management or Configuration Management) gets left out, regardless of which lifecycle model you use. IEEE 12207 later superseded it with a broader international framework.

# SECTION 3: Financial Analysis — NPV, IRR & Payback

This section covers the June 2022 exam Question 3. The scenario: An investment of R200,000 today generates R40,000 per year for 7 years. We need to evaluate whether this is worth it.

💡 The core idea Money today is worth MORE than the same money in the future — because today's money can earn interest. So R40,000 received in Year 7 is NOT worth R40,000 in today's terms. We need to 'discount' it back to today's value. That's the Time Value of Money (TVM) principle.

## Q3.1 — Payback Period [2 marks]

The payback period asks: How many years until I get my money back?

⚠️ Formula Payback Period = Initial Investment ÷ Annual Cash Flow

| Year | Cash Flow | Cumulative Cash Flow |
| --- | --- | --- |
| 0 (Today) | −R200,000 | −R200,000 |
| 1 | +R40,000 | −R160,000 |
| 2 | +R40,000 | −R120,000 |
| 3 | +R40,000 | −R80,000 |
| 4 | +R40,000 | −R40,000 |
| 5 | +R40,000 | R0 — PAID BACK! |
| 6 | +R40,000 | +R40,000 |
| 7 | +R40,000 | +R80,000 |

✅ Payback Period = R200,000 ÷ R40,000 = 5 years After 5 years, the initial investment is fully recovered. This is a simple and quick calculation — but it ignores the time value of money and any value beyond Year 5.

## Q3.2 — Net Present Value at 8% [8 marks]

NPV discounts each future cash flow back to today's value, then sums them up. If NPV > 0, the investment adds value. If NPV < 0, you'd be better off putting the money in the bank.

⚠️ Formula PV = FV ÷ (1 + r)ⁿ where r = interest rate, n = year number

| Year (n) | Future Value (FV) | Discount Factor 1÷(1.08)ⁿ | Present Value (PV) |
| --- | --- | --- | --- |
| 0 | −R200,000.00 | 1.0000 | −R200,000.00 |
| 1 | +R40,000.00 | 0.9259 | R37037.04 |
| 2 | +R40,000.00 | 0.8573 | R34293.55 |
| 3 | +R40,000.00 | 0.7938 | R31753.29 |
| 4 | +R40,000.00 | 0.7350 | R29401.19 |
| 5 | +R40,000.00 | 0.6806 | R27223.33 |
| 6 | +R40,000.00 | 0.6302 | R25206.79 |
| 7 | +R40,000.00 | 0.5835 | R23339.62 |
| TOTAL PV of Inflows |  |  | R208254.80 |

✅ NPV = R208254.80 − R200,000.00 = R8254.80 ✓ The NPV is POSITIVE (R8254.80), which means this project is worthwhile at 8% interest. It adds R8254.80 of value in today's terms. Accept the project.

## Q3.3 — Internal Rate of Return (IRR) [10 marks]

The IRR is the discount rate that makes NPV exactly zero. It represents the effective yield of the investment. We find it using interpolation between two known rates.

💡 Concept Think of IRR as the 'break-even interest rate'. If your bank offers 8% and the project's IRR is 9.22%, the project beats the bank — invest in the project.

### Step 1: Calculate NPV at 8% (already done) and at 10%

| Year | PV at 8% | PV at 10% |
| --- | --- | --- |
| 1 | R37037.04 | R36363.64 |
| 2 | R34293.55 | R33057.85 |
| 3 | R31753.29 | R30052.59 |
| 4 | R29401.19 | R27320.54 |
| 5 | R27223.33 | R24836.85 |
| 6 | R25206.79 | R22578.96 |
| 7 | R23339.62 | R20526.32 |
| Total PV | R208254.80 | R194736.75 |
| NPV (minus R200k) | R8254.80 (positive ✓) | R-5263.25 (negative ✓) |

### Step 2: Interpolate

Since NPV is positive at 8% and negative at 10%, the true IRR lies somewhere between 8% and 10%. We use linear interpolation:

⚠️ IRR Formula IRR ≈ r₁ + [ NPV₁ ÷ (NPV₁ − NPV₂) ] × (r₂ − r₁)

| Variable | Value |
| --- | --- |
| r₁ (lower rate) | 8% |
| r₂ (higher rate) | 10% |
| NPV₁ (at 8%) | R8254.80 |
| NPV₂ (at 10%) | R-5263.25 |
| Numerator: NPV₁ | R8254.80 |
| Denominator: NPV₁ − NPV₂ | R13518.05 |
| Fraction | 0.6107 |
| × (10% − 8%) = × 2% | 1.2213% |
| IRR = 8% + above | ≈ 9.22% |

✅ IRR ≈ 9.22% Since the IRR (9.22%) is GREATER than the required rate of return (8%), the project is worthwhile. Decision: ACCEPT the project. The project generates a return of 9.22% — better than the 8% cost of capital.

# SECTION 4: PERT Network Analysis

These questions appear in both practice papers. The network uses PERT (Program Evaluation and Review Technique) — a probabilistic scheduling method that accounts for uncertainty in activity durations.

💡 The Big Picture In the real world, we can rarely say 'this task will take exactly 30 days'. PERT lets us say: 'optimistically 15 days, most likely 32, worst case 42'. From those three estimates, it calculates a weighted average (expected time) and a measure of uncertainty (variance).

## Step 1: Calculate Expected Times and Variances

⚠️ Formulas Expected Time: tₑ = (Optimistic + 4 × Most Likely + Pessimistic) ÷ 6 Variance: σ² = [ (Pessimistic − Optimistic) ÷ 6 ]² The '4×' weight reflects that the most likely time is usually the most informative estimate.

| Activity | Predecessors | Optimistic | Most Likely | Pessimistic | Expected Time tₑ | Variance σ² |
| --- | --- | --- | --- | --- | --- | --- |
| A | None | 42 | 50 | 55 | 49.50 | 4.694 |
| B | A | 15 | 32 | 42 | 30.83 | 20.250 |
| C | A | 41 | 43 | 47 | 43.33 | 1.000 |
| D | B | 64 | 78 | 88 | 77.33 | 16.000 |
| E | B | 40 | 45 | 58 | 46.33 | 9.000 |
| F | C & D | 2 | 4 | 7 | 4.17 | 0.694 |
| G | E | 12 | 17 | 23 | 17.17 | 3.361 |
| H | E & F | 20 | 24 | 25 | 23.50 | 0.694 |

## Step 2: Network Structure & Path Durations

The network diagram connects activities based on their predecessors. Here's what the network looks like in text form:

| Path | Activities | Total Duration (days) |
| --- | --- | --- |
| A→B→D→F→H | A → B → D → F → H | 185.33 |
| A→B→E→H | A → B → E → H | 150.17 |
| A→B→E→G | A → B → E → G | 143.83 |
| A→C→F→H | A → C → F → H | 120.50 |

✅ Critical Path: A → B → D → F → H = 185.33 days The critical path is the LONGEST path through the network. It determines the minimum project duration. Any delay on the critical path delays the entire project.

## Q3.2 / Q4 — Expected Finish Time [8 marks]

The expected finish time is simply the total expected duration of the critical path activities:

| Activity | Expected Time | Running Total |
| --- | --- | --- |
| A | 49.50 | 49.50 |
| + B | 30.83 | 80.33 |
| + D | 77.33 | 157.67 |
| + F | 4.17 | 161.83 |
| + H | 23.50 | 185.33 |

✅ Expected Finish Time = 185.33 days ≈ 185 days

## Q3.3 / Q4 — 95% Confidence Finish Time [4 marks]

Because activity durations are uncertain, the project finish time follows a normal distribution. We use the critical path's variance to calculate how spread out possible finish times are.

💡 The Central Limit Theorem at work When we add up many uncertain durations along the critical path, the total follows a normal (bell-curve) distribution. This lets us use z-scores to answer probability questions.

### Step 1: Sum variances ALONG THE CRITICAL PATH ONLY

| Activity on CP | Variance σ² |
| --- | --- |
| A | 4.694 |
| B | 20.250 |
| D | 16.000 |
| F | 0.694 |
| H | 0.694 |
| Total Variance σ²_cp | 42.333 |
| Standard Deviation σ_cp = √σ² | 6.506 days |

⚠️ Formula T (95% confidence) = Expected Finish + z₀.₉₅ × σ_cp For 95%: z = 1.645 (standard normal table value)

| Component | Value |
| --- | --- |
| Expected Finish (μ) | 185.33 days |
| z₀.₉₅ | 1.645 |
| σ_cp | 6.506 days |
| z × σ | 1.645 × 6.506 = 10.70 days |
| T (95%) | 185.33 + 10.70 = 196.04 days |

✅ 95% Confidence Finish = 196.04 days ≈ 197 days We can be 95% confident the project will finish within 196 days.

## Q3.4 / Q4 — Probability of Finishing 2 Days After Expected [4 marks]

This asks: what is the probability of finishing by Day 187 (i.e., 185 + 2)?

⚠️ Formula z = (Target Date − Expected Finish) ÷ σ_cp Then look up P(Z < z) in the standard normal table

| Step | Calculation |
| --- | --- |
| Target date | 185 + 2 = 187 days |
| z = (Target − μ) ÷ σ | z = (187 − 185.33) ÷ 6.506 |
| z = difference ÷ σ | z = 1.67 ÷ 6.506 = 0.307 |
| P(Z < z) from normal table | P(Z < 0.307) ≈ 62.1% |

✅ Probability of finishing by Day 187 ≈ 62.1% There is approximately a 62.1% chance the project will be done within 2 days of the expected finish time.

# SECTION 5: Gantt Charts & Resource Costing

## Q5 — Understanding the Gantt Chart

A Gantt chart is a visual timeline showing when each activity starts and finishes. Each activity can only start after all its predecessors are complete.

### Activity Schedule (June 2022 Exam — Days)

| Act | Description | Predecessor | Duration | Start Day | End Day |
| --- | --- | --- | --- | --- | --- |
| A | Train project team | None | 10 days | Day 1 | Day 10 |
| B | Project paperwork & systems design | A | 15 days | Day 11 | Day 25 |
| C | Modify purchased package | B | 5 days | Day 26 | Day 30 |
| D | Manual systems flow | B | 20 days | Day 26 | Day 45 |
| E | Modify in-house procedures | B | 15 days | Day 26 | Day 40 |
| F | Test & implement modifications (purchased) | C | 20 days | Day 31 | Day 50 |
| G | Test & implement manual | D | 15 days | Day 46 | Day 60 |
| H | Test & implement in-house procedures | E | 25 days | Day 41 | Day 65 |

💡 How to read the Gantt chart Each month has 20 working days. In the exam Gantt chart, each block = 5 days. So 10 days = 2 blocks. Activity A (10 days) fills 2 blocks in December. Activity B (15 days = 3 blocks) starts immediately after A in January. The critical path is: A → B → H (total = 10 + 15 + 25 = 65 days — the longest parallel sequence).

### Activity Schedule (Practice Paper 2 — Months)

| Act | Description | Duration | Start | End |
| --- | --- | --- | --- | --- |
| A | Train project team | 1 month | December | End December |
| B | Project paperwork & systems design | 2½ months | January | Mid-March |
| C | Modify purchased package | ½ month | Mid-March | End March |
| D | Manual systems flow | 1½ months | Mid-March | End April |
| E | Modify in-house procedures | 1 month | Mid-March | Mid-April |
| F | Test (purchased pkg) | 1½ months | April | Mid-May |
| G | Test (manual) | ¾ month | End April | Mid-May |
| H | Test (in-house procedures) | 1 month | Mid-April | Mid-May |

## Q5 — Resource Cost Calculation

To calculate cost, multiply: Number of Resources × Hours per Day × Working Days × Hourly Rate

⚠️ Key assumptions 20 working days per month. 8 hours per working day. Therefore: 1 month = 160 person-hours.

### June 2022 Exam (durations in days)

| Task | Duration | Resources | Hours | Rate | Cost |
| --- | --- | --- | --- | --- | --- |
| A: Train project team | 10 days | Trainer | 10×8=80hrs | R50/hr | R4,000 |
| B: Project paperwork | 15 days | Project Manager | 15×8=120hrs | R20/hr | R2,400 |
| C: Modify purchased pkg | 5 days | SDS + ADS | 5×8×2=80hrs | R40+R40=R80/hr | R3,200 |
| D: Manual systems flow | 20 days | Project Manager | 20×8=160hrs | R20/hr | R3,200 |
| E: Modify in-house proc. | 15 days | PM + SDS | 15×8×2=240hrs | R20+R40=R60/hr | R9,000 |
| F: Test purchased pkg | 20 days | Tester + SDS | 20×8×2=320hrs | R30+R40=R70/hr | R11,200 |
| G: Test manual | 15 days | Tester | 15×8=120hrs | R30/hr | R3,600 |
| H: Test in-house | 25 days | Tester | 25×8=200hrs | R30/hr | R6,000 |

|  | TOTAL PROJECT COST |
| --- | --- |
|  | R4,000 + R2,400 + R3,200 + R3,200 + R9,000 + R11,200 + R3,600 + R6,000 = R42,600 |

### Practice Paper 2 (durations in months)

| Task | Duration | Resources | Hrs (months×160) | Rate | Cost |
| --- | --- | --- | --- | --- | --- |
| A: Train project team | 1 month | Trainer | 1×160=160hrs | R50/hr | R8,000 |
| B: Project paperwork | 2.5 months | Project Manager | 2.5×160=400hrs | R20/hr | R8,000 |
| C: Modify purchased pkg | 0.5 months | SDS + ADS | 0.5×160×2=160hrs | R40+R40=R80/hr | R6,400 |
| D: Manual systems flow | 1.5 months | Project Manager | 1.5×160=240hrs | R20/hr | R4,800 |
| E: Modify in-house proc. | 1 month | PM + SDS | 1×160×2=320hrs | R20+R40=R60/hr | R9,600 |
| F: Test purchased pkg | 1.5 months | Tester + SDS | 1.5×160×2=480hrs | R30+R40=R70/hr | R16,800 |
| G: Test manual | 0.75 months | Tester | 0.75×160=120hrs | R30/hr | R3,600 |
| H: Test in-house | 1 month | Tester | 1×160=160hrs | R30/hr | R4,800 |

|  | TOTAL PROJECT COST |
| --- | --- |
|  | R8,000 + R8,000 + R6,400 + R4,800 + R9,600 + R16,800 + R3,600 + R4,800 = R62,000 |

💡 How to approach resource cost problems in the exam 1) Convert duration to hours (days × 8 or months × 160). 2) Identify ALL resources assigned to each task. 3) Multiply: hours × rate per resource. 4) If multiple resources share a task, add their costs together. 5) Sum all tasks for the total.

# SECTION 6: Exam Quick Reference Sheet

Everything you need on one page. Use this for last-minute revision.

## All Key Formulas

| Formula | Use when... |
| --- | --- |
| FV = PV × (1 + r)ⁿ | Finding how much money grows to in future |
| PV = FV ÷ (1 + r)ⁿ | Discounting a future cash flow to today's value |
| NPV = Σ PV(inflows) − Initial Investment | Evaluating if a project adds value (NPV > 0 = good) |
| IRR ≈ r₁ + [NPV₁ ÷ (NPV₁ − NPV₂)] × (r₂ − r₁) | Finding the break-even discount rate |
| Payback Period = Investment ÷ Annual Cash Flow | Finding how quickly you recover your money |
| tₑ = (O + 4M + P) ÷ 6 | PERT expected activity duration |
| σ² = [(P − O) ÷ 6]² | PERT variance for an activity |
| σ_cp = √(Σ σ² of CP activities) | Standard deviation of project finish time |
| T_confidence = μ + z × σ_cp | Finding finish time at a given confidence level |
| z = (Target − μ) ÷ σ_cp | Finding z-score for a probability question |
| Slack = LS − ES = LF − EF | Float in a PERT/CPM activity |
| EF = ES + Duration | Forward pass in network diagram |
| LS = LF − Duration | Backward pass in network diagram |
| Cost = Hours × Hourly Rate | Resource cost per task |

## Key Terms in 10 Words or Less

| Term | What it means |
| --- | --- |
| NPV | Sum of all discounted cash flows; positive = invest |
| IRR | The discount rate where NPV = 0 |
| TVM | A rand today is worth more than a rand tomorrow |
| Critical Path | Longest network path; zero slack; controls project end date |
| Slack/Float | How much delay an activity can absorb without delaying the project |
| Baseline (CM) | A formally approved version that can only change via formal request |
| Configuration Item | Any work product managed individually under configuration management |
| Variant (CM) | Concurrent versions for different platforms (e.g., Windows, Linux) |
| Release (CM) | A version made available to users; must pass quality control |
| Promotion (CM) | A version made available to other developers |
| Rationale | The documented WHY behind a design or management decision |
| Risk = Probability × Impact | Quantitative expected cost of a risk occurring |
| Waterfall | Sequential lifecycle; each phase fully complete before next begins |
| USDP | Iterative/incremental lifecycle; 4 phases, 5 workflows, UML-based |
| IEEE 1074 | Standard defining what processes a lifecycle model must include |

## Normal Distribution Z-Score Quick Reference

| Confidence Level | Z-Score | Use case |
| --- | --- | --- |
| 68.3% | z = 1.00 | 1 standard deviation |
| 90% | z = 1.282 | Lower confidence threshold |
| 95% | z = 1.645 (one-tail) | Most common in PERT questions |
| 95% | z = 1.960 (two-tail) | Used for confidence intervals |
| 99% | z = 2.326 (one-tail) | High confidence scenarios |

✅ Final Exam Tip Always show your working step by step — even if your final answer is slightly off, you score method marks. Write the formula first, substitute values second, calculate third. Label every number with its units (days, %, Rands). The examiner rewards clear reasoning.