PFD47XS Professional Development Methods

Activity on Node Networks & Calculations

Examination Answers — 27 March 2024

# Question 1 — CPM Network Analysis

Node key:  top row = ES | Activity | EF  ·  bottom row = LS | Duration | LF  ·  Blue = Critical path (TF = 0)

## 1.1  All Paths & Project Finish Time

A → B → E → G → J  =  4 + 6 + 9 + 6 + 2  =  27 days   ← CRITICAL PATH (longest)

A → B → F           =  4 + 6 + 10          =  20 days

A → C → G → J       =  4 + 5 + 6 + 2       =  17 days

A → D → H → J       =  4 + 8 + 8 + 2       =  22 days

A → D → I            =  4 + 8 + 3           =  15 days

Project Finish Time = 27 days

## 1.2  Critical Path

Critical Path:  A → B → E → G → J  =  27 days  (all activities have Total Float = 0)

## 1.3  Forward Pass — Early Start (ES) and Early Finish (EF)

EF = ES + Duration          ES = max(EF of all predecessors)

| Act. | Dur | Pred. | ES Calculation | ES | EF |
| --- | --- | --- | --- | --- | --- |
| A ★ | 4 | Start | Start of project = 0 | 0 | 4 |
| B ★ | 6 | A | EF(A) = 4 | 4 | 10 |
| C | 5 | A | EF(A) = 4 | 4 | 9 |
| D | 8 | A | EF(A) = 4 | 4 | 12 |
| E ★ | 9 | B | EF(B) = 10 | 10 | 19 |
| F | 10 | B | EF(B) = 10 | 10 | 20 |
| H | 8 | D | EF(D) = 12 | 12 | 20 |
| I | 3 | D | EF(D) = 12 | 12 | 15 |
| G ★ | 6 | C, E | max(EF(C), EF(E)) = max(9, 19) = 19 | 19 | 25 |
| J ★ | 2 | G, H | max(EF(G), EF(H)) = max(25, 20) = 25 | 25 | 27 |

## 1.4  Backward Pass — Late Finish (LF), Late Start (LS) and Total Float (TF)

LS = LF − Duration          LF = min(LS of all successors)          TF = LS − ES

| Act. | Dur | Succ. | LF Calculation | LF | LS | TF |
| --- | --- | --- | --- | --- | --- | --- |
| J ★ | 2 | End | Project end = 27 | 27 | 25 | 0 |
| G ★ | 6 | J | LS(J) = 25 | 25 | 19 | 0 |
| H | 8 | J | LS(J) = 25 | 25 | 17 | 5 |
| F | 10 | End | Terminal node — project end = 27 | 27 | 17 | 7 |
| I | 3 | End | Terminal node — project end = 27 | 27 | 24 | 12 |
| E ★ | 9 | G | LS(G) = 19 | 19 | 10 | 0 |
| C | 5 | G | LS(G) = 19 | 19 | 14 | 10 |
| D | 8 | H, I | min(LS(H), LS(I)) = min(17, 24) = 17 | 17 | 9 | 5 |
| B ★ | 6 | E, F | min(LS(E), LS(F)) = min(10, 17) = 10 | 10 | 4 | 0 |
| A ★ | 4 | B, C, D | min(LS(B), LS(C), LS(D)) = min(4, 14, 9) = 4 | 4 | 0 | 0 |

★ = On the critical path (TF = 0).  Activities with TF > 0 can be delayed by that amount without delaying the project.

## 1.5  Float Formulas

Total Float (TF)       = LS − ES  (or equivalently: LF − EF)

Free Float (FF)        = ES(nearest successor) − EF(this activity)

Independent Float (IF) = ES(nearest successor) − LF(predecessor) − Duration

# Question 2 — PERT Network Analysis

Node key:  top row = ES | Activity | EF  ·  bottom row = LS | Ceiling ED | LF  ·  Blue = Critical path

## 2.2  Expected Durations (Ceiling ED)

ED = (O + 4M + P) ÷ 6          Ceiling ED = round up to next whole number

| Act. | O | M | P | ED = (O + 4M + P) ÷ 6 | Ceiling ED |
| --- | --- | --- | --- | --- | --- |
| A | 4 | 5 | 7 | (4+20+7)/6 = 5.17 | 6 |
| B | 1 | 3 | 6 | (1+12+6)/6 = 3.17 | 4 |
| C | 4 | 5 | 7 | (4+20+7)/6 = 5.17 | 6 |
| D | 3 | 7 | 10 | (3+28+10)/6 = 6.83 | 7 |
| E | 4 | 6 | 9 | (4+24+9)/6 = 6.17 | 7 |
| F | 2 | 3 | 5 | (2+12+5)/6 = 3.17 | 4 |
| G | 1 | 7 | 10 | (1+28+10)/6 = 6.50 | 7 |
| H | 2 | 6 | 8 | (2+24+8)/6 = 5.67 | 6 |

## 2.2b  Forward Pass (using Ceiling EDs)

EF = ES + Ceiling ED          ES = max(EF of all predecessors)

| Act. | Ceil.ED | Pred. | ES Calculation | ES | EF |
| --- | --- | --- | --- | --- | --- |
| A ★ | 6 | — | Start of project = 0 | 0 | 6 |
| B ★ | 4 | A | EF(A) = 6 | 6 | 10 |
| C | 6 | A | EF(A) = 6 | 6 | 12 |
| D ★ | 7 | B | EF(B) = 10 | 10 | 17 |
| E | 7 | B | EF(B) = 10 | 10 | 17 |
| F ★ | 4 | C, D | max(EF(C), EF(D)) = max(12, 17) = 17 | 17 | 21 |
| G | 7 | E | EF(E) = 17 | 17 | 24 |
| H ★ | 6 | E, F | max(EF(E), EF(F)) = max(17, 21) = 21 | 21 | 27 |

## All Paths

A → B → D → F → H  =  6 + 4 + 7 + 4 + 6  =  27 days   ← CRITICAL PATH

A → B → E → H       =  6 + 4 + 7 + 6       =  23 days

A → C → F → H       =  6 + 6 + 4 + 6       =  22 days

A → B → E → G       =  6 + 4 + 7 + 7       =  24 days

Expected Project Finish Time = 27 days

## 2.3  Backward Pass

LS = LF − Ceiling ED          LF = min(LS of all successors)          TF = LS − ES

| Act. | Ceil.ED | Succ. | LF Calculation | LF | LS | TF |
| --- | --- | --- | --- | --- | --- | --- |
| H ★ | 6 | End | Terminal — project end = 27 | 27 | 21 | 0 |
| G | 7 | End | Terminal — project end = 27 | 27 | 20 | 3 |
| F ★ | 4 | H | LS(H) = 21 | 21 | 17 | 0 |
| E | 7 | G, H | min(LS(G), LS(H)) = min(20, 21) = 20 | 20 | 13 | 3 |
| D ★ | 7 | F | LS(F) = 17 | 17 | 10 | 0 |
| C | 6 | F | LS(F) = 17 | 17 | 11 | 5 |
| B ★ | 4 | D, E | min(LS(D), LS(E)) = min(10, 13) = 10 | 10 | 6 | 0 |
| A ★ | 6 | B, C | min(LS(B), LS(C)) = min(6, 11) = 6 | 6 | 0 | 0 |

★ = Critical path  (TF = 0).  Critical Path: A → B → D → F → H = 27 days

## 2.3  Variance & Standard Deviation (Critical Path Activities)

Variance = ((P − O) ÷ 6)²          σ = √(sum of variances on critical path)

| Act. | O | P | (P − O) ÷ 6 | Variance |
| --- | --- | --- | --- | --- |
| A | 4 | 7 | (7-4)/6 = 0.500 | 0.250 |
| B | 1 | 6 | (6-1)/6 = 0.833 | 0.694 |
| D | 3 | 10 | (10-3)/6 = 1.167 | 1.361 |
| F | 2 | 5 | (5-2)/6 = 0.500 | 0.250 |
| H | 2 | 8 | (8-2)/6 = 1.000 | 1.000 |
| Total |  |  | Sum of variances on critical path (A+B+D+F+H) | 3.555 |

Standard Deviation:  σ = √3.555 = 1.886 days

## 2.3  95% Confidence Finish Time

For 95% confidence:   z = 1.645  (from Z-table)

x = z × σ + μ  =  1.645 × 1.886 + 27  =  3.10 + 27  =  30.10 days

→  We have 95% confidence of finishing by 30.10 days

## 2.4  Probability of Finishing 1 Day After Expected Finish

Target date = μ + 1 = 27 + 1 = 28 days

z = (x − μ) ÷ σ  =  (28 − 27) ÷ 1.886  =  0.53

From Z-table:  P(z ≤ 0.53) = 0.7019

→  Probability of finishing within 28 days = 70.19%

— End of Document —