| Student Full Name: | Student Number: |  |
| --- | --- | --- |
| Subject: Professional Methods/Development 4 | Test Date: 19 June 2020 | Duration: 2 hours |

Test 1

Faculty of Informatics & Design

Course:

BTech in Information Technology

| Question | Student Mark | Max. Score |
| --- | --- | --- |
| 1 |  | 20 |
| 2 |  | 20 |
| 3 |  | 20 |
| 4 |  | 20 |
| 5 |  | 20 |
|  |  | 100 |

Subject Coordinator:

Mr T. Makhurane

Lecturers / Examiners:

Mr T. Makhurane

Moderator:

Internal:

Special instructions:

Answer all the questions that are written in bold. Hand-in question paper at the end of examination

Requirements:

Students should not leave within the first hour even if they have completed.

Hand-in question paper together with the answer book at the end of examination

%

| Question 1 |  |  |
| --- | --- | --- |
|  | Activity; Duration (days); Predecessor(s). A; 2; -. B; 2; A. C; 4; A. D; 1; B. E; 3; C,D. F; 2; C,D. G; 4; E. H; 5; F,G. |  |
| 1.1 | Draw an Activity-on-Node Network Diagram for the following table | [6] |
| 1.2 | Determine duration of the project (in days). As well as the Critical Path (You can write your response on the same diagram as for question 1.1). | [6] |
| 1.3 | Determine floats for any two non-critical activities. | [4] |
| 1.4 | Explain the significance of the critical path to a manager scheduling project activities. | [4] |
| Question 2 |  |  |
|  | Given the following table, with all durations in days. Activity; Optimistic (A); Most Likely (M); Pessimistic; Predecessors. A; 1; 2; 3; -. B; 2; 5; 7; A. C; 6; 7; 9; A. D; 4; 7; 10; A. E; 1; 3; 6; B. F; 7; 8; 11; B. G; 4; 5; 6; C, F. H; 4; 7; 10; D. I; 4; 9; 12; H. J; 9; 12; 13; G, I. K; 3; 6; 10; E, J. |  |
| 2.1 | Draw an Activity on Node network corresponding to the table above. | [6] |
| 2.2 | Determine the critical path, and figures for μ (mu) and s. | [8] |
| 2.3 | Determine the time by which there is a 0.99 probability (or 99% chance) of having finished the project. | [6] |
| Question 3 |  |  |
| 3.1 | Define Project Management, and explain the characteristics of projects. | [3] |
| 3.2 | What is the fundamental trade-off in project management? | [3] |
| 3.3 | List and discuss the activities included in Henri Fayol’s concept of management. Explain whether or not these concepts are applicable in the case of management processes for a software development project. | [7] |
| 3.4 | Describe Mintzberg’s definitions of managerial roles. In addition, explain how these are applicable to project managers. | [7] |
| Question 4 |  |  |
|  | Assumptions: - A Five Day Working Week (Monday to Friday), - Work for 8 Hours per Day. - No overtime and No Cost per use Given a project described as follows (Precedence table + Resource sheet): Activity; Duration; Predecessors; Resources. 1; Start; 0. 2; System Design; 12; 1. 3; Define work process; 3; 1; Project Manager. 4; Identify required information and resources; 5; 3; Project Manager. 5; Design software system to support work process; 3; 4. 6; Basic software; 2; 4; Business Analyst, Developer, User. 7; Data access required; 1; 6; Business Analyst, Developer, User. 8; Vendor software required; 1; 7; Business Analyst, Developer, User. 9; Identify required hardware components; 3; 8,5; Business Analyst. 10; System Design Milestone; 0; 9. 11; Hardware and Software Acquisition; 21; 2. 12; Obtain quotations from hardware vendors; 2; 10; Buyer. 13; Obtain quotations from software vendors; 19. 14; Identify potential software products; 4; 10,12. 15; Obtain test copies for user to examine; 10; 14. 16; User comparison and approval; 5; 15. 17; Hardware and Software Acquisition Milestone; 0; 12,16,13. 18; Installation; 11; 11. 19; Order components; 3; 17. 20; Test components for technical functionality; 2; 19. 21; Assemble system; 1; 20. 22; Train user on software; 2; 21. 23; User Test of system; 3; 22. 24; Installation Milestone; 0; 23,18. Resource; Cost/Hour. Project Manager; R 150.00/h. User; R 200.00/h. Business Analyst; R 250.00/h. Developer; R 100.00/h. Buyer; R 170.00/h. |  |
| 4.1 | How much money is earned by the Project Manager alone during the five days of the project? | [6] |
| 4.2 | How much money is required to run this project for its first 6 days? | [6] |
| 4.3 | How much money us required for the first 14 days of the project? | [8] |
| Question 5 |  |  |
|  | Given the following cash flow situation Year; Cash Flow. 0; R -200000.00. 1; R 40000.00. 2; R 40000.00. 3; R 40000.00. 4; R 40000.00. 5; R 40000.00. |  |
| 5.1 | What is the payback period associated with this project? | [2] |
| 5.2 | Given an applicable rate of interest of 12%, what is the Net Present Value (NPV) associated with this project? | [8] |
| 5.3 | With suitable working, provide an estimate of the internal rate of return (IRR). | [10] |

Standardised Normal Distribution (z-table) (Full Table)

| z | 0.00 | 0.01 | 0.02 | 0.03 | 0.04 | 0.05 | 0.06 | 0.07 | 0.08 | 0.09 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 0.0 | 0.5000 | 0.5040 | 0.5080 | 0.5120 | 0.5160 | 0.5199 | 0.5239 | 0.5279 | 0.5319 | 0.5359 |
| 0.1 | 0.5398 | 0.5438 | 0.5478 | 0.5517 | 0.5557 | 0.5596 | 0.5636 | 0.5675 | 0.5714 | 0.5753 |
| 0.2 | 0.5793 | 0.5832 | 0.5871 | 0.5910 | 0.5948 | 0.5987 | 0.6026 | 0.6064 | 0.6103 | 0.6141 |
| 0.3 | 0.6179 | 0.6217 | 0.6255 | 0.6293 | 0.6331 | 0.6368 | 0.6406 | 0.6443 | 0.6480 | 0.6517 |
| 0.4 | 0.6554 | 0.6591 | 0.6628 | 0.6664 | 0.6700 | 0.6736 | 0.6772 | 0.6808 | 0.6844 | 0.6879 |
| 0.5 | 0.6915 | 0.6950 | 0.6985 | 0.7019 | 0.7054 | 0.7088 | 0.7123 | 0.7157 | 0.7190 | 0.7224 |
| 0.6 | 0.7257 | 0.7291 | 0.7324 | 0.7357 | 0.7389 | 0.7422 | 0.7454 | 0.7486 | 0.7517 | 0.7549 |
| 0.7 | 0.7580 | 0.7611 | 0.7642 | 0.7673 | 0.7704 | 0.7734 | 0.7764 | 0.7794 | 0.7823 | 0.7852 |
| 0.8 | 0.7881 | 0.7910 | 0.7939 | 0.7967 | 0.7995 | 0.8023 | 0.8051 | 0.8078 | 0.8106 | 0.8133 |
| 0.9 | 0.8159 | 0.8186 | 0.8212 | 0.8238 | 0.8264 | 0.8289 | 0.8315 | 0.8340 | 0.8365 | 0.8389 |
| 1.0 | 0.8413 | 0.8438 | 0.8461 | 0.8485 | 0.8508 | 0.8531 | 0.8554 | 0.8577 | 0.8599 | 0.8621 |
| 1.1 | 0.8643 | 0.8665 | 0.8686 | 0.8708 | 0.8729 | 0.8749 | 0.8770 | 0.8790 | 0.8810 | 0.8830 |
| 1.2 | 0.8849 | 0.8869 | 0.8888 | 0.8907 | 0.8925 | 0.8944 | 0.8962 | 0.8980 | 0.8997 | 0.9015 |
| 1.3 | 0.9032 | 0.9049 | 0.9066 | 0.9082 | 0.9099 | 0.9115 | 0.9131 | 0.9147 | 0.9162 | 0.9177 |
| 1.4 | 0.9192 | 0.9207 | 0.9222 | 0.9236 | 0.9251 | 0.9265 | 0.9279 | 0.9292 | 0.9306 | 0.9319 |
| 1.5 | 0.9332 | 0.9345 | 0.9357 | 0.9370 | 0.9382 | 0.9394 | 0.9406 | 0.9418 | 0.9429 | 0.9441 |
| 1.6 | 0.9452 | 0.9463 | 0.9474 | 0.9484 | 0.9495 | 0.9505 | 0.9515 | 0.9525 | 0.9535 | 0.9545 |
| 1.7 | 0.9554 | 0.9564 | 0.9573 | 0.9582 | 0.9591 | 0.9599 | 0.9608 | 0.9616 | 0.9625 | 0.9633 |
| 1.8 | 0.9641 | 0.9649 | 0.9656 | 0.9664 | 0.9671 | 0.9678 | 0.9686 | 0.9693 | 0.9699 | 0.9706 |
| 1.9 | 0.9713 | 0.9719 | 0.9726 | 0.9732 | 0.9738 | 0.9744 | 0.9750 | 0.9756 | 0.9761 | 0.9767 |
| 2.0 | 0.9772 | 0.9778 | 0.9783 | 0.9788 | 0.9793 | 0.9798 | 0.9803 | 0.9808 | 0.9812 | 0.9817 |
| 2.1 | 0.9821 | 0.9826 | 0.9830 | 0.9834 | 0.9838 | 0.9842 | 0.9846 | 0.9850 | 0.9854 | 0.9857 |
| 2.2 | 0.9861 | 0.9864 | 0.9868 | 0.9871 | 0.9875 | 0.9878 | 0.9881 | 0.9884 | 0.9887 | 0.9890 |
| 2.3 | 0.9893 | 0.9896 | 0.9898 | 0.9901 | 0.9904 | 0.9906 | 0.9909 | 0.9911 | 0.9913 | 0.9916 |
| 2.4 | 0.9918 | 0.9920 | 0.9922 | 0.9925 | 0.9927 | 0.9929 | 0.9931 | 0.9932 | 0.9934 | 0.9936 |
| 2.5 | 0.9938 | 0.9940 | 0.9941 | 0.9943 | 0.9945 | 0.9946 | 0.9948 | 0.9949 | 0.9951 | 0.9952 |
| 2.6 | 0.9953 | 0.9955 | 0.9956 | 0.9957 | 0.9959 | 0.9960 | 0.9961 | 0.9962 | 0.9963 | 0.9964 |
| 2.7 | 0.9965 | 0.9966 | 0.9967 | 0.9968 | 0.9969 | 0.9970 | 0.9971 | 0.9972 | 0.9973 | 0.9974 |
| 2.8 | 0.9974 | 0.9975 | 0.9976 | 0.9977 | 0.9977 | 0.9978 | 0.9979 | 0.9979 | 0.9980 | 0.9981 |
| 2.9 | 0.9981 | 0.9982 | 0.9982 | 0.9983 | 0.9984 | 0.9984 | 0.9985 | 0.9985 | 0.9986 | 0.9986 |
| 3.0 | 0.9987 | 0.9987 | 0.9987 | 0.9988 | 0.9988 | 0.9989 | 0.9989 | 0.9989 | 0.9990 | 0.9990 |
| 3.1 | 0.9990 | 0.9991 | 0.9991 | 0.9991 | 0.9992 | 0.9992 | 0.9992 | 0.9992 | 0.9993 | 0.9993 |
| 3.2 | 0.9993 | 0.9993 | 0.9994 | 0.9994 | 0.9994 | 0.9994 | 0.9994 | 0.9995 | 0.9995 | 0.9995 |
| 3.3 | 0.9995 | 0.9995 | 0.9995 | 0.9996 | 0.9996 | 0.9996 | 0.9996 | 0.9996 | 0.9996 | 0.9997 |
| 3.4 | 0.9997 | 0.9997 | 0.9997 | 0.9997 | 0.9997 | 0.9997 | 0.9997 | 0.9997 | 0.9997 | 0.9998 |
| 3.5 | 0.9998 | 0.9998 | 0.9998 | 0.9998 | 0.9998 | 0.9998 | 0.9998 | 0.9998 | 0.9998 | 0.9998 |
| 3.6 | 0.9998 | 0.9998 | 0.9999 | 0.9999 | 0.9999 | 0.9999 | 0.9999 | 0.9999 | 0.9999 | 0.9999 |

Formulas

| Free Float | FFi,j=Ej-Ei-Dij |
| --- | --- |
| Independent Float | IFi,j=0 Ej-Li-Dij IF(i,j)≥0 |
| Total Float | TFi,j=Lj-Ei-Dij |
| Expected Duration | ED=A+4M+B6 |
| Variance | B-A62 |
|  | z=x-μs |
|  | x=zs+μ |