| Figure 1 Question 1 |  | [20] |
| --- | --- | --- |
| 1.1 | 1 2 3 4 5 6 7 8 9 A 7 B 8 8 E H 5 C 2 H 6 D 9 G 13 I 7 8 JI K L N M 5 4 3 13 F 12 For the diagram above, please calculate the early start times and the late start times. | [10] |
| 1.2 | For any two activities, which are not on the critical path, calculate the free float, total float and independent float (I.e., six calculations). | [10] |
| Question 3 |  | [20] |
| 3.1 | Activity; Immediate Predecessors; Optimistic; Most Likely; Pessimistic. A; -; 42; 50; 55. B; A; 15; 32; 42. C; A; 41; 43; 47. D; B; 64; 78; 88. E; B; 40; 45; 58. F; C, D; 2; 4; 7. G; E; 12; 17; 23. H; E, F; 20; 24; 25. Draw the network. | [4] |
| 3.2 | Determine the expected finish time. | [8] |
| 3.3 | Calculate the time by which we have 95% confidence of finishing. | [4] |
| 3.4 | Calculate the probability of finishing 2 days after the expected finish time | [4] |

| Question 5 |  | [20] |
| --- | --- | --- |
| 5.2 | Given the information provided here and the Gantt chart layout provided below, construct a Gantt chart, by filling in the appropriate blocks on the Gantt chart with the character X. | [8] |

| ### Activity Letter | Activity Description | ### Predecessor | Duration (months) |
| --- | --- | --- | --- |
| A | Train project team | None | 1 |
| B | Project paperwork and systems design | A | 2 ½ |
| C | Modify purchased package | B | ½ |
| D | Manual systems flow | B | 1 ½ |
| E | Modify in-house procedures | B | 1 |
| F | Test and implement modifications to purchased package | C | 1 ½ |
| G | Test and implement manual | D | ¾ |
| H | Test and implement modifications to in-house procedures | E | 1 |

GANTT CHART EXERCISE

| Description |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A. Train Project Team |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| B. Project Management Paperwork |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| C. Modify Purchased Package |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D. Manual Systems Flow |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E. Modify In-House Procedures |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| F. Test and Implement Modifications to Purchased Package |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| G. Test and Implement Manual Systems Flow |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| H. Test and Implement Modifications to In-House Procedures |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

- Given this resource sheet

| Resource | Cost/Hour |
| --- | --- |
| Trainer | R50.00 |
| Application Domain Specialist | R40.00 |
| Solution Domain Specialist | R40.00 |
| Project Manager | R20.00 |
| Tester | R30.00 |

And this task assignment List

| Task | Resources Assigned |
| --- | --- |
| - Train Project Team | Trainer |
| - Project Management Paperwork | Project Manager |
| - Modify Purchased Package | Solution Domain Specialist, Application Domain Specialist |
| - Manual systems Flow | Project Manager |
| - Modify In-House Procedures | Project Manager, Solution Domain Specialist |
| - Test and Implement Modifications to Purchased Package | Tester, Solution Domain Specialist |
| - Test and Implement Manual Systems Flow | Tester |
| - Test and Implement Modifications to In-House Procedures | Tester |

Assume the following:

- There are 20 Working days per month.

- There are 8 hours per working day.

Assess the total amount of money needed to run the project.					[12]