Software Estimation Exercise

- Compare the estimates of effort and duration for the three projects obtained using the function point approach.

| Average of past projects: | Effort | R(000) | pp. Doc. | Errors |
| --- | --- | --- | --- | --- |
| LOC 14528 FP 500 | 15 months | 546 | 304 | 63 |

Project 1: Install a data mining package with links

| F1 | Backup and Recovery | Average | (3) |
| --- | --- | --- | --- |
| F2 | Data Communications | Significant | (4) |
| F3 | Distributed Processing | Incidental | (1) |
| F4 | Performance Critical? | Average | (3) |
| F5 | Run on existing, heavily used environment? | No effect | (0) |
| F6 | Online data entry? | Incidental | (1) |
| F7 | Online data entry on multiple screens? | Average | (3) |
| F8 | Master files updated online? | Incidental | (1) |
| F9 | Inputs, outputs, files complex? | Incidental | (1) |
| F10 | Internal processing complex? | Essential | (5) |
| F11 | Code reusable? | Significant | (4) |
| F12 | Conversion and Installation? | Significant | (4) |
| F13 | Multiple installations across organizations? | No influence | (0) |
| F14 | Facilitate change and user ease of use? | Average | (3) |
|  |  | TOTAL | 33 |

12 user inputs				classified as complex

3 user inputs				classified as average

7 user inputs				classified as simple

6 user outputs				classified as simple

8 user outputs		classified as simple  I believe it was a mistake, I will assume as it is average

2 possible user inquiries			classified as complex

2 files accessed				classified as complex

0 external interfaces

|  | Complexity Weighting |  |  |  |
| --- | --- | --- | --- | --- |
| Measurement parameter | Low | Average | High | Product |
| Number of user inputs | x 3 + | x 4 + | x 6 + = |  |
| Number of user outputs | x 4 + | x 5 + | ___x 7 + = |  |
| Number of user inquiries | _____ x 3 + | _____ x 4 + | x 6 + = |  |
| Number of files | ____ x 7 + | ___x 10 + | x 15 + = |  |
| Number of external interfaces | _____ x 5 + | _____ x 7 + | ___ x 10 + = |  |
|  |  |  | Count Total |  |

Project 2: Develop a report generator for a monthly management report

| F1 | Backup and Recovery | Significant | (4) |
| --- | --- | --- | --- |
| F2 | Data Communications | Significant | (4) |
| F3 | Distributed Processing | Significant | (4) |
| F4 | Performance Critical? | Essential | (5) |
| F5 | Run on existing, heavily used environment? | Average | (3) |
| F6 | Online data entry? | Incidental | (1) |
| F7 | Online data entry on multiple screens? | Incidental | (1) |
| F8 | Master files updated online? | Moderate | (2) |
| F9 | Inputs, outputs, files complex? | Incidental | (1) |
| F10 | Internal processing complex? | Moderate | (2) |
| F11 | Code reusable? | Average | (3) |
| F12 | Conversion and Installation? | Significant | (4) |
| F13 | Multiple installations across organizations? | Significant | (4) |
| F14 | Facilitate change and user ease of use? | Significant | (4) |
|  |  | TOTAL | 42 |

22 user inputs				classified as simple

8 user inputs				classified as average

1 user input 				classified as complex

1 user outputs				classified as simple

0 possible user inquiries

16 files accessed			classified as complex

4 external interfaces			classified as complex

|  | Complexity Weighting |  |  |  |
| --- | --- | --- | --- | --- |
| Measurement parameter | Low | Average | High | Product |
| Number of user inputs | x 3 + | x 4 + | x 6 + = |  |
| Number of user outputs | x 4 + | __ x 5 + | ___x 7 + = |  |
| Number of user inquiries | _____ x 3 + | _____ x 4 + | __ x 6 + = |  |
| Number of files | ____ x 7 + | ___x 10 + | x 15 + = |  |
| Number of external interfaces | _____ x 5 + | _____ x 7 + | x 10 + = |  |
|  |  |  | Count Total |  |

Project 3: Develop an online system to update customer records

| F1 | Backup and Recovery | Average | (3) |
| --- | --- | --- | --- |
| F2 | Data Communications | Essential | (5) |
| F3 | Distributed Processing | No effect | (0) |
| F4 | Performance Critical? | Average | (3) |
| F5 | Run on existing, heavily used environment? | Average | (3) |
| F6 | Online data entry? | Essential | (5) |
| F7 | Online data entry on multiple screens? | Essential | (5) |
| F8 | Master files updated online? | Essential | (5) |
| F9 | Inputs, outputs, files complex? | Incidental | (1) |
| F10 | Internal processing complex? | Moderate | (2) |
| F11 | Code reusable? | Average | (3) |
| F12 | Conversion and Installation? | Moderate | (2) |
| F13 | Multiple installations across organizations? | No effect | (0) |
| F14 | Facilitate change and user ease of use? | Significant | (4) |
|  |  | TOTAL | 41 |

36 user inputs				classified as average

5 user outputs				classified as simple

48 possible user inquiries		classified as average

28 files accessed			classified as average

6 external interfaces			classified as complex using as average

3 external interfaces			classified as complex

|  | Complexity Weighting |  |  |  |
| --- | --- | --- | --- | --- |
| Measurement parameter | Low | Average | High | Product |
| Number of user inputs | __x 3 + | x 4 + | __ x 6 + = |  |
| Number of user outputs | x 4 + | __ x 5 + | ___x 7 + = |  |
| Number of user inquiries | _____ x 3 + | x 4 + | __ x 6 + = |  |
| Number of files | ____ x 7 + | x 10 + | __x 15 + = |  |
| Number of external interfaces | _____ x 5 + | x 7 + | x 10 + = |  |
|  |  |  | Count Total |  |

- Using the Basic COCOMO model. Estimate the expected number of person-months of work and the project duration for an organic project involving 2600 lines of code.

- Using the Intermediate COCOMO model, estimate the expected number of person-months of work and the project duration for an Semi-detached project involving 8000 lines of code. Assume the required reliability is very high, analyst capability is low, programmer experience is high and reliability is high.

- The Intermediate COCOMO model, estimate the expected number of person-months of work and the project duration for an Embedded project involving 17000 lines of code.

Basic COCOMO Table

| Software project | a | b | c | d |
| --- | --- | --- | --- | --- |
| Organic | 2.4 | 1.05 | 2.5 | 0.38 |
| Semidetached | 3.0 | 1.12 | 2.5 | 0.35 |
| Embedded | 3.6 | 1.20 | 2.5 | 0.32 |

Intermediate COCOMO Table

| Software project | a | b | c | d |
| --- | --- | --- | --- | --- |
| Organic | 3.2 | 1.05 | 2.5 | 0.38 |
| Semidetached | 3.0 | 1.12 | 2.5 | 0.35 |
| Embedded | 2.8 | 1.20 | 2.5 | 0.32 |