PFD473S

Professional Development – Methods 4

STUDY NOTES

Software Estimation (SO12) • Quality (SO13)

Cape Peninsula University of Technology

Advanced Diploma in ICT: Applications Development (ADICTA)

2026

# Overview

These notes cover two subject outcomes from the PFD473S subject guide: SO12 Software Estimation (Lines-of-Code, Function Point Analysis, and the COCOMO '81 model) and SO13 Quality (quality management, ISO 9000/9001, the Capability Maturity Model, quality reviews, and project/quality audits). Worked examples follow the numbers used in the lecture slides and in-class exercises so you can check your own workings against them.

Relevant subject outcomes (PFD473S subject guide) • SO12 — Software Estimation: purpose and value; Lines of Code techniques (COCOMO '81); Function Point techniques (Albrecht's method); contemporary methods • SO13 — Quality: ISO; Capability Maturity Model; Project Audits — when, why, and by whom; Testing

# Part A — Software Estimation

Software estimation predicts the effort (person-months), cost, schedule (duration), and other resources (documentation pages, expected defects, staff) needed to build a piece of software, BEFORE it is built. Good estimates are essential for planning, budgeting, and setting realistic client expectations.

“The Mythical Person-Month” — a classic warning (Fred Brooks) that effort and schedule are not simply interchangeable: adding more people to a late software project often makes it later, because of communication overhead.

## A.1 Why estimation is hard

- Simple methods are based on Source Lines of Code (LOC), often expressed as KLOC (thousand lines of code).

- LOC is becoming less meaningful as productivity tools and higher-level languages reduce the code needed for the same functionality.

- Despite known flaws, no significantly better universally-adopted method has replaced LOC-based and function-based approaches.

## A.2 Method 1 — Lines of Code (LOC) estimation

Basis: the time required to develop code is treated as a function of its size. You gather historical data from past projects (effort, cost, documentation, errors, defects, staff) and calculate an average rate 'per line of code'. That rate is then applied to a new project's estimated LOC.

### Worked example (from the lecture slides)

For a new project estimated at 10 000 LOC, using historical multipliers:

| Measure | Multiplier × LOC (in thousands) | Result |
| --- | --- | --- |
| Effort | 1.606 × 10 | 16 person-months |
| Budget | 15.673 × 10 | R157 000 |
| Documentation | 58.122 × 10 | 581 pages |
| Errors | 9.784 × 10 | 98 errors |
| Defects | 2.531 × 10 | 25 defects |
| People | 0.195 × 10 | 2 people |

The LOC method is rough, but simple to apply once you have historical multipliers for your organisation or technology.

## A.3 Method 2 — Function Point Analysis (FPA)

Albrecht's Function Point method estimates size independently of the technology/language used, based on what the system DOES from the user's point of view. It counts five types of components:

- User inputs (e.g. data entry screens)

- User outputs (e.g. reports)

- User inquiries (e.g. searches)

- Files (logical data groups maintained by the system)

- External interfaces (connections to other systems)

### Step 1 — Complexity weighting table

Each component is counted at Low / Average / High complexity and multiplied by a fixed weight:

| Component | Low weight | Average weight | High weight |
| --- | --- | --- | --- |
| User inputs | ×3 | ×4 | ×6 |
| User outputs | ×4 | ×5 | ×7 |
| User inquiries | ×3 | ×4 | ×6 |
| Files | ×7 | ×10 | ×15 |
| External interfaces | ×5 | ×7 | ×10 |

Worked example from the slides — count × weight, summed per row, then all rows summed for the Unadjusted Function Point (UFP) count:

| Component | Count | Complexity | Weight | Subtotal |
| --- | --- | --- | --- | --- |
| User inputs | 6 / 5 / 7 | Low/Avg/High | 3/4/6 | 18+20+42 = 80 |
| User outputs | — / 5 / — | Average only | 5 | 25 |
| User inquiries | — / 6 / — | Average only | 4 | 24 |
| Files | 8 / — / — | Low only | 7 | 56 |
| External interfaces | — / — / 7 | High only | 10 | 70 |

UFP total = 80 + 25 + 24 + 56 + 70 = 255 (unadjusted)

### Step 2 — Technical Complexity Factor (14 General System Characteristics)

14 factors (F1–F14) are each rated 0–5 (0 = no effect, 5 = essential effect), based on how much that characteristic affects the system:

| Factor | Question | Example rating |
| --- | --- | --- |
| F1 | Reliable backup and recovery required? | 0 |
| F2 | Data communications required? | 3 |
| F3 | Distributed processing functions? | 0 |
| F4 | Performance critical? | 5 |
| F5 | Runs in existing, heavily used environment? | 0 |
| F6 | Online data entry required? | 0 |
| F7 | Online entry across multiple screens/operations? | 0 |
| F8 | Master files updated online? | 5 |
| F9 | Inputs/outputs/files/inquiries complex? | 4 |
| F10 | Internal processing complex? | 5 |
| F11 | Code designed to be reusable? | 0 |
| F12 | Conversion and installation included in design? | 0 |
| F13 | Designed for multiple installations in different orgs? | 0 |
| F14 | Designed to facilitate change / ease of use? | 0 |

Total Degree of Influence (TDI) in the example above = 22.

Function Points (FP) = UFP × (0.65 + 0.01 × TDI)

This formula adjusts the raw unadjusted count by ±35% depending on how technically demanding the 14 characteristics make the system.

### Step 3 — Using FP to estimate effort, cost, etc.

Once you have FP, apply the same 'rate per unit' idea as with LOC, using historical averages per function point:

| Historical averages (example) | Effort | Budget | Documentation | Errors |
| --- | --- | --- | --- | --- |
| 12 500 LOC / 600 FP project | 12 months | R521 000 | 300 pages | 45 errors |

Divide each average by 600 to get a 'per function point' rate, then multiply by your new project's FP count to get its estimate.

Criticism: FP has been criticised for questionable weightings, inconsistent counting rules between analysts, and under-weighting very large systems — but many practitioners still consider it more useful than raw LOC, since it does not depend on the programming language chosen.

## A.4 Method 3 — COCOMO '81 (Constructive Cost Model)

Developed by Barry Boehm (1981). Now considered a somewhat dated model, but still foundational and commonly examined. Basic COCOMO estimates effort purely from estimated program size (KLOC); Intermediate COCOMO refines this using 15 'cost drivers' covering product, hardware, personnel, and project attributes.

### Step 1 — Classify the project mode

| Project mode | a | b | c | d | Description |
| --- | --- | --- | --- | --- | --- |
| Organic | 2.4 | 1.05 | 2.5 | 0.38 | Small, standalone applications (e.g. non-web word processors) |
| Semi-detached | 3.0 | 1.12 | 2.5 | 0.35 | Intermediate size/complexity, mixed-experience team |
| Embedded | 3.6 | 1.20 | 2.5 | 0.32 | Tightly coupled to complex hardware/software systems |

### Step 2 — Basic COCOMO formulas

Effort (person-months)  E = a × (KLOC)^b

Development time (months)  D = c × (E)^d

Where KLOC = estimated size in thousands of lines of code.

### Step 3 — Intermediate COCOMO: applying cost drivers

Intermediate COCOMO multiplies the Basic effort by an Effort Adjustment Factor (EAF) — the product of up to 15 cost driver ratings, each rated from Very Low to Extra High:

| Category | Cost drivers |
| --- | --- |
| Product attributes | RELY (reliability), DATA (database size), CPLX (complexity) |
| Hardware attributes | TIME (execution time constraint), STOR (storage constraint), VIRT (platform volatility), TURN (turnaround time) |
| Personnel attributes | ACAP (analyst capability), AEXP (application experience), PCAP (programmer capability), VEXP (platform experience), LEXP (language experience) |
| Project attributes | MODP (modern practices), TOOL (software tools used), SCED (required schedule compression) |

Adjusted Effort = Basic Effort × EAF   (EAF = product of the chosen driver ratings)

Example driver ratings (from the COCOMO cost-driver table): a 'High' Analyst Capability (ACAP) rating multiplies effort by 0.86 (skilled analysts REDUCE effort), while a 'High' Required Reliability (RELY) multiplies effort by 1.15 (higher reliability INCREASES effort).

### Worked example — organic project, 12 000 LOC, highly capable developers, very large database

This mirrors the scenario given in the lecture slides. You would:

- Compute Basic Effort using the Organic constants: E = 2.4 × (12)^1.05

- Look up cost driver ratings: Analyst/Programmer Capability = Very High (lowers EAF); Database size = Very High (raises EAF)

- Multiply Basic Effort by the combined EAF to get Adjusted Effort

- Compute Development Time: D = 2.5 × (Adjusted Effort)^0.38

### In-class exercise reference (from your Software Estimation exercises)

Your subject's in-class exercise sheet gives two further worked scenarios to practise on:

- Exercise 3 — Organic project, 2 600 LOC. Cost drivers given: RELY Nominal (1.00), DATA Nominal (1.00), ACAP High (0.85), PCAP High (0.88), AEXP Low (1.22), LEXP Low (1.19).

- Exercise 4 — Semi-detached project, 8 000 LOC. Cost drivers given: RELY High (1.15), CPLX Nominal (1.00), DATA High (1.10), ACAP High (0.85), PCAP High (0.88), AEXP Low (1.22), LEXP High (0.91), TOOL High (0.90).

For each: compute Basic Effort with the mode's a/b constants, multiply by the product of all given driver ratings to get Adjusted Effort, then apply the mode's c/d constants to that Adjusted Effort to get Development Duration.

### Basic vs Intermediate COCOMO

| Feature | Basic COCOMO | Intermediate COCOMO |
| --- | --- | --- |
| Inputs | KLOC only | KLOC + up to 15 cost drivers |
| Accuracy | Rough, quick order-of-magnitude estimate | More refined, reflects team/product/project realities |
| Use case | Very early, high-level estimate | Once more project detail is known |

Boehm's duration formula is independent of team size — it depends only on job size, and assumes an appropriate number of people are available throughout. COCOMO has been tested extensively and is widely recognised, but requires practice to apply well; best used alongside another estimation method and professional judgement.

## A.5 Putting it together — a practical estimation workflow

Suggested early-project estimation sequence • Use Function Point Analysis to estimate the system's size (independent of language). • Convert FP to an equivalent LOC estimate (or use historical FP-based multipliers directly for effort/cost/etc.). • Apply Boehm's COCOMO formulas to estimate labour (person-months) required. • Use the effort estimate and COCOMO's duration formula to estimate project duration.

## Video & reading resources — Software Estimation

- COCOMO Model Explained with Math Solution — Effort, Time & Cost Estimation: https://www.youtube.com/watch?v=ewA_Ufr4FBo

- COCOMO Model in Software Engineering | Software Estimation (Gate Smashers): https://www.youtube.com/watch?v=r2qkxbCSsvE

- Basic & Intermediate COCOMO with Numerical (Gate Smashers): https://www.youtube.com/watch?v=lr0vA_p6T7Q

- Project Estimation | COCOMO Model — Guide with LOC Numerical Example: https://www.youtube.com/watch?v=mYjzbpEUXDk

- Function Point Analysis (FPA) with real-life examples (Gate Smashers): https://www.youtube.com/watch?v=7xBcVtjmGwM

- Function Point — Step by Step Guide with Numerical Examples: https://www.youtube.com/watch?v=CeKP0rUIotc

- GeeksforGeeks — Function Point (FP) Analysis reference notes: https://www.geeksforgeeks.org/software-engineering/software-engineering-functional-point-fp-analysis/

# Part B — Quality

## B.1 What is quality?

Quality is the totality of features and characteristics of a product or service that bear on its ability to satisfy stated or implied needs — i.e. the product meets its specification. A software product should deliver required functionality (functional requirements) together with required quality attributes (non-functional requirements).

Quality is especially hard for software because customer quality requirements (efficiency, reliability) often conflict with developer quality requirements (maintainability, reusability); specifications are often incomplete or inconsistent; and quality attributes conflict with each other and increase cost, requiring trade-offs.

## B.2 Quality management activities

| Activity | Description |
| --- | --- |
| Quality planning | Select applicable procedures/standards for the project and adapt as required |
| Quality assurance | Establish organisational procedures and standards for quality |
| Quality control | Ensure procedures and standards are actually followed by the development team |

Quality management should be kept separate from project management to preserve independence of judgement.

## B.3 Quality attributes

Beyond meeting functional requirements, quality software needs attributes such as:

- Efficiency — not wasteful of memory, CPU, disk, response time

- Usability — easy to use by its intended users

- Dependability — reliability, availability, security, safety

- Maintainability — able to evolve as needs change (maintenance often costs more than initial development)

Other attributes: resilience, robustness, understandability, testability, adaptability, modularity, simplicity, portability, reusability, learnability.

### Aspects of dependability

| Aspect | Meaning |
| --- | --- |
| Reliability | Probability of operating without failure, over time, in a given environment |
| Availability | Probability the system is operational and able to deliver a service when requested |
| Safety | Can the system operate without danger of injury, death, or environmental damage (critical for embedded systems) |
| Security | Ability to protect itself from accidental or deliberate attack |

For critical systems, dependability is usually the most important property:

- Safety-critical — failure may cause injury/death/environment damage, e.g. an insulin delivery system

- Mission-critical — failure may cause a goal-directed activity to fail, e.g. a spacecraft navigation system

- Business-critical — failure may cause the business itself to fail, e.g. a bank's customer account system

## B.4 Software metrics

A software metric is any measurement relating to a software system, process, or its documentation — e.g. lines of code, the Fog index, person-days needed. Metrics quantify software and its process, and may predict product attributes or control the process.

### Product quality metrics

- Mean Time To Failure (MTTF) — time between failures

- Defect density — defects relative to software size (e.g. per KLOC or function point)

- Customer satisfaction — usually measured via a five-point scale (very satisfied → very dissatisfied)

- Customer problems — all issues customers encounter, not just confirmed defects (includes usability issues, unclear documentation)

### Process vs people quality

A good process is usually required for a good product. For manufactured goods, process is the dominant quality determinant. For design-based work like software, other factors matter too — especially developer capability.

| Project size | Main quality determinant |
| --- | --- |
| Large projects, 'average' capability teams | The development PROCESS determines product quality |
| Small projects | The developers' CAPABILITIES are the main determinant |
| All projects | An unrealistic schedule will degrade product quality |

## B.5 Standards and the ISO approach

Standards are key to effective quality management. They can be international, national, organisational, or project-specific.

- Product standards — define characteristics all components should exhibit, e.g. a common coding style

- Process standards — define how the software process itself should be carried out

Benefits of standards: encapsulate best practice (avoid repeating past mistakes); provide a framework for quality assurance checks; give continuity (new staff can understand the organisation via its standards).

Common problems with standards: seen as outdated/irrelevant by engineers; too much bureaucratic form-filling; tedious manual maintenance if unsupported by tools. Good standards development involves practitioners, is reviewed regularly, and has tool support.

### ISO's three-part quality approach

| ISO activity | Description |
| --- | --- |
| Quality Planning | Identify which quality standards are relevant and how to satisfy them |
| Quality Assurance | Regularly evaluate overall project performance to confirm standards will be met |
| Quality Control | Monitor specific results against standards; eliminate causes of unsatisfactory performance |

ISO 9000 is an international family of quality management standards, applicable from manufacturing to service industries. ISO 9001 applies specifically to organisations that design, develop, and maintain products — it is a generic model that each organisation must instantiate for itself.

### Documentation standards

- Documentation PROCESS standards — how documents should be developed, validated, maintained

- Document standards — document content, structure, and appearance

- Document interchange standards — compatibility of electronic documents between systems, plus archiving so documents remain accessible even after the tools that created them become obsolete

## B.6 Quality control: reviews

Quality control involves two main approaches: quality reviews, and automated software assessment/measurement.

### Quality reviews

A group examines part or all of a process, product, or its documentation to find potential problems. Types of review include:

- Inspections — for defect removal (product-focused)

- Progress-assessment reviews — product and process

- Quality reviews — product measured against standards

A design review is a formal, documented, comprehensive, systematic examination of a design to evaluate whether it meets its requirements and to identify/propose solutions to any gaps — a necessary step wherever a project has a design phase.

Review teams should be small and reviews fairly short; records must always be kept. Comments raised during a review are typically classified as:

| Outcome | Meaning |
| --- | --- |
| No action | No change to software/documentation required |
| Refer for repair | Designer/programmer must correct an identified fault |
| Reconsider overall design | Problem impacts other parts of the design — needs a cost-effective overall judgement |
| Refer to client | Requirements/specification errors that need client input |

## B.7 The Capability Maturity Model (CMM)

Developed by the Software Engineering Institute (SEI), CMM characterises an organisation's maturity in terms of its commitment to defined processes. It has since evolved into CMM-Integration (CMMI). Five maturity levels:

| Level | Name | Character |
| --- | --- | --- |
| 1 | Initial | Ad-hoc, sometimes chaotic; success depends on individual heroics |
| 2 | Repeatable | Disciplined process — basic project management controls in place |
| 3 | Defined | Standard, consistent process used organisation-wide |
| 4 | Managed | Predictable process — quantitatively measured and controlled |
| 5 | Optimizing | Continuously improving process |

### Key Process Areas (KPAs) by level

- Level 2 (Repeatable): Requirements management, project planning & tracking, subcontractor management, quality assurance management, configuration management

- Level 3 (Defined): Organisation process focus & definition, training program, integrated software management, software product engineering, intergroup coordination, peer reviews

- Level 4 (Managed): Quantitative process management, software quality management

- Level 5 (Optimizing): Defect prevention, technology change management, process change management

To reach a given level, an organisation must demonstrate it addresses ALL key process areas defined for that level. Each level builds on the previous ones.

### Metrics used to track maturity/quality

- Financial status — Earned Value

- Technical progress — LOC under baseline, closed change requests, defects found, use cases demonstrated

- Stability — rate of new change requests over time (should decline as the system stabilises)

- Modularity — 'breakage' (impact of a change on the baseline) should decrease as architecture matures

- Maturity — Mean Time Between Failures should increase (fewer defects found) as the project nears delivery

## B.8 Project and quality audits

An audit is an independent review and examination of records and activities to assess the adequacy of controls, ensure compliance with policies/procedures, and recommend necessary changes. The main aim is to reduce uncertainty.

| Audit type | Focus |
| --- | --- |
| General project audit | Determine the overall status of the project |
| Quality audit | Determine how closely processes adhere to standards and products match requirements |

### Who audits?

- Internal auditor — company employee; reports directly to the Board/top management to preserve independence

- External auditor — independent staff brought in from outside the organisation

Auditors must always be independent from and external to the group being audited (though they may still be internal to the wider organisation), to avoid bias. A small team of three or four skilled people is typical.

### Purpose of a project audit

- Determine if the project is on-track or not

- If off-track, determine why and recommend how to recover it (or whether it should be cancelled)

- Determine whether the causes are systemic, and how to avoid them in future projects

### When and how audits happen

Audits are usually short — as little as a day, but typically 2–3 weeks. They may be planned from project start, or triggered because a project appears to be in difficulty. Unlike financial audits, project auditors are often expected to make recommendations, not just report facts.

### The six phases of an audit

| Phase | Activity |
| --- | --- |
| 1. Initiation & planning | Agree the purpose, constraints, and terms of reference |
| 2. Establish baseline | Determine what was expected at this point per the contract and agreed changes |
| 3. Investigation | Gather facts; identify who to interview; record sources |
| 4. Analysis | Draw conclusions from the gathered data |
| 5. Report & present | Report conclusions to the requester and agreed parties |
| 6. Termination | Evaluate the audit itself |

### Structure of an audit report

- Executive Summary

- Audit Focus — a clear statement of what was audited (e.g. project plan, WBS, schedule; core deliverables)

- Basis of Opinion — the standard/framework the audit was conducted against (e.g. PMBOK)

- Audit Findings — objective, provable statements of fact, not personal opinion; must be reproducible by any similarly qualified auditor

- Recovery Plan — if the project continues, what can and cannot be carried forward, stated honestly

- Documents and References used

Audit findings must stick strictly to what can be proven — a professional (objective) opinion rather than a personal (subjective) one.

## Video & reading resources — Quality

- What is Capability Maturity Model (CMM)? — TechTarget reference: https://www.techtarget.com/it-infrastructure/definition/What-is-Capability-Maturity-Model-CMM

- GeeksforGeeks — Capability Maturity Model (CMM) reference notes: https://www.geeksforgeeks.org/software-engineering/software-engineering-capability-maturity-model-cmm/

- The Capability Maturity Model and ISO 9000 Standards — comparison reading: https://www.umsl.edu/~sauterv/analysis/488_f01_papers/albright.htm

- COCOMO 2 Model in Software Engineering Explained (context for how estimation ties into quality/process maturity): https://www.youtube.com/watch?v=cyjTH-cGL-Y

# Quick-Revision Summary

| Topic | Key idea |
| --- | --- |
| LOC estimation | Historical rate × estimated KLOC → effort/cost/docs/errors/defects/people |
| Function Point Analysis | Count 5 component types by complexity, weight and sum → UFP; adjust by Technical Complexity Factor (14 GSCs) → FP |
| COCOMO '81 Basic | E = a×(KLOC)^b, D = c×(E)^d, per project mode (Organic/Semi-detached/Embedded) |
| COCOMO '81 Intermediate | Basic effort × EAF, where EAF = product of up to 15 cost driver ratings |
| Quality | Totality of features meeting stated/implied needs — functional + non-functional requirements |
| Quality planning/assurance/control | Select standards -> confirm project will meet them -> monitor & enforce compliance |
| ISO 9001 | Generic quality-process standard organisations must instantiate for their own context |
| CMM | 5 maturity levels: Initial, Repeatable, Defined, Managed, Optimizing — each with Key Process Areas |
| Quality reviews | Group examination to find defects; outcomes: no action / repair / reconsider design / refer to client |
| Audits | Independent, formal 6-phase examination to reduce uncertainty about project or quality status |

## Exam-style self-check questions

- Given historical LOC-based multipliers, calculate effort, budget, and documentation for a new estimated LOC count.

- Given counts of inputs/outputs/inquiries/files/interfaces by complexity, calculate the Unadjusted Function Point count and then apply the Technical Complexity Factor to get FP.

- Given a project mode (Organic/Semi-detached/Embedded), KLOC, and a set of cost driver ratings, calculate Basic and Adjusted COCOMO effort and development duration.

- Explain the difference between quality planning, quality assurance, and quality control.

- List the five CMM maturity levels and give one Key Process Area for each of levels 2–5.

- Describe the six phases of a project audit and what an audit report should contain.

- Explain why quality management should be kept separate from project management.

Compiled from the PFD473S 2026 Subject Guide, the Software Estimation and Quality lecture slides, and the in-class Software Estimation exercises, plus the resources linked throughout this document.