## WBS Dictionary
WORK BREAKDOWN STRUCTURE
| PROJECT TITLE | PROJECT MANAGER
| Automated Restaurant Ordering System | Moipone Kabai
TASK ID | TASK | DEPENDENT UPON | TASK OWNER | TASK DESCRIPTION | ESTIMATED COST | BEGIN DATE | ESTIMATED DATE OF COMPLETION | ACTUAL DATE OF COMPLETION
1 | Automated Restaurant Ordering System
1.1 | Initiation | 1 | Project Manager | The work to initiate the project. | 34000 | 2020-06-01 | 2020-06-12 | 2020-06-11
1.1.1 | Evaluation & Recommendations | 1.2.2 | Technical team | Working group to evaluate solution sets and make recommendations. | 10000 | 2020-06-01 | 2020-06-03 | 2020-06-03
1.1.2 | Develop Project Charter |  | Project Manager | Project Manager to develop the Project charter. | 15000 | 2020-06-04 | 2020-06-05 | 5 hun 2020
1.1.3 | Deliverable: Submit Project Charter |  | Project Manager | Project charter is delivered to the Project Sponsor. | 3000 | 2020-06-08 | 2020-06-08 | 2020-06-08
1.1.4 | Project Sponsor Reviews Project Charter |  | Project Sponsor | Project Sponsor reviews the Project charter. | 3000 | 2020-06-09 | 2020-06-10 | 2020-06-10
1.1.5 | Project Charter Signed/Approved |  | Project Sponsor | The Project Sponsor signs the Project charter which authorizes the Project Manager to move to the Planning process. | 3000 | 2020-06-11 | 2020-06-11 | 2020-06-11
1.2 | Planning |  | Project Manager | The work for the planning process for the project. | 101000 | 2020-06-12 | 2020-07-17 | 2020-07-14
1.2.1 | Create Initial Scope Statement |  | Project Manager | Project Manager creates an Initial Scope Statement | 20000 | 2020-06-12 | 2020-06-19 | 2020-06-19
1.2.2 | Determine Project Team |  | Project Manager | The Project Manager determines the project team and requests the resources. | 50000 | 2020-06-22 | 2020-06-30 | 2020-06-26
1.2.3 | Project Team Kickoff Meeting |  | Project Manager, Technical team & Project Sponsor | The planning process is officially started with a project kickoff meeting. | 5000 | 2020-06-29 | 2020-06-29 | 2020-06-29
1.2.4 | Develop Project Plan | 1.2.1 | Technical team | Under the direction of the Project Manager the team develops the project plan. | 20000 | 2020-06-30 | 2020-07-10 | 2020-07-09
1.2.5 | Submit Project Plan | 1.2.4 | Project Manager | Project Manager submits the project plan for approval. | 3000 | 2020-07-10 | 2020-07-10 | 2020-07-10
1.2.6 | Milestone: Project Plan Approval |  | Project Manager | The project plan is approved and the Project Manager has permission to proceed to execute the project according to the project plan. | 3000 | 2020-07-14 | 2020-07-14 | 2020-07-14
1.3 | Development |  | Software developer | The work to start development process. | 205000 | 2020-07-15 | 2020-10-02 | 2020-10-02
1.3.1 | Project development planned | 1.2.6 | Software developer | The project plan and requirements are given to the developer to start creating the system. | 30000 | 2020-07-15 | 2020-07-17 | 2020-07-17
1.3.2 | Verify & validate user requirements | 1.2.6 | Project Manager, Technical team & Project Sponsor | The original user requirements is reviewed by the project manager and team, then validated with the users/stakeholders. This is where additional information is added. | 15000 | 2020-07-20 | 2020-07-22 | 2020-07-22
1.3.3 | Additional ammends to the requirements |  | Software developer | The project plan and requirements are given to the developer to start creating the system. | 15000 | 2020-07-23 | 2020-07-24 | 2020-07-24
1.3.4 | Design System outlook |  | Software developer | The project architecture is discussed | 30000 | 2020-07-27 | 2020-07-31 | 2020-07-31
1.3.5 | Develop the software front end |  | Software developer | Project application GUI is being develped. | 30000 | 2020-08-03 | 2020-08-14 | 2020-08-14
1.3.6 | Develop the software back end functionality |  | Software developer | Project application functionality is developed. | 40000 | 2020-08-17 | 2020-09-18 | 2020-09-18
1.3.7 | Test the software product | 1.4.3 | Software tester & User | Check bugs in the system and dunctionality. | 35000 | 2020-09-21 | 2020-09-30 | 2020-09-30
1.3.8 | Aprove the application |  | Project Manager, Technical team & Project Sponsor | The stakeholders are are all satisfied with the developed product. | 10000 | 2020-10-01 | 2020-10-02 | 2020-10-02
1.4 | Execution |  | Project Manager, Technical team & Project Sponsor | Work involved to execute the project. | 160000 | 2020-10-05 | 2020-11-13 | 2020-11-13
1.4.1 | Project Kickoff Meeting |  | Project Manager | Project Manager conducts a formal kick off meeting with the project team, project stakeholders and project sponsor. | 5000 | 2020-10-05 | 2020-10-05 | 2020-10-05
1.4.2 | Procure Hardware/Software |  | Hardware technician | The procurement of all hardware, software and facility needed for the project. | 40000 | 2020-10-06 | 2020-10-09 | 2020-10-09
1.4.3 | Install Development System |  | Hardware technician | Team installs a development system for testing and customizations of user interfaces. | 30000 | 2020-10-12 | 2020-10-14 | 2020-10-14
1.4.4 | Testing Phase | 1.3.7 | Software tester & User | The system is tested with a select set of users. | 35000 | 2020-10-15 | 2020-10-30 | 2020-10-30
1.4.5 | Install Live System |  | Hardware technician | The actual system is installed and configured. | 30000 | 2020-11-02 | 2020-11-04 | 2020-11-04
1.4.6 | User Training |  | Technical leader | All users and managers are provided with training classes to cover advanced reporting. | 10000 | 2020-11-05 | 2020-11-13 | 2020-11-12
1.4.7 | Go Live | 1.5.1 | Technical leader | System goes live with all users. | 10000 | 2020-11-13 | 2020-11-13 | 2020-11-13
1.5 | Project completion | 1.3.8 | Project Stakeholders | Work involved in completion of the project. | 75000 | 2020-11-16 | 2020-11-27 | 2020-11-26
1.5.1 | Project Management |  | Project Stakeholders | Overall project management for the project. | 20000 | 2020-11-16 | 2020-11-18 | 2020-11-18
1.5.2 | Risk Management |  | Pjoject Manager | Risk management efforts as defined in the Risk Management Plan. | 35000 | 2020-11-19 | 2020-11-20 | 2020-11-20
1.5.3 | Audit Procurement |  | Technical leader & Hardware technician | An audit of all hardware and software procured for the project, ensures that all procured products are accounted for and in the asset management system. | 15000 | 2020-11-23 | 2020-11-25 | 2020-11-25
1.5.4 | Formal Acceptance |  | Project Sponsor | The Project Sponsor formally accepts the project by signing the acceptance document included in the project plan. | 5000 | 2020-11-26 | 2020-11-26 | 2020-11-26
|  |  |  | ESTIMATED TOTAL | 575000
CLICK HERE TO CREATE IN SMARTSHEET

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.