## Slide 1
Developing the Schedule

## Slide 2: Chapter Concepts
Estimating the resources required for each activity
Estimating the duration for each activity
Establishing the estimated start time and required completion time for the overall project
Calculating the earliest times at which each activity can start and finish, based on the project estimated start time
Calculating the latest times by which each activity must start and finish in order to complete the project by its required completion time
Determining the amount of positive or negative slack between the time each activity can start or finish and the time it must start or finish
Identifying the critical (longest) path of activities
Performing the steps in the project control process
Determining the effects of actual schedule performance on the project schedule
Incorporating changes into the schedule
Developing an updated project schedule
Determining approaches to controlling the project schedule
Implementing agile project management

## Slide 3: Learning Outcomes
Estimate the resources required for activities
Estimate the duration for an activity
Determine the earliest start and finish times for activities
Determine the latest start and finish times for activities
Explain and determine total slack
Prepare a project schedule
Identify and explain the critical path
Discuss the project control process
Develop updated schedules based on actual progress and changes
Discuss and apply approaches to control the project schedule
Explain agile project management

## Slide 4: Project Integration Management Project Time Management
Project Management Knowledge Areas from PMBOK® Guide

## Slide 5: Estimate Activity Resources
Resources include
  People, materials, equipment, facilities
Influence on the duration
  Availability of the resources
  Types of resources
  Sufficient quantities of resources for the activity durations
  Potential conflicts with other projects may cause
Involve person with expertise in resource estimate
Estimates influence costs

## Slide 6: Estimate Activity Durations
Duration must be the total elapsed time
  Time for the work to be done plus any associated waiting time

## Slide 7: Estimate Activity Durations

## Slide 8: Establish Project Start and Completion Times
Define the overall window for project completion
May not want to commit to a specific date
  Project not to start until customer has approved the contract
  Delay in contract signing may impact project start
Set finish time as number of days from project start

## Slide 9: Develop Project Schedule
Prior activities for schedule development
  Estimate duration of each activity
  Establish overall window of time for the project
Develop the schedule timetable
  Earliest start and finish times based on estimated start date
  Latest start and finish times based on required completion date

## Slide 10: Earliest start and finish times
Earliest start time (ES)
  Earliest time at which a specific activity can begin
Earliest finish time (EF)
  Earliest time by which a specific activity can be completed
EF = ES + Estimated duration
Calculate forward through the network diagram

## Slide 11: Earliest start and finish times calculation
Why is the ES for 'Dress rehearsal’ 10?

## Slide 12: 'Identify target consumers'
Start date = 0
ES = Start date = 0
Duration = 3
EF = 0 + 3 = 3

## Slide 13: 'Develop draft questionnaire'
ES = EF Task 1 = 3
Duration = 10
EF = 3 + 10 = 13

## Slide 14: 'Pilot-test questionnaire'
ES = EF Task 2 = 13
Duration = 20
EF = 13 + 20 = 33

## Slide 15: 'Review comments & finalise questionnaire'
ES = EF Task 3 = 33
Duration = 5
EF = 33 + 5 = 38

## Slide 16: 'Prepare mailing labels’, 'Print questionnaire’, 'Develop data analysis software’, and 'Develop software test data'
ES = EF Task 4 = 38
Task 5
  Duration = 2
  EF = 38 + 2 = 40
Task 6
  Duration = 10
  EF = 38 + 10 = 48
Task 7
  Duration = 12
  EF = 38 + 12 = 50
Task 8
  Duration = 2
  EF = 38 + 2 = 40

## Slide 17: 'Mail questionnaire & get responses'
Latest of Tasks 5 and 6 = 48
ES = EF Task 6 = 48
Duration = 65
EF = 48 + 65 = 113

## Slide 18: 'Test software'
Latest of Tasks 7 and 8 = 50
ES = EF Task 7 = 50
Duration = 5
EF = 50 + 5 = 55

## Slide 19: 'Input response data'
Latest of Tasks 9 and 10 = 113
ES = EF Task 9 = 113
Duration = 7
EF = 113 + 7 = 120

## Slide 20: 'Analyse results'
ES = EF Task 11 = 120
Duration = 8
EF = 120 + 8 = 128

## Slide 21: 'Prepare report'
ES = EF Task 12 = 128
Duration = 10
EF = 128 + 10 = 138
Project not complete in required time

## Slide 22: Schedule table ES and EF

## Slide 23: Latest start and finish times
Latest start time (LS)
  Latest time by which a specific activity must be started
Latest finish time (LF)
  Latest time by which a specific activity must be completed
LS = LF – Estimated duration
Calculate backward through the network diagram

## Slide 24: Latest start and finish times calculation
Why is the LF for 'Print posters & brochures' 20?

## Slide 25: 'Prepare report'
Required completion = 130
LF = Complete date = 130
Duration = 10
LS = 130 – 10 = 120

## Slide 26: 'Analyse results'
LF = LS Task 13 = 120
Duration = 8
LS = 120 – 8 = 112

## Slide 27: 'Input response data'
LF = LS Task 12 = 112
Duration = 7
LS = 112 – 7 = 105

## Slide 28: 'Test software' and 'Mail questionnaire & get responses'
LF = LS Task 11 = 105
Task 9
  Duration = 65
  LS = 105 – 65 = 40
Task 10
  Duration = 5
  LS = 105 – 5 = 100

## Slide 29: 'Develop data analysis software' and 'Develop software test data'
LF = LS Task 10 = 100
Task 7
  Duration = 12
  LS = 100 – 12 = 88
Task 8
  Duration = 2
  LS = 100 – 2 = 98

## Slide 30: 'Prepare mailing labels' and 'Print questionnaire'
LF = LS Task 9 = 40
Task 5
  Duration = 2
  LS = 40 – 2 = 38
Task 6
  Duration = 10
  LS = 40 – 10 = 30

## Slide 31: 'Review comments & finalise questionnaire'
LF = Earliest LS of Tasks 5, 6, 7, and 8 = 30
LF = LS Task 6 = 30
Duration = 5
LS = 30 – 5 = 25

## Slide 32: 'Pilot-test questionnaire'
LF = LS Task 4 = 25
Duration = 20
LS = 25 – 20 = 5

## Slide 33: 'Develop draft questionnaire'
LF = LS Task 3 = 5
Duration = 10
LS = 5 – 10 = -5

## Slide 34: 'Identify target consumers'
LF = LS Task 2 = -5
Duration = 3
LS = -5 – 3 = -8
Start date = 0
Project is 8 days late at start

## Slide 35: Schedule table LS and LF

## Slide 36: Total slack
Sometimes called float
The difference between EF time of last activity and the project required completion time
Negative slack
  Lack of slack over the entire project
  Amount of time an activity must be accelerated
Positive slack
  Maximum amount of time that the activities on a particular path can be delayed without jeopardising on-time completion

## Slide 37: Critical path
Longest path in the overall network diagram
Find which activities have the least amount of slack

## Slide 38: Critical path through a project

## Slide 39: Critical path through a project

## Slide 40: Critical path through a project

## Slide 41: Change in slack for critical path

## Slide 42: Free slack
Time a specific activity can be postponed without delaying the ES of its immediate successor activities
Calculation
  Find lowest of the values of total slack for all the activities entering into a specific activity
  Subtract value from the values of total slack for the other activities also entering into that same activity

## Slide 43: Total slack compared to free slack
Total slack for Activity 7 = 50
Total slack for Activity 8 = 60
Free slack for Activity 8 = 60 – 50 = 10 days

## Slide 44: Bar chart format
Gantt chart tool for planning and scheduling
Activities on side
Time scale on top or bottom
Estimated duration in bars
Automatically generated in software systems
Can show relationships between activities

## Slide 45: Project Control Process
Meetings occur regularly
Gather data on actual performance
Record changes
Monitor progress

## Slide 46: Effects of Actual Schedule Performance
Part (a) Total slack = +5
Part (b) Total slack = +2

## Slide 47: Incorporate Changes into Schedule
Changes may impact the schedule
  Initiated by customer or project team
  Result from unanticipated occurrence
Early change may have less impact than later change
Manage requested changes
  Estimate impact
  Obtain customer approval
  Revise project plan, schedule, and costs

## Slide 48: Update Project Schedule
Generate forecasts for project finish
  Use actual finish dates of completed activities
  Enter project changes
  Update project schedule
Determine if any changes occur in critical path

## Slide 49: Control Schedule
Schedule control steps
Analyse the schedule for needed corrective action
Decide specific corrective actions to be taken
Revise the plan to incorporate corrective actions
Recalculate the schedule to evaluate the effects of the planned corrective actions
Actions
Repeat steps if not acceptable results
Apply efforts to paths with negative slack
  Near-term activities
  Long estimated durations
Change may shift critical path
Trade-off of costs and scope

## Slide 50: Scheduling for Information Systems Development
Common problems
  Failure to identify all user requirements
  Failure to identify user requirements properly
  Continuing growth of project scope
  Underestimating learning curves for new software packages
  Incompatible hardware
  Logical design flaws
  Poor selection of software
  Failure to select the best design strategy
  Data incompatibility issues
  Failure to perform all phases of the SDLC

## Slide 51: IS example: activities, predecessors, durations

## Slide 52: IS example: ES and EF times

## Slide 53: IS example: LS and LF times

## Slide 54: IS example: schedule table

## Slide 55: IS example: critical path

## Slide 56: IS example: updated network diagram

## Slide 57: IS example: updated schedule table

## Slide 58: Project Management Information Systems
Most systems perform scheduling functions
Calculates at click of the mouse
  ES, EF, LS, and LF
  Total slack
  Critical path
Perform control functions

## Slide 59: Agile Project Management
Scrum approach participants
Product owner
Development team
Scrum master
Process includes
Establish and authorise
Define requirements
Conduct daily scrum meetings
Conduct sprint review meeting
Conduct sprint retrospective meeting

## Slide 60: Critical Success Factors
The person who will be responsible for performing the activity should estimate the duration for that activity. This generates commitment from the person.
The estimated duration for an activity must be based on the types and quantities of resources required to perform the activity.
Activity estimated durations should be aggressive yet realistic.
Activities should not be longer in estimated duration than the time intervals at which the actual progress will be reviewed and compared to planned progress.
Project management involves a proactive approach to controlling a project to ensure that the project objective is accomplished even when things do not go according to plan.
Once the project starts, it is important to monitor progress to ensure that everything is going according to plan.
The key to effective project control is measuring actual progress and comparing it to planned progress on a timely and regular basis and taking any needed corrective action immediately.
The key to effective schedule control is to address any paths with negative or deteriorating slack values aggressively as soon as they are identified. A concentrated effort to accelerate project progress must be applied to these paths.

## Slide 61: Critical Success Factors (continued)
The amount of negative slack should determine the priority for applying these concentrated efforts.
When attempting to reduce the duration of a path of activities that has negative slack, focus on activities that are near term and on activities that have long estimated durations.
Addressing schedule problems early will minimise the negative impact on scope and budget.
If a project falls too far behind, getting it back on schedule becomes more difficult, and usually requires spending more money or reducing the scope or quality.
If corrective actions are necessary, decisions must be made regarding a trade-off of scope, time, and cost.
A regular reporting period should be established for comparing actual progress to planned progress.
The shorter the reporting period, the better the chances of identifying problems early and taking corrective actions.
During each reporting period, data on actual performance and information on changes to the project scope, schedule, and budget need to be collected in a timely manner and used to calculate an updated schedule and budget.

## Slide 62: Summary
The scheduling function depends on the planning function.
The estimated types and quantities of resources required for an activity, together with the availability of those resources, will influence the estimated duration for how long it will take to perform the activity.
The estimated duration for each activity must be the total elapsed time – the time for the work to be done plus any associated waiting time.
The estimate should be aggressive yet realistic.
It may be easier to estimate the durations for near-term activities, but as the project progresses, the project team can progressively elaborate the estimated the durations as more information becomes known to allow for more accurate estimated durations.
A project schedule provides a timetable for each activity and shows the earliest start (ES) and earliest finish (EF) times and the latest start (LS) and latest finish (LF) times for each activity.
The total slack for a particular path of activities through the network is common to and shared among all activities on that path.

## Slide 63: Summary (continued)
The critical path is the longest (most time-consuming) path of activities in the network diagram.
The key to effective project control is measuring actual progress and comparing it to planned progress on a timely and regular basis and taking any needed corrective action immediately.
Actual progress – whether faster or slower than planned – will have an effect on the schedule of the remaining, incomplete activities of the project.
Any type of change – whether initiated by the customer, the contractor, the project manager, a team member, or an unanticipated event – will require a modification to the plan in terms of scope, schedule, and/or budget.
Schedule control involves four steps: analysing the schedule to determine which areas may need corrective action, deciding what specific corrective actions should be taken, revising the plan to incorporate the chosen corrective actions, and recalculating the schedule to evaluate the effects of the planned corrective actions.
One of the most important factors in effective scheduling is estimating activity durations that are as realistic as possible.