| SUBJECT PROJECT MANAGEMENT III (PRM370/PRM371S/ PRM372S) | DATE CLASS TEST 2 MAY 13 2022 | TOTAL MARKS 100 | DURATION 2 HOURS |
| --- | --- | --- | --- |

FACULTY OF INFORMATICS AND DESIGN

DIPLOMA: INFORMATION & COMMUNICATION TECHNOLOGY [DPICTA/C/M]

FULL-TIME

COURSE:

OFFERING:

SPECIAL INSTRUCTIONS

- This is NOT an open book test.

- Diagram must be completed using Microsoft word function/any other suitable software.

- Answer all questions in the answer book using the answer sheet provided.

- Read the Scenario and questions from beginning to end before attempting any question.

REQUIREMENTS

- After completion convert your text to a pdf file (This will prevent the diagram from being distorted, use any suitable software or free online PDF Converters).

- Calculator.

- At conclusion, name the file PRM2022(Course code) – SURNAME – NAME – STD NO.pdf

- Upload the completed test as an assignment on Blackboard using the link provided as instructed within the stipulated time (You will have 5 minutes to upload and submit after the test ends at 16:00).

- You have 2 attempts to upload the submission, please use it wisely as there will be no further opportunity.

# CASE STUDY: E-COMMERCE FOR A SMALL SUPERMARKET

Thabo and Beatrice own a small supermarket in a coastal town with a large and growing elderly population. Because of their location, they don’t have any competition from the large chain stores. A small private FET college, with about 1,500 students, is also located in the town.

# Part 1 - DISCUSSION BEFORE INITIATION

‘‘I think we need a website for our store,’’ Thabo tells Beatrice. ‘‘Why?’’ asks Beatrice.

‘‘Everybody has one. It’s the wave of the future,’’ responds Thabo.

‘‘I’m still not clear, Thabo. What would be on our website?’’ Beatrice asks.

‘‘Well, for one thing we could have a picture of our market with me and you standing in front of it,’’ says Thabo.

‘‘What else?’’ asks Beatrice.

Thabo answers, ‘‘Maybe people could look up stuff and order it through the website. Yeah, those college kids would think that’s great; they’re into using computers all the time. That will increase our business. They’ll buy food from our store rather than the take-aways they always eat or get delivered from Sam’s Curry Shop. And those people who live in the senior citizens’ home would use it too. I heard they’re teaching them how to use computers. And maybe we can even set up a delivery service.’’

‘‘Hold on,’’ says Beatrice. ‘‘Those college students get takeaways from Sam’s at all hours of the night. Long after we’re closed. And I think the older people enjoy getting out to eat every now and then. They have a van that brings some of them here each day to shop; and they really  don’t buy much anyway. And how will they pay for what they order through the website? I’m   all for keeping up with things, but I’m not sure this makes sense for our little supermarket, Thabo. What would we be trying to accomplish with a website?’’

‘‘I just explained it to you, Beatrice. It’s the way all businesses are going. We either keep up with things or we’ll be out of business,’’ replies Thabo.

‘‘Does this have anything to do with that Chamber of Commerce meeting you went to in Durban last week, where you said they had some consultant talking about e-business or something?’’ asks Beatrice.

‘‘Yeah, maybe,’’ Thabo says. ‘‘I think I’ll give him a call and tell him to stop by and tell him what    I want.’’

‘‘How much is all this going to cost us, Thabo?’’ asks Beatrice.

‘‘I think we need to think about this some more. You know we are probably going to have to pave the parking lot this summer.’’ Thabo answers,

‘‘Don’t worry. It’ll all work out. Trust me. Our business will increase so much, it’ll pay for itself in no time. Besides, it  can’t cost  that much; this consultant probably does these kinds of projects  all the time.’’

# Part 2 - AFTER CONSULTANT ASSISTED THE BUSINESS

After meeting with the consultant, Mr Khumalo, the requirements and scope for the project has been clearly defined. Thabo and Beatrice are now convinced of the need for a website that will also have an e-commerce component.

The consultant has given them two options. They can hire some expert programmers and then manage the support themselves, or alternatively, they can contract a consulting firm to run the site on their behalf.

Mr Khumalo has conducted detailed market research and feels that the e-commerce implementation can provide the following profit growth:

| PERIOD | BUILD | CONTRACT OUT |
| --- | --- | --- |
| First Year (Period 0) | 0 | 20,000 |
| Second Year (Period 1) | 40,000 | 40,000 |
| Third Year (Period 2) | 45,000 | 40,000 |
| Fourth Year (Period 3) | 50,000 | 45,000 |
| Fifth Year (Period 4) | 60,000 | 50,000 |

Mr Khumalo has approached all the consultants and he has obtained fixed pricing for the implementation of the two options. The costs are:

| PERIOD | BUILD | CONTRACT OUT |
| --- | --- | --- |
| First Year (Period 0) | 100,000 | 60,000 |
| Second Year (Period 1) | 10,000 | 40,000 |
| Third Year (Period 2) | 10,000 | 40,000 |
| Fourth Year (Period 3) | 6,000 | 45,000 |
| Fifth Year (Period 4) | 6,000 | 20,000 |

All parties agree that the choice of the approach to be taken will be based on the outcome of the NPV calculation. The internal rate of return is set at 8%.

# Part 3 - IMPLEMENTATION

After much consultation, the project manager presented the work breakdown structure for the project.

The tasks are listed along with the estimated duration.

# PROJECT: E-COMMERCE FOR A SMALL SUPERMARKET

Work Breakdown Structure

| Activity Number | Activity | Duration | Activity Predecessor |
| --- | --- | --- | --- |
| 1 | Gather data | 5 |  |
| 2 | Study Feasibility | 4 |  |
| 3 | Prepare Project Definition Report | 1 | 1,2 |
| 4 | Interview Users | 6 | 3 |
| 5 | Study Existing System | 10 | 3 |
| 6 | Define User Requirements | 6 | 4,5 |
| 7 | Prepare Systems Analysis Report | 1 | 6 |
| 8 | Input & Output | 10 | 7 |
| 9 | Design modelling | 4 | 7 |
| 10 | Processing & Database | 6 | 8 |
| 11 | Prepare Systems Design Report | 2 | 9,10 |
| 12 | Software Development | 20 | 11 |
| 13 | Hardware Development | 5 | 11 |
| 14 | Network Development | 12 | 11 |
| 15 | Hardware Testing | 5 | 13 |
| 16 | Network Testing | 5 | 14 |
| 17 | Software Testing | 10 | 12 |
| 18 | Prepare Testing Report | 3 | 15,16,17 |
| 19 | Training | 5 | 18 |
| 20 | System Conversion | 10 | 18 |
| 21 | Prepare Implementation Report | 6 | 19,20 |

For Activity 13 on the work breakdown structure, various contractors could not agree on the duration. Mr Nxumalo’s Technology Services estimated 4 days, but Stan’s Hardware Services said it would take 12 days. The project manager then solicited a third opinion, and Sparks Computing Services suggested that it would take 5 days.

The project manager suggested using the PERT estimation technique to best estimate the duration of activities in line with the approved completion duration of 90 days.

|  | QUESTION 1 – NET PRESENT VALUE AND PERT ESTIMATION | 30 MARKS |
| --- | --- | --- |
|  | The above case study addresses the challenges faced by small businesses when embarking on IT projects. Read the scenario and then answer the questions that follow below. |  |
|  | Required: |  |
| 1.1 | For the first stage of decision-making, a decision has to be made on whether to build or outsource the software. Complete the net present value (NPV) analysis in the answer sheet provided. | (42 x ½ = 21) |
| 1.2 | Which of the options is most viable to the organization in terms of potential for return on investment and why? | (4) |
| 1.3 | Which of the options is most viable to the organization in terms of potential for return on investment and why? Explain why in your opinion the management is likely to make an informed decision to invest based on the NPV valuation method. | (5) |
|  | QUESTION 2 – SCHEDULING (WORK BREAKDOWN STRUCTURE) | 30 MARKS |
|  | Using the information provided in the Work breakdown structure from the scenario provided above. |  |
|  | Required: |  |
| 2.1 | Perform a forward and back pass to calculate the early start (ES), early finish (EF), late start (LS), late finish (LF) and then calculate the float/slack for each activity. Complete the forward and back pass in the answer sheet provided. | (22x1 = 22) |
| 2.2 | Given the completion time of the project is 90 days, Explain the implication of the early finish time calculated based on the estimated duration to the project sponsor. | (4) |
| 2.3 | Explain to the sponsor what remedy if any will be required to keep the project on schedule based on the figure arrived by the estimated duration and the actual completion date. Note that the project sponsor is not willing to accept any time constraints (according to the early finish time) as the total project time | (4) |
|  | QUESTION 3 – NETWORK DIAGRAM | 25 MARKS |
|  | Required: |  |
| 3.1 | Complete the network diagram of the activities in the sheet provided below, in the correct sequence, dependency and flow. Use the insert function of Microsoft word or any other suitable application to connect the activities with directional arrows to complete the network diagram. Complete the forward and back pass in the answer sheet provided. | (25x1 = 25) |
| 3.2 | Colour code all tasks on the critical path on the network diagram. | (13) |
| 3.3 | Briefly explain the importance of a network diagram in project management to the sponsor | (2) |

NSWER SHEET FOR QUESTION 1.1

Please show all calculations and totals in the space provided (½ mark for each correct value X 42 = Total of 21 Mark)

NET PRESENT VALUE (Build)

| Year | 0 | 1 | 2 | 3 | 4 |
| --- | --- | --- | --- | --- | --- |
| Income |  |  |  |  |  |
| Expenses |  |  |  |  |  |
| 20,000 |  |  |  |  |  |
| PV |  |  |  |  |  |
| Net Present Value |  |  |

NET PRESENT VALUE (Outsource)

| Year | 0 | 1 | 2 | 3 | 4 |
| --- | --- | --- | --- | --- | --- |
| Income |  |  |  |  |  |
| Expenses |  |  |  |  |  |
| FV |  |  |  |  |  |
| PV |  |  |  |  |  |
| Net Present Value |  |  |

| Activity |  | Duration | Earliest |  | Latest |  | Slack |
| --- | --- | --- | --- | --- | --- | --- | --- |
| No | Description |  | Start | Finish | Start | Finish |  |
| 1 | Gather data | 5 |  |  |  |  |  |
| 2 | Study Feasibility | 4 |  |  |  |  |  |
| 3 | Prepare Project Definition Report | 1 |  |  |  |  |  |
| 4 | Interview Users | 6 |  |  |  |  |  |
| 5 | Study Existing System | 10 |  |  |  |  |  |
| 6 | Define User Requirements | 6 |  |  |  |  |  |
| 7 | Prepare Systems Analysis Report | 1 |  |  |  |  |  |
| 8 | Input & Output | 10 |  |  |  |  |  |
| 9 | Design modelling | 4 |  |  |  |  |  |
| 10 | Processing & Database | 6 |  |  |  |  |  |
| 11 | Prepare Systems Design Report | 2 |  |  |  |  |  |
| 12 | Software Development | 20 |  |  |  |  |  |
| 13 | Hardware Development | 5 |  |  |  |  |  |
| 14 | Network Development | 12 |  |  |  |  |  |
| 15 | Hardware Testing | 5 |  |  |  |  |  |
| 16 | Network Testing | 5 |  |  |  |  |  |
| 17 | Software Testing | 10 |  |  |  |  |  |
| 18 | Prepare Testing Report | 3 |  |  |  |  |  |
| 19 | Training | 5 |  |  |  |  |  |
| 20 | System Conversion | 10 |  |  |  |  |  |
| 21 | Prepare Implementation Report | 6 |  |  |  |  |  |

ANSWER SHEET FOR QUESTION 2.1 (Total of 22 Mark)

(All correct values in a row =1 Mark, 3/4 correct values = 0.5, 2 or less correct value = Zero)

| Gather data |  |  |
| --- | --- | --- |
| 1 |  | 5 |

| Input & Output |  |  |
| --- | --- | --- |
| 8 |  | 10 |

| System Analysis Report |  |  |
| --- | --- | --- |
| 7 |  | 1 |

| Hardware Testing |  |  |
| --- | --- | --- |
| 16 |  | 5 |

| Feasibility study |  |  |
| --- | --- | --- |
| 2 |  | 4 |

| Design modelling |  |  |
| --- | --- | --- |
| 10 |  | 4 |

| Project definition report |  |  |
| --- | --- | --- |
| 3 |  | 1 |

| Processing & Database |  |  |
| --- | --- | --- |
| 9 |  | 6 |

| Software Testing |  |  |
| --- | --- | --- |
| 15 |  | 10 |

| Systems Design Report |  |  |
| --- | --- | --- |
| 11 |  | 2 |

| Testing Report |  |  |
| --- | --- | --- |
| 18 |  | 6 |

| Interview Users |  |  |
| --- | --- | --- |
| 4 |  | 6 |

| Hardware Development |  |  |
| --- | --- | --- |
| 13 |  | 5 |

| Software Development |  |  |
| --- | --- | --- |
| 12 |  | 20 |

| Implementation Report |  |  |
| --- | --- | --- |
| 21 |  | 6 |

| Network Development |  |  |
| --- | --- | --- |
| 14 |  | 12 |

| Study Existing System |  |  |
| --- | --- | --- |
| 5 |  | 10 |

| System Conversion |  |  |
| --- | --- | --- |
| 20 |  | 10 |

| Training |  |  |
| --- | --- | --- |
| 19 |  | 5 |

| Define User Requirements |  |  |
| --- | --- | --- |
| 6 |  | 6 |

| Network Testing |  |  |
| --- | --- | --- |
| 17 |  | 5 |

| Activity |  |  |
| --- | --- | --- |
| No |  | Duration |

LEGEND

ANSWER SHEET FOR QUESTION 3.1 (Correct flow of Network diagram =25 mark; identifying critical path = 13 mark) Total of 38 Mark

You can use the next page to conveniently arrange the activities (The diagram should ideally form 2 connected parallel flow of activities based on the space)