| Student Full Name: | Student Number: |  |
| --- | --- | --- |
| Subject: PFD47XS Professional Development/Methods | Test Date: 27 March 2024 | Duration: 2 hours |

Faculty of Informatics & Design

Course:

BTech in Information Technology

| Question | Student Mark | Max. Score |
| --- | --- | --- |
| 1 |  | 20 |
| 2 |  | 20 |
| 3 |  | 20 |
| 4 |  | 20 |
|  |  | 100 |

Subject Coordinator:

Mr T. Makhurane

Lecturers / Examiners:

Mr T. Makhurane

Moderator:

Internal:

External:

Special instructions:

Answer all the questions that are written in bold. Hand-in question paper at the end of examination

Requirements:

Students should not leave within the first hour even if they have completed.

Hand-in question paper together with the answer book at the end of examination

%

Figure 1

| Question 1 |  | [20] |
| --- | --- | --- |
|  | Draw the network. AOA or AON are both acceptable. Activity; Duration; Predecessor. A; 4; -. B; 6; A. C; 5; A. D; 8; A. E; 9; B. F; 10; B. G; 6; C,E. H; 8; D. I; 3; D. J; 2; G,H. |  |
| 1.1 | Determine the Finish time for the project. | [6] |
| 1.2 | Determine the Critical Path. | [4] |
| 1.3 | For three activities not on the critical path, if any, calculate the Free Float, Independent Float and Total Float. | [10] |
| Question 2 |  | [20] |
| 2.1 | Activity; Immediate Predecessors; Optimistic; Most Likely; Pessimistic. A; -; 4; 5; 7. B; A; 1; 3; 6. C; A; 4; 5; 7. D; B; 3; 7; 10. E; B; 4; 6; 9. F; C, D; 2; 3; 5. G; E; 1; 7; 10. H; E, F; 2; 6; 8. Draw the network. AOA or AON are both acceptable. | [4] |
| 2.2 | Determine the expected finish time. | [8] |
| 2.3 | Calculate the time by which we have 95% confidence of finishing. | [4] |
| 2.4 | Calculate the probability of finishing 1 days after the expected finish time | [4] |

| Question 3 |  | [20] |
| --- | --- | --- |
| 3.1 | Define project management. | [4] |
| 3.2 | Explain the fundamental trade-off in project management. | [4] |
| 3.3 | Name four of Henri Fayol’s principles of management, and explain how they are applicable in a situation where we have a project manager leading a team of five members working on a software development project. | [12] |
| Question 4 |  | [20] |
| 4.1 | Given the information provided here and the Gantt chart layout provided below, construct a Gantt chart, by filling in the appropriate blocks on the Gantt chart with the character X on this question paper. | [20] |

| ### Activity Letter | Activity Description | ### Predecessor | Duration (days) |
| --- | --- | --- | --- |
| A | Train project team | None | 10 |
| B | Project paperwork and systems design | A | 5 |
| C | Modify purchased package | B | 5 |
| D | Manual systems flow | B | 10 |
| E | Modify in-house procedures | B | 15 |
| F | Test and implement modifications to purchased package | C | 15 |
| G | Test and implement manual | D | 15 |
| H | Test and implement modifications to in-house procedures | E | 5 |

Given this resource sheet

| Resource | Cost/Hour |
| --- | --- |
| Trainer | R50.00 |
| Application Domain Specialist | R40.00 |
| Solution Domain Specialist | R40.00 |
| Project Manager | R20.00 |
| Tester | R30.00 |

And this task assignment List

| Task | Resources Assigned |
| --- | --- |
| - Train Project Team | Trainer |
| - Project Management Paperwork | Project Manager |
| - Modify Purchased Package | Solution Domain Specialist, Application Domain Specialist |
| - Manual systems Flow | Project Manager |
| - Modify In-House Procedures | Project Manager, Solution Domain Specialist |
| - Test and Implement Modifications to Purchased Package | Tester, Solution Domain Specialist |
| - Test and Implement Manual Systems Flow | Tester |
| - Test and Implement Modifications to In-House Procedures | Tester |

Assume the following:

- There are 20 Working days per month.

- There are 8 hours per working day.

Assess the total amount of money needed to run the project.					[20]

Formulae

ED=A+4M+B6

Var= B-A62

z=x-μs

x=zs+μ

End of Test Paper