## Slide 1: PERT

## Slide 2: CPM
CPM – Critical Path Method. This this the longest path through the network where all activities have ES = LS and EF = LF. All such activities are called CRITICAL.

## Slide 3: PERT – Programme Evaluation and Review Technique
The duration is probabilistic.
It is difficult to estimate exactly how long an activity will take. So, the inventors of PERT decided to make use of 3 guesses at the duration.
From those 3 guesses they decided to calculate an average duration, which they decided to call the Expected Duration.

## Slide 4
We use the ED figures on our network to calculate the Earliest Finish Time For the project. This figure is called
We need to calculate another figure for our network which is to be called . But first, we calculate s squared .
To calculate , we add up all the variances along the Critical Path.
A Variance is calculated for each activity using the formula

## Slide 6: Now, we know z, so what next?
We need to find the probability associated with z. To do so, we need to look the probability on a table called the z-table.
Another name for the z-table is the standardized normal distribution.

## Slide 8
Predecessor |  | Optimistic | Most Likely | Pessimistic | ED | Ceiling(ED) | Variance | 
- | A | 1 | 3 | 5 | 3 | 3 | 0,44 | 
A | B | 5 | 6 | 7 | 6 | 6 | 0,11 | 
A | C | 2 | 3 | 4 | 3 | 3 | 0,11 | 
B, C | D | 1 | 5 | 7 | 4,7 | 5 | 1,00 | 
 |  |  |  |  |  |  | s^2 | 1,556
 |  |  |  |  |  |  | s | 1,247
This network tells us that on average, this project will finish at time 14. |  |  |  |  |  |  |  | 
Another way of saying that, is there is a 50% chance that the project will be finished by time 14 |  |  |  |  |  |  |  |