PFD470S/PFD471S/PFD472S

Please look up any formulas required in the lecture slides and hand in your submission the appropriate slot on Blackboard.

- Compare the estimates of effort and duration for the following 2 projects obtained using the function point approach.

| Average of past projects: | Effort | R(000) | pp. Doc. | Errors |
| --- | --- | --- | --- | --- |
| LOC 12500 FP 600 | 12 months | 521 | 300 | 45 |

Project 1: Develop a report generator for a monthly management report, 8000 LOC.

| F1 | Backup and Recovery | Significant | (4) |
| --- | --- | --- | --- |
| F2 | Data Communications | Significant | (4) |
| F3 | Distributed Processing | Significant | (4) |
| F4 | Performance Critical? | Essential | (5) |
| F5 | Run on existing, heavily used environment? | Average | (3) |
| F6 | Online data entry? | Incidental | (1) |
| F7 | Online data entry on multiple screens? | Incidental | (1) |
| F8 | Master files updated online? | Moderate | (2) |
| F9 | Inputs, outputs, files complex? | Incidental | (1) |
| F10 | Internal processing complex? | Moderate | (2) |
| F11 | Code reusable? | Average | (3) |
| F12 | Conversion and Installation? | Significant | (4) |
| F13 | Multiple installations across organizations? | Significant | (4) |
| F14 | Facilitate change and user ease of use? | Significant | (4) |

22 user inputs				classified as simple

4 user outputs				classified as simple

6 user outputs				classified as complex

0 possible user inquiries

16 files accessed			classified as complex

4 external interfaces			classified as complex

Project 2: Develop an online system to update customer records, 17000 LOC.

| F1 | Backup and Recovery | Average | (3) |
| --- | --- | --- | --- |
| F2 | Data Communications | Essential | (5) |
| F3 | Distributed Processing | No effect | (0) |
| F4 | Performance Critical? | Average | (3) |
| F5 | Run on existing, heavily used environment? | Average | (3) |
| F6 | Online data entry? | Essential | (5) |
| F7 | Online data entry on multiple screens? | Essential | (5) |
| F8 | Master files updated online? | Essential | (5) |
| F9 | Inputs, outputs, files complex? | Incidental | (1) |
| F10 | Internal processing complex? | Moderate | (2) |
| F11 | Code reusable? | Average | (3) |
| F12 | Conversion and Installation? | Moderate | (2) |
| F13 | Multiple installations across organizations? | No effect | (0) |
| F14 | Facilitate change and user ease of use? | Significant | (4) |

36 user inputs				classified as average

5 user outputs				classified as simple

48 possible user inquiries		classified as average

28 files accessed			classified as average

3 external interfaces			classified as complex

- Estimate the expected number of person-months of work and the project duration for an organic project involving 2600 lines of code.

Cost Drivers:

Product Attributes:

Required Software Reliability (RELY): Nominal (1.00)

Hardware Attributes:

Size of the Database (DATA): Nominal (1.00)

Personnel Attributes:

Analyst Capability (ACAP): High (0.85)

Programmer Capability (PCAP): High (0.88)

Project Attributes:

Application Experience (APEX): Low (1.22)

Programming Language Experience (PLEX): Low (1.19)

- Estimate the expected number of person-months of work and the project duration for an Semi-detached project involving 8000 lines of code.

Cost Drivers:

Product Attributes:

Required Software Reliability (RELY): High (1.15)

Complexity of the Product (CPLX): Nominal (1.00)

Hardware Attributes:

Size of the Database (DATA): High (1.10)

Personnel Attributes:

Analyst Capability (ACAP): High (0.85)

Programmer Capability (PCAP): High (0.88)

Project Attributes:

Application Experience (APEX): Low (1.22)

Programming Language Experience (PLEX): High (0.91)

Use of Modern Software Tools (TOOL): High (0.90).